## Sheet1
Activity ID | WBS Path | Activity Name | Original Duration | Start | Finish | DS_Funding Source | DS_Funding Status | DS_Institution | DS_WPM | Global Labor Cost [USD] | Global Non Labor Cost [USD] | Global Total Cost [USD] | Labor Cost USA [USD] | Non Labor Cost USA [USD] | Total Cost USA [USD] | Labor Cost CAN [CAD] | Non Labor Cost CAN [CAD] | Total Cost CAN [CAD] | Labor Cost EU [EUR] | Non Labor Cost EU [EUR] | Total Cost EU [EUR] | Labor Cost UK [GBP] | Non Labor Cost UK [GBP] | Total Cost UK [GBP]
DarkSide DarkSide Current |  |  | 1788 | 2016-01-01 | 2023-02-28 |  |  |  |  | 20810298.28 | 91576551.56 | 112386849.85 | 7492991.08 | 20811133.06 | 28304124.15 | 1880000 | 12565495 | 14445495 | 9137552 | 55572520 | 64710072 | 1500000 | 646000 | 2146000
DarkSide.1 (New WBS) |  |  | 2191 | 2017-01-01 | 2022-12-31 |  |  |  |  | 8908716.1 | 47303446.5 | 56212162.6 | 2063316.1 | 9031500 | 11094816.1 | 1000000 | 8693495 | 9693495 | 3814000 | 28497000 | 32311000 | 1500000 | 646000 | 2146000
DarkSide.1.01 Photo Electronics |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 7123900 | 19074700 | 26198600 | 1677000 | 1280000 | 2957000 | 0 | 0 | 0 | 3179000 | 16177000 | 19356000 | 1500000 | 0 | 1500000
DarkSide.1.01.01 SiPM |  |  | 1461 | 2017-01-01 | 2020-12-31 |  |  |  |  | 5306100 | 7483000 | 12789100 | 0 | 575000 | 575000 | 0 | 0 | 0 | 3051000 | 6280000 | 9331000 | 1500000 | 0 | 1500000
DS-1111001 | 1.01.01 | SiPM-R&D | 1461 | 01-Jan-17* | 2020-12-31 | INFN-CSN2 | Proposed | LNGS | A. Razeto | 0 | 121000 | 121000 | 0 | 0 | 0 |  |  | 0 |  | 110000 | 110000 |  |  | 0
DS-1111002 | 1.01.01 | SiPM - Protorype | 1461 | 01-Jan-17* | 2020-12-31 | INFN-CIPE-1 | Proposed | INFN-BO | E. Scapparone | 0 | 540100 | 540100 | 0 | 0 | 0 |  |  | 0 |  | 491000 | 491000 |  |  | 0
DS-1111003 | 1.01.01 | SiPM - Production | 1461 | 01-Jan-17* | 2020-12-31 | INFN-PON | Proposed | INFN-BO | E. Scapparone | 0 | 6246900 | 6246900 | 0 | 0 | 0 |  |  | 0 |  | 5679000 | 5679000 |  |  | 0
DS-1111004 | 1.01.01 | SiPM-Technician | 1461 | 01-Jan-17* | 2020-12-31 | INFN-MP | Proposed | INFN-BO | E. Scapparone | 468600 | 0 | 468600 | 0 | 0 | 0 |  |  | 0 | 426000 |  | 426000 |  |  | 0
DS-1111005 | 1.01.01 | SiPM- Packaging technician | 1461 | 01-Jan-17* | 2020-12-31 | STSFC | Proposed | INFN-BO | E. Scapparone | 1950000 | 0 | 1950000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 1500000 |  | 1500000
DS-1111006 | 1.01.01 | SiPM - Scientists | 1461 | 01-Jan-17* | 2020-12-31 | AstroCeNT | Proposed | INFN-BO | E. Scapparone | 2887500 | 0 | 2887500 | 0 | 0 | 0 |  |  | 0 | 2625000 |  | 2625000 |  |  | 0
DS-1111000 | 1.01.01 | SiPM-Fused Silica | 488 | 01-Sep-19* | 2020-12-31 | NSF Cap | Proposed | UMass | A. Pocar | 0 | 575000 | 575000 | 0 | 575000 | 575000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.01.02 Tile and Substrates |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 1317800 | 1185200 | 2503000 | 1177000 | 490000 | 1667000 | 0 | 0 | 0 | 128000 | 632000 | 760000 | 0 | 0 | 0
DS-1112000 | 1.01.02 | Tile and substrates-R&D | 2007 | 01-Jan-17* | 2022-06-30 | NSF Cap | Proposed | Princeton | G. Giovanetti | 0 | 490000 | 490000 | 0 | 490000 | 490000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1112001 | 1.01.02 | Tile and substrates-Scientists | 2007 | 01-Jan-17* | 2022-06-30 | NSF Labor | Proposed | Princeton | G. Giovanetti | 577000 | 0 | 577000 | 577000 | 0 | 577000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1112002 | 1.01.02 | Tile and substrates - Packaging at PU | 2007 | 01-Jan-17* | 2022-06-30 | NSF in kind | Proposed | Princeton | G. Giovanetti | 600000 | 0 | 600000 | 600000 | 0 | 600000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1112003 | 1.01.02 | Tile and substrates -PCB and components | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CIPE-1 | Proposed | LNGS | A. Razeto | 0 | 695200 | 695200 | 0 | 0 | 0 |  |  | 0 |  | 632000 | 632000 |  |  | 0
DS-1112004 | 1.01.02 | Tile and substrates - Technicians | 2007 | 01-Jan-17* | 2022-06-30 | INFN-MP | Proposed | LNGS | A. Razeto | 140800 | 0 | 140800 | 0 | 0 | 0 |  |  | 0 | 128000 |  | 128000 |  |  | 0
DarkSide.1.01.03 Front-end electronics |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 500000 | 1240200 | 1740200 | 500000 | 215000 | 715000 | 0 | 0 | 0 | 0 | 932000 | 932000 | 0 | 0 | 0
DS-1113000 | 1.01.03 | Front-end electronics | 2007 | 01-Jan-17* | 2022-06-30 |  | Proposed | LNGS | A. Razeto | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.01.03.01 FEB prototyping |  |  | 546 | 2017-01-01 | 2018-06-30 |  |  |  |  | 0 | 82500 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0
DS-1113100 | 1.01.03.01 | FEB prototyping | 546 | 01-Jan-17* | 2018-06-30 | INFN-CSN2 | Proposed | LNGS | A. Razeto | 0 | 82500 | 82500 | 0 | 0 | 0 |  |  | 0 |  | 75000 | 75000 |  |  | 0
DarkSide.1.01.03.02 FEB preproduction |  |  | 639 | 2020-01-01 | 2021-09-30 |  |  |  |  | 0 | 36300 | 36300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 0 | 0 | 0
DS-1113200 | 1.01.03.02 | FEB preproduction | 639 | 01-Jan-20* | 2021-09-30 | INFN-CIPE-1 | Proposed | LNGS | A. Razeto | 0 | 36300 | 36300 | 0 | 0 | 0 |  |  | 0 |  | 33000 | 33000 |  |  | 0
DarkSide.1.01.03.03 FEB production |  |  | 1826 | 2017-01-01 | 2021-12-31 |  |  |  |  | 0 | 906400 | 906400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824000 | 824000 | 0 | 0 | 0
DS-1113300 | 1.01.03.03 | FEB production -TPC | 1826 | 01-Jan-17* | 2021-12-31 | INFN-CIPE-1 | Proposed | LNGS | A. Razeto | 0 | 534600 | 534600 | 0 | 0 | 0 |  |  | 0 |  | 486000 | 486000 |  |  | 0
DS-1113301 | 1.01.03.03 | FEB production - consumables | 1826 | 01-Jan-17* | 2021-12-31 | INFN-CSN2 | Proposed | LNGS | A. Razeto | 0 | 27500 | 27500 | 0 | 0 | 0 |  |  | 0 |  | 25000 | 25000 |  |  | 0
DS-1113302 | 1.01.03.03 | FEB production - Veto | 1826 | 01-Jan-17* | 2021-12-31 | INFN-CIPE-2 | Proposed | LNGS | A. Razeto | 0 | 344300 | 344300 | 0 | 0 | 0 |  |  | 0 |  | 313000 | 313000 |  |  | 0
DarkSide.1.01.03.04 Steering Module |  |  | 1826 | 2017-01-01 | 2021-12-31 |  |  |  |  | 500000 | 215000 | 715000 | 500000 | 215000 | 715000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-1113410 | 1.01.03.04 | Steering module prototyping | 455 | 01-Jan-17* | 2018-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113411 | 1.01.03.04 | Printed circuit boards | 455 | 01-Jan-17* | 2018-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113412 | 1.01.03.04 | Run prototyping | 455 | 01-Jan-17* | 2018-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113413 | 1.01.03.04 | Argon for cryogenics test | 455 | 01-Jan-17* | 2018-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113420 | 1.01.03.04 | Steering Module preproduction | 152 | 31-Oct-20* | 2021-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113421 | 1.01.03.04 | Printed circuit boards | 152 | 31-Oct-20* | 2021-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113422 | 1.01.03.04 | Run - preproduction | 152 | 31-Oct-20* | 2021-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 4000 | 4000 | 0 | 4000 | 4000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113423 | 1.01.03.04 | Argon for cryogenics test | 152 | 31-Oct-20* | 2021-03-31 | DOE | Proposed | BNL | S. Rescia | 0 | 1000 | 1000 | 0 | 1000 | 1000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113430 | 1.01.03.04 | Steering module Production | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113431 | 1.01.03.04 | Substrates | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 0 | 8000 | 8000 | 0 | 8000 | 8000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113432 | 1.01.03.04 | Printed circuit boards | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 0 | 9000 | 9000 | 0 | 9000 | 9000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113433 | 1.01.03.04 | Run-production | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 0 | 170000 | 170000 | 0 | 170000 | 170000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113434 | 1.01.03.04 | Material burden | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 0 | 15000 | 15000 | 0 | 15000 | 15000 |  |  | 0 |  |  | 0 |  |  | 0
DS-1113435 | 1.01.03.04 | Steering module production labor | 365 | 01-Jan-21* | 2021-12-31 | DOE | Proposed | BNL | S. Rescia | 500000 | 0 | 500000 | 500000 | 0 | 500000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.01.04 Detector module integration |  |  | 1826 | 2017-01-01 | 2021-12-31 |  |  |  |  | 0 | 397100 | 397100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361000 | 361000 | 0 | 0 | 0
DS-111400 | 1.01.04 | Detector module integration | 1826 | 01-Jan-17* | 2021-12-31 | INFN-CSN2 | Secured | INFN-PI | E. Paoloni | 0 | 397100 | 397100 | 0 | 0 | 0 |  |  | 0 |  | 361000 | 361000 |  |  | 0
DarkSide.1.01.05 Motherboard characterization |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 0 | 1040600 | 1040600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 946000 | 946000 | 0 | 0 | 0
DS-111500 | 1.01.05 | Motherboard characterization | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CSN2 |  | INFN-NA | M. La Commara | 0 | 1040600 | 1040600 | 0 | 0 | 0 |  |  | 0 |  | 946000 | 946000 |  |  | 0
DarkSide.1.01.07 Optolink |  |  | 1096 | 2018-01-01 | 2020-12-31 |  |  |  |  | 0 | 5604500 | 5604500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5095000 | 5095000 | 0 | 0 | 0
DS-111700 | 1.01.07 | Optolink -Prototyping and preproduction | 1096 | 01-Jan-18* | 2020-12-31 | INFN-CSN2 | Secured | LNGS | A. Razeto | 0 | 300300 | 300300 | 0 | 0 | 0 |  |  | 0 |  | 273000 | 273000 |  |  | 0
DS-111800 | 1.01.07 | Optolink - TPC, Veto fibers + Optical driver PCB | 1096 | 01-Jan-18* | 2020-12-31 | INFN-CIPE-1 | Secured | LNGS | A. Razeto | 0 | 3348400 | 3348400 | 0 | 0 | 0 |  |  | 0 |  | 3044000 | 3044000 |  |  | 0
DS-111900 | 1.01.07 | Optolink - Receivers and Driver components | 1096 | 01-Jan-18* | 2020-12-31 | INFN-CIPE-2 | Secured | LNGS | A. Razeto | 0 | 1955800 | 1955800 | 0 | 0 | 0 |  |  | 0 |  | 1778000 | 1778000 |  |  | 0
DarkSide.1.01.08 Cabling |  |  | 1461 | 2017-01-01 | 2020-12-31 |  |  |  |  | 0 | 249700 | 249700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227000 | 227000 | 0 | 0 | 0
DS-111901 | 1.01.08 | Cabling | 1461 | 01-Jan-17* | 2020-12-31 | INFN-CSN2 | Secured | INFN-MI | M. Citterio | 0 | 249700 | 249700 | 0 | 0 | 0 |  |  | 0 |  | 227000 | 227000 |  |  | 0
DarkSide.1.01.09 Motherboard |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 0 | 468600 | 468600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426000 | 426000 | 0 | 0 | 0
DS-112000 | 1.01.09 | Motherboard | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CSN2 | Secured | INFN-BO | M. Guerzoni | 0 | 193600 | 193600 | 0 | 0 | 0 |  |  | 0 |  | 176000 | 176000 |  |  | 0
DS-112100 | 1.01.09 | Motherboard-cleaning | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CIPE-2 | Secured | LNL | G. Keppel | 0 | 275000 | 275000 | 0 | 0 | 0 |  |  | 0 |  | 250000 | 250000 |  |  | 0
DarkSide.1.01.10 SiPM power supplies |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 0 | 1061500 | 1061500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965000 | 965000 | 0 | 0 | 0
LATER1 | 1.01.10 | SiPM power supplies | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CIPE-2 | Secured | INFN-BO | A. Razeto | 0 | 1061500 | 1061500 | 0 | 0 | 0 |  |  | 0 |  | 965000 | 965000 |  |  | 0
DarkSide.1.01.11 Integrated electronics |  |  | 2007 | 2017-01-01 | 2022-06-30 |  |  |  |  | 0 | 344300 | 344300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313000 | 313000 | 0 | 0 | 0
LATER2 | 1.01.11 | Integrated electronics | 2007 | 01-Jan-17* | 2022-06-30 | INFN-CSN2 | Secured | INFN-TO | M. Rocha | 0 | 344300 | 344300 | 0 | 0 | 0 |  |  | 0 |  | 313000 | 313000 |  |  | 0
DarkSide.1.02 DarkSide-20k Inner Detector and Cryogenics |  |  | 1767 | 2017-03-01 | 2021-12-31 |  |  |  |  | 125316.1 | 9711846.5 | 9837162.6 | 125316.1 | 6212500 | 6337816.1 | 0 | 4590495 | 4590495 | 0 | 260000 | 260000 | 0 | 0 | 0
DarkSide.1.02.01 General Background Considerations (Surface and Bulk Requirements) |  |  | 442 | 2019-05-01 | 2020-07-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-120060 | 1.02.01 | Air Quality Consideration | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120080 | 1.02.01 | Radon-free Clean Room Requirements | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120100 | 1.02.01 | Resurface or Not | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120120 | 1.02.01 | Handling after Resurfaced | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120140 | 1.02.01 | MC Confirmation | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120160 | 1.02.01 | All TPC Material Certification Interfaced with Background Budget | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120020 | 1.02.01 | General Background Considerations (Surface and Bulk Requirements) | 442 | 01-May-19* | 2020-07-15 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120040 | 1.02.01 | determine radiopurity specification for relevant inner surfaces and components for DS-20k | 442 | 01-May-19* | 2020-07-15 |  |  |  | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.02 General Considerations of Clevios Coating Strategy |  |  | 454 | 2019-05-01 | 2020-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-120200 | 1.02.02 | Clevios Screening/Rn emanation measurement | 442 | 01-May-19* | 2020-07-15 |  |  | CIEMAT | R. Santorelli | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120180 | 1.02.02 | General Considerations of Clevios Coating Strategy | 454 | 01-May-19* | 2020-07-27 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120220 | 1.02.02 | Surface quality requirement certification | 442 | 02-May-19* | 2020-07-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120240 | 1.02.02 | anode/cathode before coating clevios | 442 | 03-May-19* | 2020-07-17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120260 | 1.02.02 | anode flatness requirement | 442 | 04-May-19* | 2020-07-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120280 | 1.02.02 | Wall Grooves | 442 | 05-May-19* | 2020-07-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120300 | 1.02.02 | Anode and Cathode (how to coat) | 442 | 06-May-19* | 2020-07-20 |  |  | Carleton | M. Kuzniak | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120320 | 1.02.02 | Wall Field Ring Groove (how to coat) | 442 | 07-May-19* | 2020-07-21 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120340 | 1.02.02 | Ground - bottom of vessel, external surface (how to coat) | 442 | 08-May-19* | 2020-07-22 |  |  | Carleton | M. Kuzniak | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120360 | 1.02.02 | Electrical contact connection certification | 442 | 09-May-19* | 2020-07-23 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120380 | 1.02.02 | Maximum Thickness confirmation (at contact point and field ring groove) | 442 | 10-May-19* | 2020-07-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120400 | 1.02.02 | Minimum Thickness Confirmation (anode/cathode) | 442 | 11-May-19* | 2020-07-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120420 | 1.02.02 | How to Connect | 442 | 12-May-19* | 2020-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120440 | 1.02.02 | LAr/LN2 Thermal Cycle Tests | 442 | 13-May-19* | 2020-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.03 General Considerations of the TPB Coating |  |  | 1 | 2019-05-13 | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-120460 | 1.02.03 | General Considerations of the TPB Coating | 1 | 13-May-19* | 2019-05-13 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120480 | 1.02.03 | TPB Screening | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120500 | 1.02.03 | Determine optimal TPB coating condition for bare acylic | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120520 | 1.02.03 | Determine optimal TPB coating condition on Clevios | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120540 | 1.02.03 | Reflector panels (or directly on ESR 3M foil) | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120560 | 1.02.03 | Determine Optimal Coating Condition on ESR if Chosen | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120580 | 1.02.03 | Anode and Cathode | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120600 | 1.02.03 | Facility Development if for in Vacuum Coating (Requirements included) | 1 | 13-May-19* | 2019-05-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.04 Proto-Proto TPC |  |  | 186 | 2019-05-10 | 2019-11-11 |  |  |  |  | 0 | 116000 | 116000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0
DS-120640 | 1.02.04 | TPC concuptual design | 1 | 10-May-19* | 2019-05-10 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121140 | 1.02.04 | HV feedthroughs | 1 | 10-May-19* | 2019-05-10 | NSF |  | UCLA | H. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121160 | 1.02.04 | HV connectors and cabling | 1 | 10-May-19* | 2019-05-10 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121200 | 1.02.04 | Optical fibers for signal (feedthroughs, warm fibers, cryogenic fibers) | 1 | 10-May-19* | 2019-05-10 | INFN |  | LNGS | A. Razeto | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121220 | 1.02.04 | Optical feedthrough mounting tower | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121240 | 1.02.04 | Laser system for SPE calibration | 1 | 10-May-19* | 2019-05-10 |  |  | CERN | F. Pietropaolo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121260 | 1.02.04 | PT-1000s for temperature monitoring during filling | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121280 | 1.02.04 | DAQ System | 1 | 10-May-19* | 2019-05-10 | INFN |  | INFN-Roma1 | M. Rescigno | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120620 | 1.02.04 | Proto-Proto TPC | 92 | 10-May-19* | 2019-08-09 |  | Secured | UCLA | Y. Wang | 0 | 106000 | 106000 | 0 | 40000 | 40000 |  |  | 0 |  | 60000 | 60000 |  |  | 0
DS-120660 | 1.02.04 | TPC engineering design | 1 | 2019-05-11 | 2019-05-11 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121060 | 1.02.04 | Radioactive source MC& design | 1 | 2019-05-11 | 2019-05-11 | NSF |  | UC Davis | M. Poehlmann | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121120 | 1.02.04 | TPC wiring | 1 | 2019-05-11 | 2019-05-11 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120700 | 1.02.04 | TPC supporting structure | 1 | 2019-05-12 | 2019-05-12 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120720 | 1.02.04 | Anode diving bell machine and polish | 1 | 2019-05-12 | 2019-05-12 | NSF |  | U Hawaii | J. Maricic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120800 | 1.02.04 | Acrylic field cage panels machine | 1 | 2019-05-12 | 2019-05-12 | INFN |  | INFN-BO | A. Margotti | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120860 | 1.02.04 | Acrylic reflection panels machine | 1 | 2019-05-12 | 2019-05-12 | INFN |  | INFN-BO | A. Margotti | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120920 | 1.02.04 | Acrylic cathode window machine | 1 | 2019-05-12 | 2019-05-12 | INFN |  | INFN-BO | A. Margotti | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121040 | 1.02.04 | Resistor chain fabrication | 1 | 2019-05-12 | 2019-05-12 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121080 | 1.02.04 | Radioactive source holder machine | 1 | 2019-05-12 | 2019-05-12 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121100 | 1.02.04 | Radioactive source collimator machine | 1 | 2019-05-12 | 2019-05-12 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121180 | 1.02.04 | Motion feedthroughs | 1 | 2019-05-12 | 2019-05-12 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121000 | 1.02.04 | Wire frame fabrication | 91 | 2019-05-12 | 2019-08-10 | NSF Construction Grant | Secured | Houston | A. Renshaw | 0 | 4000 | 4000 | 0 | 4000 | 4000 |  |  | 0 |  |  | 0 |  |  | 0
DS-121020 | 1.02.04 | WIre fabrication | 184 | 2019-05-12 | 2019-11-11 | NSF Construction Grant | Secured | Houston | A. Renshaw | 0 | 6000 | 6000 | 0 | 6000 | 6000 |  |  | 0 |  |  | 0 |  |  | 0
DS-120740 | 1.02.04 | Anode diving bell annealing | 1 | 2019-05-13 | 2019-05-13 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120820 | 1.02.04 | Acrylic field cage panels annealing | 1 | 2019-05-13 | 2019-05-13 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120880 | 1.02.04 | Acrylic relfection panels annealing | 1 | 2019-05-13 | 2019-05-13 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120940 | 1.02.04 | Acrylic cathode window annealing | 1 | 2019-05-13 | 2019-05-13 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120680 | 1.02.04 | TPC integration | 91 | 2019-05-13 | 2019-08-11 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120760 | 1.02.04 | Anode diving bell Clevios coating | 1 | 2019-05-14 | 2019-05-14 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120840 | 1.02.04 | Acrylic field cage panels Clveios coating | 1 | 2019-05-14 | 2019-05-14 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120900 | 1.02.04 | ESR TPB coating | 1 | 2019-05-14 | 2019-05-14 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120960 | 1.02.04 | Acrylic cathode window Clevios coating | 1 | 2019-05-14 | 2019-05-14 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120780 | 1.02.04 | Anode diving bell TPB coating | 1 | 2019-05-15 | 2019-05-15 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-120980 | 1.02.04 | Acrylic cathode window TPB coating | 1 | 2019-05-15 | 2019-05-15 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05 Prototype TPC (mock up) |  |  | 435 | 2019-05-10 | 2020-07-17 |  |  |  |  | 113861.55 | 316000 | 429861.56 | 113861.55 | 316000 | 429861.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121300 | 1.02.05 | Prototype TPC (mock up) | 1 | 10-May-19* | 2019-05-10 |  | Secured | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01 Vessel (Acrylic) |  |  | 435 | 2019-05-10 | 2020-07-17 |  |  |  |  | 4597.73 | 0 | 4597.73 | 4597.73 | 0 | 4597.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121320 | 1.02.05.01 | Vessel (Acrylic) | 1 | 10-May-19* | 2019-05-10 |  |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01.01 Top Plate (Anode) |  |  | 1 | 2019-05-10 | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121340 | 1.02.05.01.01 | Top Plate (Anode) | 1 | 10-May-19* | 2019-05-10 |  |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121360 | 1.02.05.01.01 | Conceptual desgin inherited from DS-20k | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121380 | 1.02.05.01.01 | Load Analysis | 1 | 10-May-19* | 2019-05-10 |  |  |  | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121400 | 1.02.05.01.01 | Engineering Drawing | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121420 | 1.02.05.01.01 | Coating Clevios | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121440 | 1.02.05.01.01 | Coating TPB | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121460 | 1.02.05.01.01 | Electrical Contact Point Masking | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01.02 Bottom Plate (cathode) |  |  | 1 | 2019-05-10 | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121480 | 1.02.05.01.02 | Bottom Plate (cathode) | 1 | 10-May-19* | 2019-05-10 |  |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121500 | 1.02.05.01.02 | Conceptual desgin inherited from DS-20k | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121520 | 1.02.05.01.02 | Load Analysis | 1 | 10-May-19* | 2019-05-10 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121540 | 1.02.05.01.02 | Engineering Drawing | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121560 | 1.02.05.01.02 | Coating Clevios | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121580 | 1.02.05.01.02 | Coating TPB | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121600 | 1.02.05.01.02 | Electrical Contact Point Masking | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01.03 Wall Panels (x8) |  |  | 1 | 2019-05-10 | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121620 | 1.02.05.01.03 | Wall Panels (x8) | 1 | 10-May-19* | 2019-05-10 |  |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121640 | 1.02.05.01.03 | Conceptual desgin inherited from DS-20k | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121660 | 1.02.05.01.03 | Load Analysis | 1 | 10-May-19* | 2019-05-10 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121680 | 1.02.05.01.03 | Engineering Drawing | 1 | 10-May-19* | 2019-05-10 |  |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121700 | 1.02.05.01.03 | Groove Cutting | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121720 | 1.02.05.01.03 | After Cut Surface Treatment | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121740 | 1.02.05.01.03 | Coating Clevios | 1 | 10-May-19* | 2019-05-10 |  |  | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01.04 Access Port Certification (Inherited from DS-20k) |  |  | 1 | 2019-05-10 | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121760 | 1.02.05.01.04 | Access Port Certification (Inherited from DS-20k) | 1 | 10-May-19* | 2019-05-10 |  |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.01.05 Internal TPC Required Parts Installation |  |  | 435 | 2019-05-10 | 2020-07-17 |  |  |  |  | 4597.73 | 0 | 4597.73 | 4597.73 | 0 | 4597.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121780 | 1.02.05.01.05 | Internal TPC Required Parts Installation | 1 | 10-May-19* | 2019-05-10 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121860 | 1.02.05.01.05 | Instrumentation Connections (anode, grid, first field ring) | 1 | 10-May-19* | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121880 | 1.02.05.01.05 | Bonding Strategy (Inherited from DS-20k) | 1 | 10-May-19* | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121800 | 1.02.05.01.05 | Reflector Cage | 1 | 2019-05-11 | 2019-05-11 |  |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121820 | 1.02.05.01.05 | Field Cage | 1 | 2019-05-11 | 2019-05-11 |  |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121840 | 1.02.05.01.05 | UH Postdoc for Wire Frame Installation | 15 | 2020-07-03 | 2020-07-17 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 4597.73 | 0 | 4597.73 | 4597.73 | 0 | 4597.73 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.02 Field Cage (20k mockup) |  |  | 55 | 2019-05-10 | 2019-07-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-121900 | 1.02.05.02 | Field Cage (20k mockup) | 1 | 10-May-19* | 2019-05-10 |  |  |  | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122000 | 1.02.05.02 | HV Connection to Anode, Grid and First Field Ring | 1 | 10-May-19* | 2019-05-10 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122020 | 1.02.05.02 | Assembly Steps and Details | 1 | 10-May-19* | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121920 | 1.02.05.02 | Conceptual desgin inherited from DS-20k | 1 | 2019-07-02 | 2019-07-02 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121940 | 1.02.05.02 | Field Modeling and Optimization | 1 | 2019-07-03 | 2019-07-03 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121960 | 1.02.05.02 | Clevios Polymer Coating | 1 | 2019-07-03 | 2019-07-03 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-121980 | 1.02.05.02 | Resistor Link | 1 | 2019-07-03 | 2019-07-03 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.03 Reflector Cage (20k mockup) |  |  | 55 | 2019-05-10 | 2019-07-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122040 | 1.02.05.03 | Reflector Cage (20k mockup) | 1 | 10-May-19* | 2019-05-10 |  |  |  | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122140 | 1.02.05.03 | Assembly Details | 1 | 10-May-19* | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122060 | 1.02.05.03 | Conceptual desgin inherited from DS-20k | 1 | 2019-07-02 | 2019-07-02 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122080 | 1.02.05.03 | Panel Mechanical Design | 1 | 2019-07-03 | 2019-07-03 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122100 | 1.02.05.03 | Thermal Modeling | 1 | 2019-07-03 | 2019-07-03 | INFN |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122120 | 1.02.05.03 | Coating and Handling Details | 1 | 2019-07-03 | 2019-07-03 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.04 Bottom Ground (Inherited from DS-20k) |  |  | 1 | 2019-05-10 | 2019-05-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122160 | 1.02.05.04 | Bottom Ground (Inherited from DS-20k) | 1 | 10-May-19* | 2019-05-10 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.05 Extraction Grid (Wire and Frame) |  |  | 368 | 2019-07-01 | 2020-07-02 |  |  |  |  | 109263.82 | 316000 | 425263.82 | 109263.82 | 316000 | 425263.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122200 | 1.02.05.05 | Wire frame Design and FEA Modeling | 61 | 01-Jul-19* | 2019-08-30 | NSF Construction Grant | Secured | Houston | A. Renshaw | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122180 | 1.02.05.05 | Extraction Grid (Wire and Frame) | 336 | 01-Jul-19* | 2020-05-31 | NSF | Secured | Houston | A. Renshaw | 0 | 158000 | 158000 | 0 | 158000 | 158000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122440 | 1.02.05.05 | Houston Postdoc | 336 | 01-Jul-19* | 2020-05-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 109263.82 | 0 | 109263.82 | 109263.82 | 0 | 109263.82 |  |  | 0 |  |  | 0 |  |  | 0
DS-122360 | 1.02.05.05 | Wire Frame Fabrication | 121 | 2019-08-31 | 2019-12-29 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 45000 | 45000 | 0 | 45000 | 45000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122220 | 1.02.05.05 | Wire Winding Machine Parts | 61 | 01-Sep-19* | 2019-10-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 25000 | 25000 | 0 | 25000 | 25000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122260 | 1.02.05.05 | Wire Pins Fabrication | 61 | 01-Sep-19* | 2019-10-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 15000 | 15000 | 0 | 15000 | 15000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122280 | 1.02.05.05 | Stainless Steel Wire Procurement | 61 | 01-Sep-19* | 2019-10-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 4000 | 4000 | 0 | 4000 | 4000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122240 | 1.02.05.05 | Wire Winding Machine Assembly | 61 | 2019-11-01 | 2019-12-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122300 | 1.02.05.05 | Wire Tension Measurement | 31 | 2020-01-01 | 2020-01-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122320 | 1.02.05.05 | Wrapped Wire Certification | 15 | 2020-02-01 | 2020-02-15 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122340 | 1.02.05.05 | Wrapped Wire Production | 61 | 2020-02-16 | 2020-04-16 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 20000 | 20000 | 0 | 20000 | 20000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122380 | 1.02.05.05 | Wire Grid Assembly | 31 | 2020-04-17 | 2020-05-17 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 6000 | 6000 | 0 | 6000 | 6000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122400 | 1.02.05.05 | Wire Grid Wire Tension Check | 31 | 2020-05-18 | 2020-06-17 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 6000 | 6000 | 0 | 6000 | 6000 |  |  | 0 |  |  | 0 |  |  | 0
DS-122420 | 1.02.05.05 | Shipping from Houston to CERN | 15 | 2020-06-18 | 2020-07-02 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 7000 | 7000 | 0 | 7000 | 7000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.06 Internal Argon Loop |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122460 | 1.02.05.06 | Internal Argon Loop | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.07 SiPM Related Interfacing |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122480 | 1.02.05.07 | SiPM Related Interfacing | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.08 Cathode HV System (TPC) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122500 | 1.02.05.08 | Cathode HV System (TPC) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.09 TPC Instrumentation Cabling (in TPC) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122520 | 1.02.05.09 | TPC Instrumentation Cabling (in TPC) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.05.10 Liquid Argon Leveling Control |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122540 | 1.02.05.10 | Liquid Argon Leveling Control | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06 DarkSide-20k TPC |  |  | 181 | 2019-07-01 | 2019-12-28 |  |  |  |  | 0 | 3910000 | 3910000 | 0 | 540000 | 540000 | 0 | 4500000 | 4500000 | 0 | 200000 | 200000 | 0 | 0 | 0
DS-122560 | 1.02.06 | DarkSide-20k TPC | 1 | 01-Jul-19* | 2019-07-01 |  |  | UCLA | H. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01 Vessel (Acrylic) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 3150000 | 3150000 | 0 | 0 | 0 | 0 | 4500000 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0
DS-122580 | 1.02.06.01 | Vessel (Acrylic) | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 3150000 | 3150000 | 0 | 0 | 0 |  | 4500000 | 4500000 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.01 Top Plate (Anode) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122600 | 1.02.06.01.01 | Top Plate (Anode) | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122620 | 1.02.06.01.01 | Engineering Drawing | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122640 | 1.02.06.01.01 | Load Analysis | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122660 | 1.02.06.01.01 | Coating Clevios | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122680 | 1.02.06.01.01 | Surface Preparation | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122700 | 1.02.06.01.01 | Tooling | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122720 | 1.02.06.01.01 | Drying Process | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122740 | 1.02.06.01.01 | Coating TPB | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122760 | 1.02.06.01.01 | Segmented Coating or Large in Vacuum Coating | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122780 | 1.02.06.01.01 | Contact Point Masking | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.02 Bottom Plate (cathode) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-122800 | 1.02.06.01.02 | Bottom Plate (cathode) | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122820 | 1.02.06.01.02 | Engineering Drawing | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122840 | 1.02.06.01.02 | Load Analysis | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122860 | 1.02.06.01.02 | Coating Clevios | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122880 | 1.02.06.01.02 | Surface Preparation | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122900 | 1.02.06.01.02 | Tooling | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122920 | 1.02.06.01.02 | Drying Process | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122940 | 1.02.06.01.02 | Coating TPB | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122960 | 1.02.06.01.02 | Segmented Coating or Large in Vacuum Coating | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-122980 | 1.02.06.01.02 | Facility Requirements | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.03 Wall Panels (x8) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123000 | 1.02.06.01.03 | Wall Panels (x8) | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123020 | 1.02.06.01.03 | Engineering Drawing | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123040 | 1.02.06.01.03 | Load Analysis | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123060 | 1.02.06.01.03 | Groove Cutting | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123080 | 1.02.06.01.03 | After Cut Surface Treatment | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123100 | 1.02.06.01.03 | Coating Clevios | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123120 | 1.02.06.01.03 | Drying Process | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.04 Access Port Certification |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123140 | 1.02.06.01.04 | Access Port Certification | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123160 | 1.02.06.01.04 | Which method to transition from scrylic to SS flange | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123180 | 1.02.06.01.04 | Anode, grid, first field ring contact point | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123200 | 1.02.06.01.04 | Cathode HV access port or contact | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123220 | 1.02.06.01.04 | TPC Instrumentation Cabling port | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.05 Internal TPC Required Parts Installation |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123240 | 1.02.06.01.05 | Internal TPC Required Parts Installation | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123260 | 1.02.06.01.05 | Reflector Cage | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123280 | 1.02.06.01.05 | Field Cage | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123300 | 1.02.06.01.05 | Wire Frame | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123320 | 1.02.06.01.05 | Instrumentation Connections (anode, grid, first field ring) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.01.06 Bonding Strategy |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123340 | 1.02.06.01.06 | Bonding Strategy | 1 | 01-Jul-19* | 2019-07-01 | CFI |  | Alberta | A. Hallin | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123360 | 1.02.06.01.06 | Where | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123380 | 1.02.06.01.06 | Facility Requirements | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123400 | 1.02.06.01.06 | Annealing Plan | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123420 | 1.02.06.01.06 | Wall Bonding (first) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123440 | 1.02.06.01.06 | Bottom Plate Bonding (second) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123460 | 1.02.06.01.06 | Final Top Plate Bonding (last) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123480 | 1.02.06.01.06 | Re-open Plan (Consider should re-opening be required) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.02 Field Cage |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123500 | 1.02.06.02 | Field Cage | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123520 | 1.02.06.02 | Field Ring Groove Cross Section Determination | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123540 | 1.02.06.02 | Field Modeling and Optimization | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123560 | 1.02.06.02 | Clevios Polymer Coating | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123580 | 1.02.06.02 | Resistor Link | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123600 | 1.02.06.02 | Flexible PCB selection and screening | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123620 | 1.02.06.02 | Maximum Flexibility Testing | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123640 | 1.02.06.02 | Use thick Kapton and thick copper layer | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123660 | 1.02.06.02 | Mounting plan considering thermal expansion | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123680 | 1.02.06.02 | Optimize shape with thermal expansion consideration | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123700 | 1.02.06.02 | Resistor Size Determination | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123720 | 1.02.06.02 | Resistor Screening | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123740 | 1.02.06.02 | Solder Flux selection and screening | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123760 | 1.02.06.02 | HV Connection to Anode, Grid and First Field Ring | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123780 | 1.02.06.02 | Assembly Steps and Details | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.03 Reflector Cage |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123800 | 1.02.06.03 | Reflector Cage | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UC Davis | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123820 | 1.02.06.03 | Determination of TPB on ESR directly or Acrylic | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123840 | 1.02.06.03 | Panel Mechanical Design | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123860 | 1.02.06.03 | Thermal Modeling | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123880 | 1.02.06.03 | Mock-up test and certification | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123900 | 1.02.06.03 | Coating and Handling Details | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123920 | 1.02.06.03 | Assembly Details | 1 | 01-Jul-19* | 2019-07-01 | NSF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.04 Ground (bottom of bottom acrylic vessel) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123940 | 1.02.06.04 | Ground (bottom of bottom acrylic vessel) | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-123960 | 1.02.06.04 | Clevios coating and handling details | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.05 Extraction Grid (Wire and Frame) |  |  | 181 | 2019-07-01 | 2019-12-28 |  |  |  |  | 0 | 540000 | 540000 | 0 | 540000 | 540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-123980 | 1.02.06.05 | Extraction Grid (Wire and Frame) | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | Houston | A. Renshaw | 0 | 270000 | 270000 | 0 | 270000 | 270000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124240 | 1.02.06.05 | Wrapped Wire Certification | 15 | 01-Jul-19* | 2019-07-15 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124220 | 1.02.06.05 | Wire Tension Measurement | 31 | 01-Jul-19* | 2019-07-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124300 | 1.02.06.05 | Wrapped Wire Shipping to LNGS | 31 | 01-Jul-19* | 2019-07-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 7000 | 7000 | 0 | 7000 | 7000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124360 | 1.02.06.05 | Wire Frame Shipping to LNGS | 31 | 01-Jul-19* | 2019-07-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 14000 | 14000 | 0 | 14000 | 14000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124400 | 1.02.06.05 | Wire Grid tensions check at LNGS | 31 | 01-Jul-19* | 2019-07-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 9000 | 9000 | 0 | 9000 | 9000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124000 | 1.02.06.05 | Wire frame Design and FEA Modeling | 61 | 01-Jul-19* | 2019-08-30 | NSF | Secured | Houston | A. Renshaw | 0 | 20000 | 20000 | 0 | 20000 | 20000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124020 | 1.02.06.05 | Frame Materials Screening | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124040 | 1.02.06.05 | Wire Materials Screening | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124060 | 1.02.06.05 | Wire Pin Materials Screening | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124080 | 1.02.06.05 | Fabrication Plan (welding and annealing) | 61 | 01-Jul-19* | 2019-08-30 | NSF | Secured | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124100 | 1.02.06.05 | Wire Fixture Method Determination | 61 | 01-Jul-19* | 2019-08-30 | NSF | Secured | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124120 | 1.02.06.05 | Wire Winding Machine Modifications | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124140 | 1.02.06.05 | Wire Spool Design and Testing | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124160 | 1.02.06.05 | Wire Spool Procurement | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124200 | 1.02.06.05 | Stainless Steel Wire Procurement | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 15000 | 15000 | 0 | 15000 | 15000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124320 | 1.02.06.05 | Stainless Steel Procurement | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 20000 | 20000 | 0 | 20000 | 20000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124380 | 1.02.06.05 | Wire Grid Assembly at LNGS | 61 | 01-Jul-19* | 2019-08-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 25000 | 25000 | 0 | 25000 | 25000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124180 | 1.02.06.05 | Wire Pin Fabrication | 121 | 01-Jul-19* | 2019-10-29 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 25000 | 25000 | 0 | 25000 | 25000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124260 | 1.02.06.05 | Wrapped Wire production | 121 | 01-Jul-19* | 2019-10-29 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 30000 | 30000 | 0 | 30000 | 30000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124280 | 1.02.06.05 | Wrapped Wire spooling and cleaning | 121 | 01-Jul-19* | 2019-10-29 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124340 | 1.02.06.05 | Wire Frame Fabrication | 181 | 01-Jul-19* | 2019-12-28 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 40000 | 40000 | 0 | 40000 | 40000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.06.06 TPC itegration at LNGS |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 220000 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0
DS-124420 | 1.02.06.06 | TPC itegration at LNGS | 1 | 01-Jul-19* | 2019-07-01 | INFN-CSN2 |  | Naples | Y. Suvorov | 0 | 220000 | 220000 | 0 | 0 | 0 |  |  | 0 |  | 200000 | 200000 |  |  | 0
DarkSide.1.02.07 Internal Argon Loop Planning and Testing |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 30000 | 30000 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-124440 | 1.02.07 | Internal Argon Loop Planning and Testing | 1 | 01-Jul-19* | 2019-07-01 | NSF |  | UCLA | Y. Wang | 0 | 30000 | 30000 | 0 | 30000 | 30000 |  |  | 0 |  |  | 0 |  |  | 0
DS-124460 | 1.02.07 | UAr Flow Strategy within TPC | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124480 | 1.02.07 | Interfacing with field cage and reflector cage | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124500 | 1.02.07 | Interfacing with external plumbing | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124520 | 1.02.07 | Interface with leveling system | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124540 | 1.02.07 | Interface with acrylic vessel port | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.08 SiPM Related Interfacing |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-124560 | 1.02.08 | SiPM Related Interfacing | 1 | 01-Jul-19* | 2019-07-01 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124580 | 1.02.08 | Detailed Drawings of mechanics to fit motherboard to TPC top and bottom | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124600 | 1.02.08 | Fabrication of the Support Structure | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | R. Santorelli | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124620 | 1.02.08 | Integration of the PDM MB assembly | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | A. Pocar | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124640 | 1.02.08 | MotherBoard on Support Structure | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | A. Pocar | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124660 | 1.02.08 | PDM assembly to tpc | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | A. Pocar | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124680 | 1.02.08 | Integration of the TPC full assembly with the cryostat top-cap | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | T. Napolitano | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124700 | 1.02.08 | Penentration interfacing with Veto | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124720 | 1.02.08 | Penentration interfacing with Cryostat | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124740 | 1.02.08 | Heat issue of cold electronics and its mitigation for bubbling (LNGS) (reference acrylic bottom shape) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124760 | 1.02.08 | Interfacing with all SiPM related cabling | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.09 TPC Instrumentation Cabling (outside TPC) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-124780 | 1.02.09 | TPC Instrumentation Cabling (outside TPC) | 1 | 01-Jul-19* | 2019-07-01 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124800 | 1.02.09 | Acrylic port determination | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124820 | 1.02.09 | Gas Pocket related | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124840 | 1.02.09 | TPC level sensor | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.10 HV System |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-124860 | 1.02.10 | HV System | 1 | 01-Jul-19* | 2019-07-01 |  |  | UC Davis | E. Pantic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.10.01 Cathode HV System (outside TPC) |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-124880 | 1.02.10.01 | Cathode HV System (outside TPC) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124900 | 1.02.10.01 | Conceptual design | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124920 | 1.02.10.01 | Field modeling and optimization | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124940 | 1.02.10.01 | HV feedthrough engineer design | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124960 | 1.02.10.01 | HV feedthrough fabrication | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-124980 | 1.02.10.01 | HV power supply procurement | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125000 | 1.02.10.01 | HV feedthrough stand-alone test | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125020 | 1.02.10.01 | Cathode region mock-up and test at 150% of full HV | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.10.02 HV system for S2 |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125040 | 1.02.10.02 | HV system for S2 | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | L. Pagani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125060 | 1.02.10.02 | Determination of HV delivery method | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125080 | 1.02.10.02 | HV feedthrough design | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125100 | 1.02.10.02 | HV feedtrhough fabrication | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125120 | 1.02.10.02 | HV power supply procurement | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125140 | 1.02.10.02 | HV feedthrough stand-alone test | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125160 | 1.02.10.02 | Anode HV (grounded) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125180 | 1.02.10.02 | Grid HV | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125200 | 1.02.10.02 | First Field Cage Ring | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.11 Liquid Argon Leveling Control |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125220 | 1.02.11 | Liquid Argon Leveling Control | 1 | 01-Jul-19* | 2019-07-01 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.11.01 Leveling monitor |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125240 | 1.02.11.01 | Leveling monitor | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125260 | 1.02.11.01 | Instrumental leveling sensor (outside TPC) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125280 | 1.02.11.01 | Intrinsic leveling sensor (S2 uniformity) | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125300 | 1.02.11.01 | Leveling software development | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125320 | 1.02.11.01 | Test and certification | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.11.02 Leveling control |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125340 | 1.02.11.02 | Leveling control | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125360 | 1.02.11.02 | Conceptual design | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125380 | 1.02.11.02 | Engineering drawing | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125400 | 1.02.11.02 | FEA modeling | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125420 | 1.02.11.02 | Prototyping | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125440 | 1.02.11.02 | Interface with DS-20k cryostat | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125460 | 1.02.11.02 | Production | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125480 | 1.02.11.02 | Test and certification | 1 | 01-Jul-19* | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.13 Proto-Proto Cryogenics System |  |  | 1 | 2019-07-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125500 | 1.02.13 | Proto-Proto Cryogenics System | 1 | 01-Jul-19* | 2019-07-01 |  | Secured | CERN | F. Pietropaolo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125520 | 1.02.13 | Using existing cryogenics system AT CERN NP building 182, Francesco's lab | 1 | 01-Jul-19* | 2019-07-01 |  |  |  | F. Pietropaolo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14 DarkSide-20k UAr Cryogenics System |  |  | 1767 | 2017-03-01 | 2021-12-31 |  |  |  |  | 11454.55 | 5339846.5 | 5351301.05 | 11454.55 | 5276500 | 5287954.55 | 0 | 90495 | 90495 | 0 | 0 | 0 | 0 | 0 | 0
DS-125540 | 1.02.14 | DarkSide-20k UAr Cryogenics System | 1767 | 01-Mar-17* | 2021-12-31 | NSF |  | FNAL | C. Kendziora | 0 | 1630000 | 1630000 | 0 | 1630000 | 1630000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01 Cryogenics test@CERN |  |  | 1095 | 2017-03-01 | 2020-02-28 |  |  |  |  | 11454.55 | 1429846.5 | 1441301.05 | 11454.55 | 1366500 | 1377954.55 | 0 | 90495 | 90495 | 0 | 0 | 0 | 0 | 0 | 0
DS-125600 | 1.02.14.01 | P&ID | 1 | 01-Mar-17* | 2017-03-01 |  |  | FNAL | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125620 | 1.02.14.01 | 3D CAD Model | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125640 | 1.02.14.01 | Calculation and evaluation | 1 | 01-Mar-17* | 2017-03-01 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125580 | 1.02.14.01 | Overall Design | 821 | 01-Mar-17* | 2019-05-30 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125560 | 1.02.14.01 | Cryogenics test@CERN | 1095 | 01-Mar-17* | 2020-02-28 | NSF |  | UCLA | X. Xiao | 0 | 490000 | 490000 | 0 | 490000 | 490000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.02 CERN Safety Review |  |  | 242 | 2018-11-01 | 2019-06-30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125660 | 1.02.14.01.02 | CERN Safety Review | 242 | 01-Nov-18* | 2019-06-30 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.03 Condenser Box |  |  | 1036 | 2017-03-01 | 2019-12-31 |  |  |  |  | 5727.27 | 203346.5 | 209073.77 | 5727.27 | 140000 | 145727.27 | 0 | 90495 | 90495 | 0 | 0 | 0 | 0 | 0 | 0
DS-125700 | 1.02.14.01.03 | Customized Vacumm Vessel procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 27000 | 27000 | 0 | 27000 | 27000 |  |  | 0 |  |  | 0 |  |  | 0
DS-125720 | 1.02.14.01.03 | Cryogenics Valves Procurement | 1 | 01-Mar-17* | 2017-03-01 | CFI |  | Carleton | M. Boulay | 0 | 63346.5 | 63346.5 | 0 | 0 | 0 |  | 90495 | 90495 |  |  | 0 |  |  | 0
DS-125740 | 1.02.14.01.03 | Brazed plate heat exchangers procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 8000 | 8000 | 0 | 8000 | 8000 |  |  | 0 |  |  | 0 |  |  | 0
DS-125760 | 1.02.14.01.03 | Pressure transducers procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 13000 | 13000 | 0 | 13000 | 13000 |  |  | 0 |  |  | 0 |  |  | 0
DS-125780 | 1.02.14.01.03 | PT100 and readout circuit procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-125800 | 1.02.14.01.03 | Condenser Fabrication and tube cutting | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-125820 | 1.02.14.01.03 | Welding and Assembly | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 4090.91 | 0 | 4090.91 | 4090.91 | 0 | 4090.91 |  |  | 0 |  |  | 0 |  |  | 0
DS-125840 | 1.02.14.01.03 | Helium Leak Check | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-125860 | 1.02.14.01.03 | Pressure test | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-125680 | 1.02.14.01.03 | Condenser Box | 1036 | 01-Mar-17* | 2019-12-31 | NSF |  | UCLA | X. Xiao | 0 | 72000 | 72000 | 0 | 72000 | 72000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.04 Gas Circulation Pump |  |  | 822 | 2017-10-01 | 2019-12-31 |  |  |  |  | 0 | 50000 | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-125900 | 1.02.14.01.04 | LiHan Motor Assembly Procurement | 1 | 01-Oct-17* | 2017-10-01 |  |  | IHEP | C. Yang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125920 | 1.02.14.01.04 | Reed Valve Procurement | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125940 | 1.02.14.01.04 | Pump body fabrication | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125960 | 1.02.14.01.04 | Chilled Water Loop Fabrication | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125980 | 1.02.14.01.04 | Power system procurement | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126000 | 1.02.14.01.04 | Operational monitor system fabrication | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126020 | 1.02.14.01.04 | Assembly | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126040 | 1.02.14.01.04 | Helium Leak Check | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126060 | 1.02.14.01.04 | Pressure test | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126080 | 1.02.14.01.04 | Test Running at various frequencies and voltages | 1 | 01-Oct-17* | 2017-10-01 | NSF |  | UCLA | Y. Wang | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126100 | 1.02.14.01.04 | CE Certification | 1 | 01-Oct-17* | 2017-10-01 |  |  | CERN | M. Carlini | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-125880 | 1.02.14.01.04 | Gas Circulation Pump | 822 | 01-Oct-17* | 2019-12-31 | NSF |  | UCLA | Y. Wang | 0 | 50000 | 50000 | 0 | 50000 | 50000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.05 Gas Panel |  |  | 730 | 2018-01-01 | 2019-12-31 |  |  |  |  | 0 | 297500 | 297500 | 0 | 297500 | 297500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126140 | 1.02.14.01.05 | Room Temperature Valves Procurement | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 58000 | 58000 | 0 | 58000 | 58000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126160 | 1.02.14.01.05 | Sensors Procurement | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 8500 | 8500 | 0 | 8500 | 8500 |  |  | 0 |  |  | 0 |  |  | 0
DS-126180 | 1.02.14.01.05 | Relief valve procurement | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126200 | 1.02.14.01.05 | Vacuum Pumps Procurement | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 63000 | 63000 | 0 | 63000 | 63000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126220 | 1.02.14.01.05 | Tube Cutting and Fabrication | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 7000 | 7000 | 0 | 7000 | 7000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126240 | 1.02.14.01.05 | Assembly and Welding | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126260 | 1.02.14.01.05 | Helium Leak Check | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126280 | 1.02.14.01.05 | Pressure Test | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126120 | 1.02.14.01.05 | Gas Panel | 730 | 01-Jan-18* | 2019-12-31 | NSF |  | UCLA | X. Xiao | 0 | 151000 | 151000 | 0 | 151000 | 151000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.06 Transfer Lines |  |  | 730 | 2018-01-01 | 2019-12-31 |  |  |  |  | 1636.36 | 26000 | 27636.36 | 1636.36 | 26000 | 27636.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126320 | 1.02.14.01.06 | Bellows Procurement | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126340 | 1.02.14.01.06 | Flange Fabrication | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 3000 | 3000 | 0 | 3000 | 3000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126360 | 1.02.14.01.06 | Bayonet Fabrication | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | UCLA | X. Xiao | 0 | 3000 | 3000 | 0 | 3000 | 3000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126380 | 1.02.14.01.06 | Assembly and Welding | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | FNAL | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126400 | 1.02.14.01.06 | Helium Leak Check | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | FNAL | C. Kendziora | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-126420 | 1.02.14.01.06 | Pressure Test | 1 | 01-Jan-18* | 2018-01-01 | NSF |  | FNAL | C. Kendziora | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-126300 | 1.02.14.01.06 | Transfer Lines | 730 | 01-Jan-18* | 2019-12-31 | NSF |  | FNAL | C. Kendziora | 0 | 15000 | 15000 | 0 | 15000 | 15000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.07 DS-Proto Cryostat instrumentation |  |  | 31 | 2019-06-01 | 2019-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126440 | 1.02.14.01.07 | DS-Proto Cryostat instrumentation | 31 | 01-Jun-19* | 2019-07-01 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.08 Slow Control |  |  | 730 | 2018-01-01 | 2019-12-31 |  |  |  |  | 0 | 10000 | 10000 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126460 | 1.02.14.01.08 | Slow Control | 730 | 01-Jan-18* | 2019-12-31 | NSF |  | UCLA | Y. Wang | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.09 Test System Integration at CERN |  |  | 31 | 2019-07-01 | 2019-07-31 |  |  |  |  | 0 | 5000 | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126480 | 1.02.14.01.09 | Test System Integration at CERN | 31 | 01-Jul-19* | 2019-07-31 | NSF |  | UCLA | X. Xiao | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.10 Test at CERN |  |  | 153 | 2019-08-01 | 2019-12-31 |  |  |  |  | 0 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126520 | 1.02.14.01.10 | Long-term Stability | 1 | 01-Aug-19* | 2019-08-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126540 | 1.02.14.01.10 | Operation at various circulation speeds | 1 | 01-Aug-19* | 2019-08-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126560 | 1.02.14.01.10 | Maximum achievable circulation speed and cooling power | 1 | 01-Aug-19* | 2019-08-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126580 | 1.02.14.01.10 | Total power failure test | 1 | 01-Aug-19* | 2019-08-01 | NSF |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126500 | 1.02.14.01.10 | Test at CERN | 153 | 01-Aug-19* | 2019-12-31 | NSF |  | UCLA | X. Xiao | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.11 Integrated Radon Trap |  |  | 1036 | 2017-03-01 | 2019-12-31 |  |  |  |  | 4090.91 | 326000 | 330090.91 | 4090.91 | 326000 | 330090.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126620 | 1.02.14.01.11 | Design | 1 | 01-Mar-17* | 2017-03-01 |  |  |  | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126640 | 1.02.14.01.11 | Material Radon Emanation | 1 | 01-Mar-17* | 2017-03-01 |  |  | CIEMAT | R. Santorelli | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126660 | 1.02.14.01.11 | Charcoal Procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 150000 | 150000 | 0 | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126680 | 1.02.14.01.11 | Porous Plate Procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 2000 | 2000 | 0 | 2000 | 2000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126700 | 1.02.14.01.11 | Particulate Filter Procurement | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 6000 | 6000 | 0 | 6000 | 6000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126720 | 1.02.14.01.11 | Radon Trap Body Fabrication | 1 | 01-Mar-17* | 2017-03-01 | NSF |  | UCLA | X. Xiao | 0 | 3000 | 3000 | 0 | 3000 | 3000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126740 | 1.02.14.01.11 | Assembly and Welding | 1 | 01-Mar-17* | 2017-03-01 |  |  |  | X. Xiao | 2454.55 | 0 | 2454.55 | 2454.55 | 0 | 2454.55 |  |  | 0 |  |  | 0 |  |  | 0
DS-126760 | 1.02.14.01.11 | Helium Leak Check | 1 | 01-Mar-17* | 2017-03-01 |  |  |  | X. Xiao | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-126780 | 1.02.14.01.11 | Pressure Test | 1 | 01-Mar-17* | 2017-03-01 |  |  |  | X. Xiao | 818.18 | 0 | 818.18 | 818.18 | 0 | 818.18 |  |  | 0 |  |  | 0 |  |  | 0
DS-126600 | 1.02.14.01.11 | Integrated Radon Trap | 1036 | 01-Mar-17* | 2019-12-31 | NSF |  | UCLA | X. Xiao | 0 | 165000 | 165000 | 0 | 165000 | 165000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.01.12 Transportation to LNGS |  |  | 59 | 2020-01-01 | 2020-02-28 |  |  |  |  | 0 | 20000 | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126800 | 1.02.14.01.12 | Transportation to LNGS | 59 | 01-Jan-20* | 2020-02-28 | NSF |  | UCLA | X. Xiao | 0 | 20000 | 20000 | 0 | 20000 | 20000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.14.02 DS-20k UAr Cryogenics System &LNGS |  |  | 731 | 2020-01-01 | 2021-12-31 |  |  |  |  | 0 | 2280000 | 2280000 | 0 | 2280000 | 2280000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-126860 | 1.02.14.02 | Design Finalization | 59 | 2020-01-01 | 2020-02-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126880 | 1.02.14.02 | LNGS Safety Review | 59 | 2020-01-01 | 2020-02-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126900 | 1.02.14.02 | Internal surface treatment requirement and procedure for all parts in contact with Underground Argon | 59 | 01-Jan-20* | 2020-02-28 |  |  |  |  | 0 | 5000 | 5000 | 0 | 5000 | 5000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126820 | 1.02.14.02 | DS-20k UAr Cryogenics System &LNGS | 731 | 01-Jan-20* | 2021-12-31 | NSF |  | FNAL | C. Kendziora | 0 | 1140000 | 1140000 | 0 | 1140000 | 1140000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126940 | 1.02.14.02 | Finalized design from CERN Test | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126960 | 1.02.14.02 | Integrated with radon trap | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127000 | 1.02.14.02 | Finalized design from CERN Test | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127020 | 1.02.14.02 | Power drive system | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127040 | 1.02.14.02 | CE Certification | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127080 | 1.02.14.02 | Integrated with internal calibration source injection port | 1 | 01-Mar-20* | 2020-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-126920 | 1.02.14.02 | Final Condenser Box | 306 | 01-Mar-20* | 2020-12-31 | NSF |  | UCLA |  | 0 | 30000 | 30000 | 0 | 30000 | 30000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126980 | 1.02.14.02 | Final Gas circulation pump | 306 | 01-Mar-20* | 2020-12-31 | NSF |  | UCLA |  | 0 | 235000 | 235000 | 0 | 235000 | 235000 |  |  | 0 |  |  | 0 |  |  | 0
DS-127060 | 1.02.14.02 | Final gas panel and piping | 306 | 01-Mar-20* | 2020-12-31 | NSF |  | UCLA |  | 0 | 55000 | 55000 | 0 | 55000 | 55000 |  |  | 0 |  |  | 0 |  |  | 0
DS-127100 | 1.02.14.02 | Final transfer line | 306 | 01-Mar-20* | 2020-12-31 | NSF |  | UCLA |  | 0 | 35000 | 35000 | 0 | 35000 | 35000 |  |  | 0 |  |  | 0 |  |  | 0
DS-126840 | 1.02.14.02 | Getter system (SAES hot getter system "Mega-Torr") | 214 | 01-Jun-20* | 2020-12-31 | NSF |  | Princeton |  | 0 | 750000 | 750000 | 0 | 750000 | 750000 |  |  | 0 |  |  | 0 |  |  | 0
DS-127120 | 1.02.14.02 | Integration at LNGS | 181 | 2021-01-01 | 2021-06-30 | NSF |  | UCLA |  | 0 | 20000 | 20000 | 0 | 20000 | 20000 |  |  | 0 |  |  | 0 |  |  | 0
DS-127140 | 1.02.14.02 | Test and commissioning | 184 | 2021-07-01 | 2021-12-31 | NSF |  | UCLA |  | 0 | 10000 | 10000 | 0 | 10000 | 10000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15 DarkSide-Prototype Cryogenics System |  |  | 854 | 2019-03-01 | 2021-07-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127160 | 1.02.15 | DarkSide-Prototype Cryogenics System | 1 | 01-Jul-21* | 2021-07-01 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.01 Design (compact version of the DS-20k cryogenics system) |  |  | 1 | 2019-03-01 | 2019-03-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127180 | 1.02.15.01 | Design (compact version of the DS-20k cryogenics system) | 1 | 01-Mar-19* | 2019-03-01 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127200 | 1.02.15.01 | P&ID | 1 | 01-Mar-19* | 2019-03-01 |  |  | FNAL | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127220 | 1.02.15.01 | 3D CAD Model | 1 | 01-Mar-19* | 2019-03-01 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127240 | 1.02.15.01 | Calculation and Evaluation | 1 | 01-Mar-19* | 2019-03-01 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.02 Material Procurement |  |  | 184 | 2019-03-02 | 2019-09-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127260 | 1.02.15.02 | Material Procurement | 1 | 2019-03-02 | 2019-03-02 |  |  | Naples | G. Fiorillo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127280 | 1.02.15.02 | Getter System | 1 | 01-Sep-19* | 2019-09-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127300 | 1.02.15.02 | Valves | 1 | 01-Sep-19* | 2019-09-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127320 | 1.02.15.02 | Sensors | 1 | 01-Sep-19* | 2019-09-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127340 | 1.02.15.02 | Vacuum Pumps | 1 | 01-Sep-19* | 2019-09-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.03 CERN/LNGS Safety Review |  |  | 1 | 2019-03-02 | 2019-03-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127360 | 1.02.15.03 | CERN/LNGS Safety Review | 1 | 2019-03-02 | 2019-03-02 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.04 Fabrication |  |  | 61 | 2019-03-02 | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127380 | 1.02.15.04 | Fabrication | 1 | 2019-03-02 | 2019-03-02 |  |  | UCLA | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127400 | 1.02.15.04 | Condenser | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127420 | 1.02.15.04 | Gas Panel | 1 | 01-May-19* | 2019-05-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127440 | 1.02.15.04 | lab 3D layout | 1 | 01-May-19* | 2019-05-01 |  |  |  | X. Xiao | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.05 Integration |  |  | 1 | 2020-06-02 | 2020-06-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127460 | 1.02.15.05 | Integration | 1 | 2020-06-02 | 2020-06-02 |  |  | Naples | G. Fiorillo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.06 Commissioning and Test |  |  | 1 | 2020-06-03 | 2020-06-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127480 | 1.02.15.06 | Commissioning and Test | 1 | 2020-06-03 | 2020-06-03 |  |  | Naples | G. Fiorillo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.07 Transportation to LNGS |  |  | 5 | 2020-06-01 | 2020-06-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127500 | 1.02.15.07 | Transportation to LNGS | 1 | 01-Jun-20* | 2020-06-01 |  |  | Naples | G. Fiorillo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127540 | 1.02.15.07 | Radon Trap | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127560 | 1.02.15.07 | Design | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127580 | 1.02.15.07 | Fabrication | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127600 | 1.02.15.07 | Integration to the cryogenics system | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127520 | 1.02.15.07 | Transportation | 1 | 2020-06-04 | 2020-06-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127620 | 1.02.15.07 | Test and Commissioning | 1 | 2020-06-05 | 2020-06-05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.15.08 Cryostat |  |  | 1 | 2020-06-01 | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127640 | 1.02.15.08 | Cryostat | 1 | 01-Jun-20* | 2020-06-01 |  |  | INFN-Roma1 | S. De Cecco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127660 | 1.02.15.08 | Design | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127680 | 1.02.15.08 | Fabrication | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127700 | 1.02.15.08 | Certification | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127720 | 1.02.15.08 | Integration to cryogenics | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127740 | 1.02.15.08 | Insulation vacuum port | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.16 UAr Storage and Recovery System |  |  | 1 | 2020-06-01 | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127760 | 1.02.16 | UAr Storage and Recovery System | 1 | 01-Jun-20* | 2020-06-01 |  |  | FNAL | C. Kendziora | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.16.01 UAr receiving |  |  | 1 | 2020-06-01 | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127780 | 1.02.16.01 | UAr receiving | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.16.02 Liquid UAr Storage |  |  | 1 | 2020-06-01 | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127800 | 1.02.16.02 | Liquid UAr Storage | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127820 | 1.02.16.02 | Cryostat | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127840 | 1.02.16.02 | Condenser | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127860 | 1.02.16.02 | Passive pressure controlled cooling control valve | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127880 | 1.02.16.02 | LN2 Delivery System | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127900 | 1.02.16.02 | Slow Control System | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127920 | 1.02.16.02 | Control Panel (line and valves) | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.02.17 DarkSide-20k Integration |  |  | 1 | 2020-06-01 | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-127940 | 1.02.17 | DarkSide-20k Integration | 1 | 01-Jun-20* | 2020-06-01 | INFN |  | Naples |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127960 | 1.02.17 | Interface with Cryostat | 1 | 01-Jun-20* | 2020-06-01 |  |  |  | A. Zani | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-127980 | 1.02.17 | interfacing with Veto | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-128000 | 1.02.17 | interfacing with calibration | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-128020 | 1.02.17 | later | 1 | 01-Jun-20* | 2020-06-01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.03 Materials |  |  | 1736 | 2017-04-01 | 2021-12-31 |  |  |  |  | 38500 | 989800 | 1028300 | 0 | 150000 | 150000 | 0 | 0 | 0 | 35000 | 0 | 35000 | 0 | 646000 | 646000
DS-130300 | 1.03 | Spreadsheet and database | 1552 | 01-Apr-17* | 2021-06-30 | INFN-CSN2 |  | LNGS | K. Pelczar | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-130100 | 1.03 | Background Budget | 1736 | 01-Apr-17* | 2021-12-31 | In kind Spain |  | CIEMAT | V. Pesudo | 38500 | 0 | 38500 | 0 | 0 | 0 |  |  | 0 | 35000 |  | 35000 |  |  | 0
DS-130500 | 1.03 | Materials Radiopurity Assay | 1736 | 01-Apr-17* | 2021-12-31 |  |  | Krakow | G. Zuzel | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-130501 | 1.03 | Materials Radiopurity Assay - BHSU assays | 1736 | 01-Apr-17* | 2021-12-31 | NSF |  | BHSU | D. Asunskis | 0 | 90000 | 90000 | 0 | 90000 | 90000 |  |  | 0 |  |  | 0 |  |  | 0
DS-130502 | 1.03 | Materials Radiopurity Assay - Temple assays | 1736 | 01-Apr-17* | 2021-12-31 | NSF |  | Temple | J. Martoff | 0 | 60000 | 60000 | 0 | 60000 | 60000 |  |  | 0 |  |  | 0 |  |  | 0
DS-130503 | 1.03 | Materials Radiopurity Assay - LSC assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Spain |  | CIEMAT | R. Santorelli | 0 | 325000 | 325000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 250000 | 250000
DS-130504 | 1.03 | Materials Radiopurity Assay - Radioch. And Mass. Spec. - CIEMAT assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Spain |  | CIEMAT | V. Pesudo | 0 | 208000 | 208000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 160000 | 160000
DS-130505 | 1.03 | Materials Radiopurity Assay - Radioc. And Mass. Spec. - LSC assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Spain |  | Zaragoza Univ. | S. Cebrian | 0 | 208000 | 208000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 160000 | 160000
DS-130506 | 1.03 | Materials Radiopurity Assay - Large surf. Assay - LSC assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Spain |  | Zaragoza Univ. | S. Cebrian | 0 | 66300 | 66300 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 51000 | 51000
DS-130507 | 1.03 | Materials Radiopurity Assay - Large surf. Assay - Krakow assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Poland |  | Krakow | G. Zuzel | 0 | 19500 | 19500 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 15000 | 15000
DS-130508 | 1.03 | Materials Radiopurity Assay - Pb/Po - Krakow assays | 1736 | 01-Apr-17* | 2021-12-31 | In kind Poland |  | Krakow | G. Zuzel | 0 | 13000 | 13000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 10000 | 10000
DS-130400 | 1.03 | Cosmogenic & Intrinsic Activity | 1280 | 01-Jul-18* | 2021-12-31 | In kind Spain |  | Zaragoza Univ. | S. Cebrian | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-130200 | 1.03 | Surface contamination, Handling & Process Development | 1096 | 01-Jan-19* | 2021-12-31 |  |  | LNL | G. Keppel | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.04 Calibrations |  |  | 1646 | 2018-06-30 | 2022-12-31 |  |  |  |  | 387500 | 486000 | 873500 | 261000 | 255000 | 516000 | 0 | 0 | 0 | 115000 | 210000 | 325000 | 0 | 0 | 0
DS-143000 | 1.04 | External deployment system, Photoneutron source and camera system | 1646 | 30-Jun-18* | 2022-12-31 | NSF |  | Temple | J. Martoff | 245000 | 147000 | 392000 | 245000 | 147000 | 392000 |  |  | 0 |  |  | 0 |  |  | 0
DS-141000 | 1.04 | Sources | 1369 | 01-Jul-18* | 2022-03-30 |  |  | Hawaii | J. Maricic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-141001 | 1.04 | Sources - Gas sources | 1369 | 01-Jul-18* | 2022-03-30 | NSF | Proposed | Princeton | P. Meyers | 7000 | 40000 | 47000 | 7000 | 40000 | 47000 |  |  | 0 |  |  | 0 |  |  | 0
DS-141002 | 1.04 | Sources - Gas sources | 1369 | 01-Jul-18* | 2022-03-30 | Poland |  | Krakow | G. Zuzel | 5500 | 5500 | 11000 | 0 | 0 | 0 |  |  | 0 | 5000 | 5000 | 10000 |  |  | 0
DS-141003 | 1.04 | Sources - ?-ray | 1369 | 01-Jul-18* | 2022-03-30 | NSF | Proposed | Virginia Tech. | B. Vogelaar | 5000 | 30000 | 35000 | 5000 | 30000 | 35000 |  |  | 0 |  |  | 0 |  |  | 0
DS-141004 | 1.04 | Sources - AmC, AmBe, AmLi | 1369 | 01-Jul-18* | 2022-03-30 | NSF | Proposed | Temple | J. Martoff | 4000 | 38000 | 42000 | 4000 | 38000 | 42000 |  |  | 0 |  |  | 0 |  |  | 0
DS-141005 | 1.04 | Sources - 252Cf | 1369 | 01-Jul-18* | 2022-03-30 | Russia |  | BNRU / MSU | M. Gromov | 11000 | 22000 | 33000 | 0 | 0 | 0 |  |  | 0 | 10000 | 20000 | 30000 |  |  | 0
DS-141006 | 1.04 | Sources - UV led for VETO calibration | 1369 | 01-Jul-18* | 2022-03-30 | Russia |  | BNRU / MSU | M. Gromov | 0 | 22000 | 22000 | 0 | 0 | 0 |  |  | 0 |  | 20000 | 20000 |  |  | 0
DS-141007 | 1.04 | Sources - Pyroelectric neutron generator | 1369 | 01-Jul-18* | 2022-03-30 | Russia |  | BNRU / MSU | A. Chepurnov | 110000 | 165000 | 275000 | 0 | 0 | 0 |  |  | 0 | 100000 | 150000 | 250000 |  |  | 0
DS-142000 | 1.04 | TPC guide mechanics | 1369 | 01-Jul-18* | 2022-03-30 | NSF | Proposed | Hawaii | J. Maricic | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-142001 | 1.04 | TPC guide mechanics | 1369 | 01-Jul-18* | 2022-03-30 | In kind IN2P3 |  | Hawaii | J. Maricic | 0 | 16500 | 16500 | 0 | 0 | 0 |  |  | 0 |  | 15000 | 15000 |  |  | 0
DarkSide.1.05 Outer Detector |  |  | 1369 | 2018-07-01 | 2022-03-30 |  |  |  |  | 0 | 2460200 | 2460200 | 0 | 0 | 0 | 0 | 400000 | 400000 | 0 | 1982000 | 1982000 | 0 | 0 | 0
DS-151000 | 1.05 | Development of Gd loaded acrylic | 639 | 01-Jul-18* | 2020-03-30 | INFN-CSN2 | Proposed | INFN-GE | B. Bottino | 0 | 116600 | 116600 | 0 | 0 | 0 |  |  | 0 |  | 106000 | 106000 |  |  | 0
DS-153000 | 1.05 | Development of VETO Reflectors | 275 | 30-Sep-19* | 2020-06-30 | Poland | Proposed | AstroCeNT | M. Kuzniak | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-155000 | 1.05 | Developent of VETO electronics | 459 | 30-Sep-19* | 2020-12-31 | INFN-CSN2 | Proposed | INFN-GE | S. Davini | 0 | 209000 | 209000 | 0 | 0 | 0 |  |  | 0 |  | 190000 | 190000 |  |  | 0
DS-155001 | 1.05 | Developent of VETO electronics - radiopurity | 459 | 30-Sep-19* | 2020-12-31 | In kind Spain | Proposed | CIEMAT | V. Pesudo | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-156000 | 1.05 | VETO Prototype | 356 | 01-Jan-20* | 2020-12-21 | INFN-CSN2 | Proposed | INFN-GE | L. Di Noto | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-157000 | 1.05 | VETO mechanics | 366 | 01-Jan-20* | 2020-12-31 | INFN-CSN2 | Proposed | INFN-GE | A. Caminata | 0 | 352000 | 352000 | 0 | 0 | 0 |  |  | 0 |  | 320000 | 320000 |  |  | 0
DS-152000 | 1.05 | Procurement of the VETO acrylic | 366 | 30-Mar-20* | 2021-03-30 | IHEP | Proposed | IHEP | C. Yang | 0 | 605000 | 605000 | 0 | 0 | 0 |  |  | 0 |  | 550000 | 550000 |  |  | 0
DS-154000 | 1.05 | Procurement of VETO Reflectors | 366 | 30-Jun-20* | 2021-06-30 |  | Proposed | AstroCeNT | M. Kuzniak | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-154001 | 1.05 | Procurement of VETO Reflectors - 3M foil | 366 | 30-Jun-20* | 2021-06-30 | CFI | Proposed | AstroCeNT | M. Kuzniak | 0 | 280000 | 280000 | 0 | 0 | 0 |  | 400000 | 400000 |  |  | 0 |  |  | 0
DS-154002 | 1.05 | Procurement of VETO Reflectors - 3M foil | 366 | 30-Jun-20* | 2021-06-30 | INFN-CIPE-2 | Proposed | AstroCeNT | M. Kuzniak | 0 | 89100 | 89100 | 0 | 0 | 0 |  |  | 0 |  | 81000 | 81000 |  |  | 0
DS-154003 | 1.05 | Procurement of VETO Reflectors - 3M foil | 366 | 30-Jun-20* | 2021-06-30 | AstroCeNT | Proposed | AstroCeNT | M. Kuzniak | 0 | 137500 | 137500 | 0 | 0 | 0 |  |  | 0 |  | 125000 | 125000 |  |  | 0
DS-154004 | 1.05 | Procurement of VETO Reflectors - TPB | 366 | 30-Jun-20* | 2021-06-30 | INFN-CIPE-2 | Proposed | AstroCeNT | M. Kuzniak | 0 | 82500 | 82500 | 0 | 0 | 0 |  |  | 0 |  | 75000 | 75000 |  |  | 0
DS-154005 | 1.05 | Procurement of VETO Reflectors - TPB | 366 | 30-Jun-20* | 2021-06-30 | AstroCeNT | Proposed | AstroCeNT | M. Kuzniak | 0 | 137500 | 137500 | 0 | 0 | 0 |  |  | 0 |  | 125000 | 125000 |  |  | 0
DS-154006 | 1.05 | Procurement of VETO Reflectors - Evaporation systems and consumables | 366 | 30-Jun-20* | 2021-06-30 | INFN-CIPE-2 | Proposed | LNGS | N. Canci | 0 | 242000 | 242000 | 0 | 0 | 0 |  |  | 0 |  | 220000 | 220000 |  |  | 0
DS-154007 | 1.05 | Procurement of VETO Reflectors - Packaging | 366 | 30-Jun-20* | 2021-06-30 | INFN-CIPE-2 | Proposed | LNGS | N. Canci | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-158000 | 1.05 | VETO installation nad commissioning | 182 | 30-Sep-21* | 2022-03-30 | INFN-CIPE-2 | Proposed | INFN-GE | A. Caminata | 0 | 165000 | 165000 | 0 | 0 | 0 |  |  | 0 |  | 150000 | 150000 |  |  | 0
DarkSide.1.06 ELECTRONICS (DAQ, Trigger and Slow Control) |  |  | 1736 | 2017-04-01 | 2021-12-31 |  |  |  |  | 1019000 | 3151400 | 4170400 | 0 | 50000 | 50000 | 1000000 | 3703000 | 4703000 | 290000 | 463000 | 753000 | 0 | 0 | 0
DarkSide.1.06.01 Readout |  |  | 1736 | 2017-04-01 | 2021-12-31 |  |  |  |  | 1019000 | 2507900 | 3526900 | 0 | 0 | 0 | 1000000 | 3138000 | 4138000 | 290000 | 283000 | 573000 | 0 | 0 | 0
DS-161000 | 1.06.01 | Readout | 1736 | 01-Apr-17* | 2021-12-31 |  | Secured | TRIUMF | F. Retiere | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-161001 | 1.06.01 | Readout boards | 1736 | 01-Apr-17* | 2021-12-31 | INFN-CSN2 | Secured | INFN-Roma1 | M. Rescigno | 0 | 311300 | 311300 | 0 | 0 | 0 |  |  | 0 |  | 283000 | 283000 |  |  | 0
DS-161002 | 1.06.01 | Readout boards | 1736 | 01-Apr-17* | 2021-12-31 | CFI | Proposed | TRIUMF | F. Retiere | 0 | 1566600 | 1566600 | 0 | 0 | 0 |  | 2238000 | 2238000 |  |  | 0 |  |  | 0
DS-161003 | 1.06.01 | Readout boards | 1736 | 01-Apr-17* | 2021-12-31 | CFI | Proposed | TRIUMF | F. Retiere | 700000 | 0 | 700000 | 0 | 0 | 0 | 1000000 |  | 1000000 |  |  | 0 |  |  | 0
DS-161004 | 1.06.01 | Readout boards | 1736 | 01-Apr-17* | 2021-12-31 | INFN-MP | Secured | INFN-Roma1 | M. Rescigno | 159500 | 0 | 159500 | 0 | 0 | 0 |  |  | 0 | 145000 |  | 145000 |  |  | 0
DS-161005 | 1.06.01 | Readout boards for veto | 1736 | 01-Apr-17* | 2021-12-31 | CFI | Proposed | TRIUMF | F. Retiere | 159500 | 630000 | 789500 | 0 | 0 | 0 |  | 900000 | 900000 | 145000 |  | 145000 |  |  | 0
DarkSide.1.06.02 Trigger |  |  | 1460 | 2017-04-01 | 2021-03-30 |  |  |  |  | 0 | 285500 | 285500 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 180000 | 180000 | 0 | 0 | 0
DS-162000 | 1.06.02 | Trigger | 1460 | 01-Apr-17* | 2021-03-30 |  | Secured | INFN-Roma1 | A. Messina | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-162001 | 1.06.02 | Trigger - clock distribution | 1460 | 01-Apr-17* | 2021-03-30 | CFI | Secured | TRIUMF | P. Amaudruz | 0 | 87500 | 87500 | 0 | 0 | 0 |  | 125000 | 125000 |  |  | 0 |  |  | 0
DS-162002 | 1.06.02 | Trigger - Event builder + Cluster | 1460 | 01-Apr-17* | 2021-03-30 | INFN-CSN2 | Secured | INFN-Roma1 | A. Messina | 0 | 198000 | 198000 | 0 | 0 | 0 |  |  | 0 |  | 180000 | 180000 |  |  | 0
DarkSide.1.06.03 Slow Control |  |  | 456 | 2020-04-01 | 2021-06-30 |  |  |  |  | 0 | 50000 | 50000 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-163000 | 1.06.03 | Slow Control | 456 | 01-Apr-20* | 2021-06-30 | NSF | Secured | TBD |  | 0 | 50000 | 50000 | 0 | 50000 | 50000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.06.04 Infrastructure and Power supply |  |  | 640 | 2020-04-01 | 2021-12-31 |  |  |  |  | 0 | 308000 | 308000 | 0 | 0 | 0 | 0 | 440000 | 440000 | 0 | 0 | 0 | 0 | 0 | 0
DS-164000 | 1.06.04 | Infrastructure and Power supply | 640 | 01-Apr-20* | 2021-12-31 | CFI | Proposed |  |  | 0 | 308000 | 308000 | 0 | 0 | 0 |  | 440000 | 440000 |  |  | 0 |  |  | 0
DarkSide.1.07 Offline |  |  | 1644 | 2018-04-01 | 2022-09-30 |  |  |  |  | 214500 | 0 | 214500 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 195000 | 0 | 0 | 0
DS-175000 | 1.07 | HW CPU and Storage | 1644 | 01-Apr-18* | 2022-09-30 | INFN-CIPE-2 | Secured | INFN-Roma1 | V. Ippolito | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-174000 | 1.07 | Physics and Analysis Interface | 549 | 01-Jul-18* | 2019-12-31 |  |  | LPNHE | C. Giganti | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-171000 | 1.07 | SW Package | 640 | 01-Jul-18* | 2020-03-31 |  |  | INFN-Roma1 | V. Ippolito | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-172000 | 1.07 | Reconstruction software | 548 | 01-Oct-18* | 2020-03-31 | IN2P3 |  | IN2P3 | D. Franco | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-172001 | 1.07 | Reconstruction software | 548 | 01-Oct-18* | 2020-03-31 |  |  | INFN-Roma1 | V. Ippolito | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-172002 | 1.07 | Reconstruction software engineer | 548 | 01-Oct-18* | 2020-03-31 | INFN-MP |  | INFN-Roma1 | V. Ippolito | 104500 | 0 | 104500 | 0 | 0 | 0 |  |  | 0 | 95000 |  | 95000 |  |  | 0
DS-173000 | 1.07 | Monte Carlo Simulations | 456 | 01-Apr-20* | 2021-06-30 | CNRS |  | Houston | P. Agnes | 110000 | 0 | 110000 | 0 | 0 | 0 |  |  | 0 | 100000 |  | 100000 |  |  | 0
DarkSide.1.08 ReD |  |  | 1095 | 2017-01-01 | 2019-12-31 |  |  |  |  | 0 | 938900 | 938900 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 399000 | 399000 | 0 | 0 | 0
DS-180340 | 1.08 | Offsite calibration | 1 | 01-Jan-17* | 2017-01-01 | DOE | Proposed | BNL | B. Walsh | 0 | 500000 | 500000 | 0 | 500000 | 500000 |  |  | 0 |  |  | 0 |  |  | 0
DS-180500 | 1.08 | nToF Spectrometer | 273 | 01-Jan-17* | 2017-09-30 | INFN-CSN2 |  | INFN-Roma1 | M. Rescigno | 0 | 58300 | 58300 | 0 | 0 | 0 |  |  | 0 |  | 53000 | 53000 |  |  | 0
DS-180330 | 1.08 | Slow Control | 365 | 01-Jan-17* | 2017-12-31 | INFN-CSN2 |  | INFN-GE | A. Caminata | 0 | 15400 | 15400 | 0 | 0 | 0 |  |  | 0 |  | 14000 | 14000 |  |  | 0
DS-180310 | 1.08 | TPC & Cryogenics | 730 | 01-Jan-17* | 2018-12-31 | INFN-CSN2 |  | INFN-NA | Y. Suvorov | 0 | 185900 | 185900 | 0 | 0 | 0 |  |  | 0 |  | 169000 | 169000 |  |  | 0
DS-180400 | 1.08 | Meutron Beam | 730 | 01-Jan-17* | 2018-12-31 | INFN-CSN2 |  | LNS | M. Gulino | 0 | 66000 | 66000 | 0 | 0 | 0 |  |  | 0 |  | 60000 | 60000 |  |  | 0
DS180200 | 1.08 | ReD Photoelectronics | 1003 | 01-Jan-17* | 2019-09-30 |  |  | INFN-BO | E. Scapparone | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-180300 | 1.08 | GAP-TPC | 1095 | 01-Jan-17* | 2019-12-31 |  |  | INFN-NA | G. Fiorillo | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-180320 | 1.08 | FE & DAQ | 1095 | 01-Jan-17* | 2019-12-31 | INFN-CSN2 |  | INFN-NA | G. Fiorillo | 0 | 25300 | 25300 | 0 | 0 | 0 |  |  | 0 |  | 23000 | 23000 |  |  | 0
DS-180600 | 1.08 | Commissioning & operation | 822 | 01-Oct-17* | 2019-12-31 | INFN-CSN2 |  | INFN-NA | G. Fiorillo | 0 | 88000 | 88000 | 0 | 0 | 0 |  |  | 0 |  | 80000 | 80000 |  |  | 0
DS-180100 | 1.08 | Simulations & Analysis | 184 | 01-Jul-18* | 2018-12-31 |  |  | LNS | L. Pandola | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.1.09 DarkSide Proto |  |  | 1006 | 2018-04-01 | 2020-12-31 |  |  |  |  | 0 | 1479400 | 1479400 | 0 | 584000 | 584000 | 0 | 0 | 0 | 0 | 814000 | 814000 | 0 | 0 | 0
DS-196000 | 1.09 | Cryostat | 183 | 01-Apr-18* | 2018-09-30 | INFN-CSN2 | Secured | INFN-Roma1 | S. De Cecco | 0 | 72600 | 72600 | 0 | 0 | 0 |  |  | 0 |  | 66000 | 66000 |  |  | 0
DS-197000 | 1.09 | Cryogenics | 731 | 01-Apr-18* | 2020-03-31 | NSF | Proposed | UCLA | H. Wang | 0 | 584000 | 584000 | 0 | 584000 | 584000 |  |  | 0 |  |  | 0 |  |  | 0
DS-191000 | 1.09 | Integration | 669 | 01-Sep-18* | 2020-06-30 | INFN-CSN2 | Secured | INFN-NA | G. Fiorillo | 0 | 67100 | 67100 | 0 | 0 | 0 |  |  | 0 |  | 61000 | 61000 |  |  | 0
DS-192000 | 1.09 | DAQ | 457 | 01-Apr-19* | 2020-06-30 | INFN-CSN2 | Secured | INFN-Roma1 | M. Rescigno | 0 | 132000 | 132000 | 0 | 0 | 0 |  |  | 0 |  | 120000 | 120000 |  |  | 0
DS-193000 | 1.09 | Calibration Setup | 305 | 01-Jun-19* | 2020-03-31 | INFN-CSN2 | Secured | INFN-NA | G. Fiorillo | 0 | 60500 | 60500 | 0 | 0 | 0 |  |  | 0 |  | 55000 | 55000 |  |  | 0
DS-194000 | 1.09 | Commissioning | 366 | 01-Oct-19* | 2020-09-30 | INFN-CSN2 | Secured | INFN-NA | G. Fiorillo | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-195000 | 1.09 | Operation | 366 | 01-Jan-20* | 2020-12-31 | INFN-CSN2 | Secured | INFN-NA | G. Fiorillo | 0 | 508200 | 508200 | 0 | 0 | 0 |  |  | 0 |  | 462000 | 462000 |  |  | 0
DarkSide.1.10 Outer Cryostat |  |  | 1297 | 2018-10-11 | 2022-04-29 |  |  |  |  | 0 | 9011200 | 9011200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8192000 | 8192000 | 0 | 0 | 0
DS-110100 | 1.1 | Warm Structure | 614 | 11-Oct-18* | 2020-06-15 | INFN-PON | Secured | CERN | M. Nessi | 0 | 2299000 | 2299000 | 0 | 0 | 0 |  |  | 0 |  | 2090000 | 2090000 |  |  | 0
DS-110200 | 1.1 | Cold Cryostat | 962 | 15-May-19* | 2021-12-31 | INFN-PON | Secured | CERN | M. Nessi | 0 | 4160200 | 4160200 | 0 | 0 | 0 |  |  | 0 |  | 3782000 | 3782000 |  |  | 0
DS-110400 | 1.1 | Argon 5.0 | 1 | 01-Jun-20* | 2020-06-01 |  |  | LNGS | F. Gabriele | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-110300 | 1.1 | Cryogenics System | 698 | 01-Jun-20* | 2022-04-29 | INFN-PON | Secured | UCLA | H. Wang | 0 | 2552000 | 2552000 | 0 | 0 | 0 |  |  | 0 |  | 2320000 | 2320000 |  |  | 0
DarkSide.2 Urania |  |  | 1341 | 2017-07-01 | 2022-11-12 |  |  |  |  | 6045674.98 | 23017733.06 | 29063408.04 | 5429674.98 | 11779633.06 | 17209308.04 | 880000 | 3406000 | 4286000 | 0 | 8049000 | 8049000 | 0 | 0 | 0
DarkSide.2.01 Urania Project Management Oversight |  |  | 751 | 2019-10-01 | 2022-09-30 |  |  |  |  | 1856044.47 | 57377.8 | 1913422.27 | 1856044.47 | 57377.8 | 1913422.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200000 | 2.01 | Project Management for FY20 | 251 | 01-Oct-19* | 2020-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 330551.68 | 0 | 330551.68 | 330551.68 | 0 | 330551.68 |  |  | 0 |  |  | 0 |  |  | 0
DS-200010 | 2.01 | Project Controls for FY20 | 251 | 01-Oct-19* | 2020-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 86245.15 | 0 | 86245.15 | 86245.15 | 0 | 86245.15 |  |  | 0 |  |  | 0 |  |  | 0
DS-200020 | 2.01 | Safety Oversight for FY20 | 251 | 01-Oct-19* | 2020-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 183776.87 | 0 | 183776.87 | 183776.87 | 0 | 183776.87 |  |  | 0 |  |  | 0 |  |  | 0
DS-200030 | 2.01 | Travel for FY20 | 251 | 01-Oct-19* | 2020-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 0 | 18692.71 | 18692.71 | 0 | 18692.71 | 18692.71 |  |  | 0 |  |  | 0 |  |  | 0
DS-200040 | 2.01 | Project Management for FY21 | 250 | 2020-10-01 | 2021-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 340798.78 | 0 | 340798.78 | 340798.78 | 0 | 340798.78 |  |  | 0 |  |  | 0 |  |  | 0
DS-200050 | 2.01 | Project Controls for FY21 | 250 | 2020-10-01 | 2021-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 88228.79 | 0 | 88228.79 | 88228.79 | 0 | 88228.79 |  |  | 0 |  |  | 0 |  |  | 0
DS-200060 | 2.01 | Safety Oversight for FY21 | 250 | 2020-10-01 | 2021-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 189473.95 | 0 | 189473.95 | 189473.95 | 0 | 189473.95 |  |  | 0 |  |  | 0 |  |  | 0
DS-200070 | 2.01 | Travel for FY21 | 250 | 2020-10-01 | 2021-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 0 | 19122.64 | 19122.64 | 0 | 19122.64 | 19122.64 |  |  | 0 |  |  | 0 |  |  | 0
DS-200080 | 2.01 | Project Management for FY22 | 250 | 2021-10-01 | 2022-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 351363.55 | 0 | 351363.55 | 351363.55 | 0 | 351363.55 |  |  | 0 |  |  | 0 |  |  | 0
DS-200090 | 2.01 | Project Controls for FY22 | 250 | 2021-10-01 | 2022-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 90258.05 | 0 | 90258.05 | 90258.05 | 0 | 90258.05 |  |  | 0 |  |  | 0 |  |  | 0
DS-200100 | 2.01 | Safety Oversight for FY22 | 250 | 2021-10-01 | 2022-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 195347.64 | 0 | 195347.64 | 195347.64 | 0 | 195347.64 |  |  | 0 |  |  | 0 |  |  | 0
DS-200110 | 2.01 | Travel for FY22 | 250 | 2021-10-01 | 2022-09-30 | BNL/DOE | Proposed | BNL | B. Walsh | 0 | 19562.46 | 19562.46 | 0 | 19562.46 | 19562.46 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.02 Urania Plant Fabrication and Delivery |  |  | 1161 | 2017-07-01 | 2020-09-03 |  |  |  |  | 0 | 9253900 | 9253900 | 0 | 400000 | 400000 | 0 | 0 | 0 | 0 | 8049000 | 8049000 | 0 | 0 | 0
DS-200200 | 2.02 | R&D activitty in support of PSA design | 853 | 01-Jul-17* | 2019-10-31 | INFN-MIUR | Spent | Naples | M. Simeone | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DS-200210 | 2.02 | PI for 2.01 Plant | 1099 | 01-Sep-17* | 2020-09-03 | INFN-CS2 | Secured | Naples | M. Simeone | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200220 | 2.02 | Feed Characterization | 484 | 05-Jul-18* | 2019-10-31 | PNNL LDRD | Spent | PNNL | H. Back | 0 | 400000 | 400000 | 0 | 400000 | 400000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200230 | 2.02 | Plant Design | 210 | 2019-11-01 | 2020-05-28 | INFN-MIUR | Secured | Naples | M. Simeone | 0 | 550000 | 550000 | 0 | 0 | 0 |  |  | 0 |  | 500000 | 500000 |  |  | 0
DS-200240 | 2.02 | Plant Construction | 70 | 2020-05-29 | 2020-08-06 | INFN-MIUR | Secured | Naples | M. Simeone | 0 | 8193900 | 8193900 | 0 | 0 | 0 |  |  | 0 |  | 7449000 | 7449000 |  |  | 0
DS-200250 | 2.02 | Plant Performance Check | 6 | 2020-08-01 | 2020-08-06 | INFN-MIUR | Secured | Naples | M. Simeone | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200260 | 2.02 | Plant Shipment | 28 | 2020-08-07 | 2020-09-03 | INFN-MIUR | Secured | Naples | M. Simeone | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03 Urania Cortez Site Prep & Plant Installation |  |  | 1007 | 2017-09-01 | 2021-09-13 |  |  |  |  | 1915800.25 | 5780400 | 7696200.25 | 1423000.25 | 5548000 | 6971000.25 | 704000 | 332000 | 1036000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200300 | 2.03 | PI for 2.02 Site Prep and Installation | 1474 | 01-Sep-17* | 2021-09-13 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03.01 Project Management |  |  | 485 | 2019-10-04 | 2021-09-13 |  |  |  |  | 1431399.85 | 750000 | 2181399.85 | 1184999.85 | 750000 | 1934999.85 | 352000 | 0 | 352000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200310 | 2.03.01 | Field Operations Engineering Support | 485 | 04-Oct-19* | 2021-09-13 | BNL/DOE | Proposed | BNL | B. Walsh | 844011.07 | 0 | 844011.07 | 844011.07 | 0 | 844011.07 |  |  | 0 |  |  | 0 |  |  | 0
DS-200320 | 2.03.01 | Extraction Operations Engineering and PNNL Support | 485 | 04-Oct-19* | 2021-09-13 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 750000 | 750000 | 0 | 750000 | 750000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200330 | 2.03.01 | Process Engineering Support | 485 | 04-Oct-19* | 2021-09-13 | CFI | Secured | Carleton | M. Boulay | 246400 | 0 | 246400 | 0 | 0 | 0 | 352000 |  | 352000 |  |  | 0 |  |  | 0
DS-200340 | 2.03.01 | Plant Operations Support | 255 | 04-Sep-20* | 2021-09-13 | BNL/DOE | Proposed | BNL | B. Walsh | 340988.79 | 0 | 340988.79 | 340988.79 | 0 | 340988.79 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03.02 Preliminary Site Work |  |  | 419 | 2019-01-07 | 2020-09-03 |  |  |  |  | 238000.4 | 1716000 | 1954000.4 | 238000.4 | 1716000 | 1954000.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200350 | 2.03.02 | PI for 2.02.02 Preliminary Site Work | 419 | 07-Jan-19* | 2020-09-03 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200360 | 2.03.02 | Gas Sampling and Shipping | 200 | 17-Jan-19* | 2019-10-31 | NSF | Secured | Houston | A. Renshaw | 0 | 15000 | 15000 | 0 | 15000 | 15000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200370 | 2.03.02 | Gas Sample Analysis | 200 | 17-Jan-19* | 2019-10-31 | NSF | Secured | Houston | A. Renshaw | 0 | 35000 | 35000 | 0 | 35000 | 35000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200380 | 2.03.02 | Feed Optimization | 233 | 17-Jan-19* | 2019-12-20 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200390 | 2.03.02 | Procurement of Control Room | 209 | 01-Jul-19* | 2020-04-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 56000 | 56000 | 0 | 56000 | 56000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200400 | 2.03.02 | Plant, electrical, storage and truck building materials and supplies | 209 | 01-Jul-19* | 2020-04-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 100000 | 100000 | 0 | 100000 | 100000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200410 | 2.03.02 | Buildings/Control Room | 297 | 01-Jul-19* | 2020-09-03 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200420 | 2.03.02 | Postdoc | 275 | 01-Aug-19* | 2020-09-03 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 238000.4 | 0 | 238000.4 | 238000.4 | 0 | 238000.4 |  |  | 0 |  |  | 0 |  |  | 0
DS-200430 | 2.03.02 | Phase I Installation | 66 | 04-Oct-19* | 2020-01-13 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 200000 | 200000 | 0 | 200000 | 200000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200440 | 2.03.02 | Land development for slabs | 120 | 2019-10-04 | 2020-03-31 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 300000 | 300000 | 0 | 300000 | 300000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200450 | 2.03.02 | Concrete Work Oversight | 142 | 04-Oct-19* | 2020-04-30 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200460 | 2.03.02 | Electrical Installation Oversight | 230 | 04-Oct-19* | 2020-09-03 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200470 | 2.03.02 | Tools and Equipment for Site Prep | 230 | 04-Oct-19* | 2020-09-03 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 150000 | 150000 | 0 | 150000 | 150000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200480 | 2.03.02 | Pipe Work | 49 | 2019-11-01 | 2020-01-15 | NSF | Secured | Houston | A. Renshaw | 0 | 50000 | 50000 | 0 | 50000 | 50000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200490 | 2.03.02 | Phase II Installation | 71 | 2020-01-14 | 2020-04-23 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 200000 | 200000 | 0 | 200000 | 200000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200500 | 2.03.02 | Pouring of concrete slabs | 22 | 2020-04-01 | 2020-04-30 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 350000 | 350000 | 0 | 350000 | 350000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200510 | 2.03.02 | Phase III Installation | 70 | 2020-04-24 | 2020-08-03 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 200000 | 200000 | 0 | 200000 | 200000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200520 | 2.03.02 | Control Room Installation | 88 | 2020-05-01 | 2020-09-03 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 25000 | 25000 | 0 | 25000 | 25000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200530 | 2.03.02 | Plant, electrical, storage and truck area building erection | 88 | 2020-05-01 | 2020-09-03 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 35000 | 35000 | 0 | 35000 | 35000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200540 | 2.03.02 | Commission Electrical System | 23 | 2020-08-04 | 2020-09-03 | NSF | Secured | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03.03 Plant & Site Integration |  |  | 241 | 2020-09-04 | 2021-08-23 |  |  |  |  | 0 | 1167000 | 1167000 | 0 | 1167000 | 1167000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200550 | 2.03.03 | Plant Installation | 121 | 2020-09-04 | 2021-03-04 | NSF Mid-scale | Proposed | UH | A. Renshaw | 0 | 1046000 | 1046000 | 0 | 1046000 | 1046000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200560 | 2.03.03 | PI for 2.02.03 Plant and Site Integration | 354 | 04-Sep-20* | 2021-08-23 | NSF | Secured | UMass | A. Pocar | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200570 | 2.03.03 | Coupling Between KM and Urania | 10 | 2021-03-05 | 2021-03-18 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 121000 | 121000 | 0 | 121000 | 121000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03.04 Full System Start-up & Commissioning |  |  | 121 | 2021-03-19 | 2021-09-08 |  |  |  |  | 0 | 1665000 | 1665000 | 0 | 1665000 | 1665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200580 | 2.03.04 | Plant start-up and commissioning Equipment and Tools | 121 | 19-Mar-21* | 2021-09-08 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 365000 | 365000 | 0 | 365000 | 365000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200590 | 2.03.04 | Plant consumables for Start-up and Commissioning | 121 | 19-Mar-21* | 2021-09-08 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 1300000 | 1300000 | 0 | 1300000 | 1300000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.03.05 QA/QC Instrumentation Installation |  |  | 743 | 2018-09-24 | 2021-09-13 |  |  |  |  | 246400 | 482400 | 728800 | 0 | 250000 | 250000 | 352000 | 332000 | 684000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200600 | 2.03.05 | Procure gas analysis instrumentation | 206 | 24-Sep-18* | 2019-07-22 | CFI | Secured | Carleton | M. Boulay | 0 | 160300 | 160300 | 0 | 0 | 0 |  | 229000 | 229000 |  |  | 0 |  |  | 0
DS-200610 | 2.03.05 | PI for 2.02.05 QA/QC Inst Installation | 1086 | 24-Sep-18* | 2021-09-13 | CFI | Secured | Carleton | R. Ajaj | 246400 | 0 | 246400 | 0 | 0 | 0 | 352000 |  | 352000 |  |  | 0 |  |  | 0
DS-200620 | 2.03.05 | Installation and characterization of gas analysis instrumentation | 537 | 2019-07-23 | 2021-09-13 | CFI | Secured | Carleton | M. Boulay | 0 | 72100 | 72100 | 0 | 0 | 0 |  | 103000 | 103000 |  |  | 0 |  |  | 0
DS-200630 | 2.03.05 | Production and Installation of large sample collecitons system | 537 | 2019-07-23 | 2021-09-13 | PNNL In-Kind | Secured | PNNL | H. Back | 0 | 250000 | 250000 | 0 | 250000 | 250000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.04 Extraction |  |  | 251 | 2021-09-14 | 2022-09-14 |  |  |  |  | 2273830.26 | 5843555.26 | 8117385.52 | 2150630.26 | 5774255.26 | 7924885.52 | 176000 | 99000 | 275000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200640 | 2.04 | PI for 2.03 Extraction | 366 | 2021-09-14 | 2022-09-14 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.04.01 Project Management |  |  | 251 | 2021-09-14 | 2022-09-14 |  |  |  |  | 2273830.26 | 450000 | 2723830.26 | 2150630.26 | 450000 | 2600630.26 | 176000 | 0 | 176000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200650 | 2.04.01 | Field Operations Engineering Support | 251 | 2021-09-14 | 2022-09-14 | BNL/DOE | Proposed | BNL | B. Walsh | 436223.96 | 0 | 436223.96 | 436223.96 | 0 | 436223.96 |  |  | 0 |  |  | 0 |  |  | 0
DS-200660 | 2.04.01 | Extraction Operations Engineering and PNNL Support | 251 | 2021-09-14 | 2022-09-14 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 450000 | 450000 | 0 | 450000 | 450000 |  |  | 0 |  |  | 0 |  |  | 0
DS-200670 | 2.04.01 | Process Engineer | 251 | 2021-09-14 | 2022-09-14 | CFI | Proposed | Carleton | M. Boulay | 123200 | 0 | 123200 | 0 | 0 | 0 | 176000 |  | 176000 |  |  | 0 |  |  | 0
DS-200680 | 2.04.01 | Technical Engineer | 251 | 2021-09-14 | 2022-09-14 | NSF | Secured | Fort Lewis | R. Haaland | 144000.03 | 0 | 144000.03 | 144000.03 | 0 | 144000.03 |  |  | 0 |  |  | 0 |  |  | 0
DS-200690 | 2.04.01 | Plant Operations Support | 251 | 14-Sep-21* | 2022-09-14 | BNL/DOE | Proposed | BNL | B. Walsh | 1570406.26 | 0 | 1570406.26 | 1570406.26 | 0 | 1570406.26 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.04.02 Plant Operations |  |  | 251 | 2021-09-14 | 2022-09-14 |  |  |  |  | 0 | 5393555.26 | 5393555.26 | 0 | 5324255.26 | 5324255.26 | 0 | 99000 | 99000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200700 | 2.04.02 | Precision gas analysis | 251 | 14-Sep-21* | 2022-09-14 | CFI | Proposed | Carleton | M. Boulay | 0 | 69300 | 69300 | 0 | 0 | 0 |  | 99000 | 99000 |  |  | 0 |  |  | 0
DS-200710 | 2.04.02 | Utilities, Consumables and Plant Maintenance | 251 | 2021-09-14 | 2022-09-14 | BNL/DOE | Proposed | BNL | B. Walsh | 0 | 5274255.26 | 5274255.26 | 0 | 5274255.26 | 5274255.26 |  |  | 0 |  |  | 0 |  |  | 0
DS-200720 | 2.04.02 | Large Volume Sample Collection | 251 | 2021-09-14 | 2022-09-14 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 50000 | 50000 | 0 | 50000 | 50000 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.04.03 Production |  |  | 366 | 2021-09-14 | 2022-09-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200730 | 2.04.03 | Production of first batch for shipment | 42 | 14-Sep-21* | 2021-10-25 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200740 | 2.04.03 | PI for 2.03.03 Production | 366 | 14-Sep-21* | 2022-09-14 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200750 | 2.04.03 | Production of second batch for shipment | 42 | 2021-10-26 | 2021-12-06 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200760 | 2.04.03 | Production of third batch for shipment | 42 | 2021-12-07 | 2022-01-17 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200770 | 2.04.03 | Production of fourth batch for shipment | 42 | 2022-01-18 | 2022-02-28 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200780 | 2.04.03 | Production of fifth batch for shipment | 42 | 2022-03-01 | 2022-04-11 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200790 | 2.04.03 | Production of sixth batch for shipment | 42 | 2022-04-12 | 2022-05-23 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200800 | 2.04.03 | Production of seventh batch for shipment | 42 | 2022-05-24 | 2022-07-04 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200810 | 2.04.03 | Production of eight batch for shipment | 72 | 2022-07-05 | 2022-09-14 | PNNL In-Kind | Proposed | PNNL | H. Back | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.05 Storage and Shipping |  |  | 1194 | 2019-07-08 | 2022-10-13 |  |  |  |  | 0 | 2082500 | 2082500 | 0 | 0 | 0 | 0 | 2975000 | 2975000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200820 | 2.05 | PI for 2.04 Storage and Shipping | 1194 | 08-Jul-19* | 2022-10-13 | CFI | Secured | Carleton | V. Strickland | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.2.05.01 Shipping and Storage Vessels Procurement |  |  | 1194 | 2019-07-08 | 2022-10-13 |  |  |  |  | 0 | 1729000 | 1729000 | 0 | 0 | 0 | 0 | 2470000 | 2470000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200830 | 2.05.01 | Procurement of shipping vessels 1-2 | 602 | 08-Jul-19* | 2021-02-28 | CFI | Secured | Carleton | M. Boulay | 0 | 420000 | 420000 | 0 | 0 | 0 |  | 600000 | 600000 |  |  | 0 |  |  | 0
DS-200840 | 2.05.01 | Procurement of shipping vessel filling equipment | 602 | 08-Jul-19* | 2021-02-28 | CFI | Secured | Carleton | M. Boulay | 0 | 49000 | 49000 | 0 | 0 | 0 |  | 70000 | 70000 |  |  | 0 |  |  | 0
DS-200850 | 2.05.01 | PI for 2.04.01 Shipping and Storage Vessels Procurement | 796 | 08-Jul-19* | 2021-09-10 | CFI | Secured | Carleton | M. Boulay | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200860 | 2.05.01 | Procurement of shipping vessels 3-5 | 296 | 2021-03-01 | 2021-12-21 | CFI | Proposed | Carleton | M. Boulay | 0 | 630000 | 630000 | 0 | 0 | 0 |  | 900000 | 900000 |  |  | 0 |  |  | 0
DS-200870 | 2.05.01 | Procurement of shipping vessels 6-8 | 296 | 2021-12-22 | 2022-10-13 | CFI | Proposed | Carleton | M. Boulay | 0 | 630000 | 630000 | 0 | 0 | 0 |  | 900000 | 900000 |  |  | 0 |  |  | 0
DarkSide.2.05.02 Ship Product |  |  | 365 | 2021-10-14 | 2022-10-13 |  |  |  |  | 0 | 353500 | 353500 | 0 | 0 | 0 | 0 | 505000 | 505000 | 0 | 0 | 0 | 0 | 0 | 0
DS-200880 | 2.05.02 | PI for 2.04.04 Ship Product | 365 | 14-Oct-21* | 2022-10-13 | CFI | Secured | Carleton | V. Strickland | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-200890 | 2.05.02 | Shipment of first batch to Sardinia | 42 | 25-Oct-21* | 2021-12-05 | CFI | Secured | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200900 | 2.05.02 | Shipment of Second batch to Sardinia | 42 | 2021-12-07 | 2022-01-17 | CFI | Secured | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200910 | 2.05.02 | Shipment of third batch to Sardinia | 42 | 2022-01-18 | 2022-02-28 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200920 | 2.05.02 | Shipment of fourth batch to Sardinia | 42 | 2022-03-01 | 2022-04-11 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200930 | 2.05.02 | Shipment of fifth batch to Sardinia | 42 | 2022-04-12 | 2022-05-23 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200940 | 2.05.02 | Shipment of sixth batch to Sardinia | 42 | 2022-05-24 | 2022-07-04 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200950 | 2.05.02 | Shipment of seventh batch to Sardinia | 42 | 2022-07-05 | 2022-08-15 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DS-200960 | 2.05.02 | Shipment of eigth batch to Sardinia | 59 | 2022-08-16 | 2022-10-13 | CFI | Proposed | Carleton | M. Boulay | 0 | 44187.5 | 44187.5 | 0 | 0 | 0 |  | 63125 | 63125 |  |  | 0 |  |  | 0
DarkSide.2.06 Shutdown |  |  | 30 | 2022-10-14 | 2022-11-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS-200970 | 2.06 | PI for Shutdown | 30 | 2022-10-14 | 2022-11-12 | NSF Mid-scale | Proposed | Houston | A. Renshaw | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DarkSide.3 ARIA + DArT |  |  | 1769 | 2016-02-01 | 2023-02-28 |  |  |  |  | 1385507.2 | 11285572 | 12671079.2 | 0 | 0 | 0 | 0 | 8000 | 8000 | 1259552 | 10254520 | 11514072 | 0 | 0 | 0
DarkSide.3.0 Aria Project Management Oversight |  |  | 1394 | 2019-05-07 | 2023-02-28 |  |  |  |  | 835507.2 | 305800 | 1141307.2 | 0 | 0 | 0 | 0 | 0 | 0 | 759552 | 278000 | 1037552 | 0 | 0 | 0
A1050 | 3 | Personnel Spent | 1 | 07-May-19* | 2019-05-07 | INFN-FISR | Secured | INFN-CA | W. Bonivento | 34100 | 0 | 34100 | 0 | 0 | 0 |  |  | 0 | 31000 |  | 31000 |  |  | 0
A1060 | 3 | Personnel Spent | 1 | 07-May-19* | 2019-05-07 | INFN-RAS | Secured | INFN-CA | W. Bonivento | 46481.6 | 0 | 46481.6 | 0 | 0 | 0 |  |  | 0 | 42256 |  | 42256 |  |  | 0
A1070 | 3 | Personner spent | 1 | 07-May-19* | 2019-05-07 | INFN-PREMIALE | Secured | INFN-CA | W. Bonivento | 39925.6 | 0 | 39925.6 | 0 | 0 | 0 |  |  | 0 | 36296 |  | 36296 |  |  | 0
A1010 | 3 | Travel | 1394 | 07-May-19* | 2023-02-28 | INFN-FISR | Secured | INFN-CA | W. Bonivento | 0 | 18700 | 18700 | 0 | 0 | 0 |  |  | 0 |  | 17000 | 17000 |  |  | 0
A1020 | 3 | Travel | 1394 | 07-May-19* | 2023-02-28 | INFN-PREMIALE | Secured | INFN-CA | W. Bonivento | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
A1030 | 3 | Travel | 1394 | 07-May-19* | 2023-02-28 | INFN-RAS | Secured | INFN-CA | W. Bonivento | 0 | 67100 | 67100 | 0 | 0 | 0 |  |  | 0 |  | 61000 | 61000 |  |  | 0
A1040 | 3 | Travel | 1394 | 07-May-19* | 2023-02-28 | INFN-RAS | Proposed | INFN-CA | W. Bonivento | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
A1080 | 3 | Personnel | 1394 | 07-May-19* | 2023-02-28 | INFN-PREMIALE | Secured | INFN-CA | W. Bonivento | 165000 | 0 | 165000 | 0 | 0 | 0 |  |  | 0 | 150000 |  | 150000 |  |  | 0
A1090 | 3 | Personnel RAS4 | 1394 | 07-May-19* | 2023-02-28 | INFN-RAS | Proposed | INFN-CA | W. Bonivento | 550000 | 0 | 550000 | 0 | 0 | 0 |  |  | 0 | 500000 |  | 500000 |  |  | 0
A1100 | 3 | Safety | 1394 | 07-May-19* | 2023-02-28 | INFN-RAS | Proposed | INFN-CA | W. Bonivento | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DarkSide.3.01 Seruci-0 and Seruci-1 Material |  |  | 2557 | 2016-02-01 | 2023-01-31 |  |  |  |  | 550000 | 10500072 | 11050072 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 9545520 | 10045520 | 0 | 0 | 0
DarkSide.3.01.01 Column Sections Construction and Tests |  |  | 1065 | 2016-02-01 | 2018-12-31 |  |  |  |  | 0 | 6301372 | 6301372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5728520 | 5728520 | 0 | 0 | 0
DS-3111 | 3.01.01 | Column Sections Construction | 1049 | 01-Feb-16* | 2018-12-15 | INFN-FISR | Secured | INFN-CA | F. Gabriele | 0 | 4290000 | 4290000 | 0 | 0 | 0 |  |  | 0 |  | 3900000 | 3900000 |  |  | 0
DS-3112 | 3.01.01 | Column Sections Construction | 1049 | 01-Feb-16* | 2018-12-15 | INFN-RAS | Secured | INFN-CA | F. Gabriele | 0 | 880000 | 880000 | 0 | 0 | 0 |  |  | 0 |  | 800000 | 800000 |  |  | 0
DS-3113 | 3.01.01 | Column Sections Construction | 1049 | 01-Feb-16* | 2018-12-15 | INFN-RAS | Secured | INFN-CA | F. Gabriele | 0 | 503518.4 | 503518.4 | 0 | 0 | 0 |  |  | 0 |  | 457744 | 457744 |  |  | 0
DS-3134 | 3.01.01 | Column Construction | 1049 | 01-Feb-16* | 2018-12-15 | INFN-PREMIALE | Secured | INFN-CA | F. Gabriele | 0 | 481553.6 | 481553.6 | 0 | 0 | 0 |  |  | 0 |  | 437776 | 437776 |  |  | 0
DS-3115 | 3.01.01 | Leak Test at Polaris (travel) | 837 | 01-Aug-16* | 2018-11-15 | INFN-FISR | Spent | INFN-CA | M. Razeti | 0 | 35200 | 35200 | 0 | 0 | 0 |  |  | 0 |  | 32000 | 32000 |  |  | 0
DS-3116 | 3.01.01 | Leak Test at CERN (travel) | 861 | 02-Aug-16* | 2018-12-10 | INFN-RAS | Secured | INFN-NA | Y. Suvorov | 0 | 44000 | 44000 | 0 | 0 | 0 |  |  | 0 |  | 40000 | 40000 |  |  | 0
DS-3117 | 3.01.01 | Leak Test at CERN (measurement) | 1 | 31-Dec-18* | 2018-12-31 | INFN-RAS | Secured | INFN-CA | L. Mapelli | 0 | 67100 | 67100 | 0 | 0 | 0 |  |  | 0 |  | 61000 | 61000 |  |  | 0
DarkSide.3.01.02 Seruci-0 |  |  | 335 | 2018-07-01 | 2019-05-31 |  |  |  |  | 0 | 222200 | 222200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202000 | 202000 | 0 | 0 | 0
DS-3128 | 3.01.02 | Electrical and Vacuum Components | 335 | 01-Jul-18* | 2019-05-31 | INFN-RAS | Secured | INFN-CA | F. Gabriele | 0 | 31900 | 31900 | 0 | 0 | 0 |  |  | 0 |  | 29000 | 29000 |  |  | 0
DS-3121 | 3.01.02 | Nitrogen Recovery (Stirling) (Inkind) | 257 | 01-Sep-18* | 2019-05-15 |  | Secured | LNGS | P. Cavalcante | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-3122 | 3.01.02 | Nitrogen Storage for Seruci-0 | 183 | 30-Sep-18* | 2019-03-31 | INFN-RAS | Proposed | INFN-CA | R. Tartaglia | 0 | 44000 | 44000 | 0 | 0 | 0 |  |  | 0 |  | 40000 | 40000 |  |  | 0
DS-3126 | 3.01.02 | Water Cooling System for Seruci-0 | 183 | 30-Sep-18* | 2019-03-31 | INFN-RAS | Proposed | INFN-CA | R. Tartaglia | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-3125 | 3.01.02 | Chiller | 243 | 01-Oct-18* | 2019-05-31 | INFN-RAS | Secured | INFN-CA | R. Tartaglia | 0 | 47300 | 47300 | 0 | 0 | 0 |  |  | 0 |  | 43000 | 43000 |  |  | 0
DS-3127 | 3.01.02 | Leak Detector | 5 | 30-Apr-19* | 2019-05-04 | INFN-RAS | Secured | INFN-CA | R. Tartaglia | 0 | 44000 | 44000 | 0 | 0 | 0 |  |  | 0 |  | 40000 | 40000 |  |  | 0
DarkSide.3.01.03 Seruci-1 |  |  | 731 | 2018-07-01 | 2020-06-30 |  |  |  |  | 0 | 1496000 | 1496000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360000 | 1360000 | 0 | 0 | 0
DS-31281 | 3.01.03 | Electrical and Vacuum Components 2 | 670 | 01-Jul-18* | 2020-04-30 | INFN-RAS | Proposed | INFN-CA | F. Gabriele | 0 | 33000 | 33000 | 0 | 0 | 0 |  |  | 0 |  | 30000 | 30000 |  |  | 0
DS-3124 | 3.01.03 | Engineering and Review | 516 | 01-Feb-19* | 2020-06-30 | INFN-RAS | Proposed | INFN-CA | R. Tartaglia | 0 | 88000 | 88000 | 0 | 0 | 0 |  |  | 0 |  | 80000 | 80000 |  |  | 0
DS-3123 | 3.01.03 | Service Gas for Installation | 61 | 01-Apr-19* | 2019-05-31 | INFN-RAS | Proposed | INFN-CA | R. Tartaglia | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-31341 | 3.01.03 | Fine Tuning System | 261 | 15-Apr-19* | 2019-12-31 | INFN-RAS | Proposed | LNGS | R. Tartaglia | 0 | 66000 | 66000 | 0 | 0 | 0 |  |  | 0 |  | 60000 | 60000 |  |  | 0
DS-3129 | 3.01.03 | Residual Gas Analyzer | 154 | 01-May-19* | 2019-10-01 | INFN-RAS | Proposed | INFN-CA | R. Tartaglia | 0 | 134200 | 134200 | 0 | 0 | 0 |  |  | 0 |  | 122000 | 122000 |  |  | 0
DS-3136 | 3.01.03 | Nitrogen Storage for Seruci-1 | 335 | 01-Jul-19* | 2020-05-30 | INFN-RAS | Proposed | LNGS | R. Tartaglia | 0 | 209000 | 209000 | 0 | 0 | 0 |  |  | 0 |  | 190000 | 190000 |  |  | 0
DS-3131 | 3.01.03 | Piller (UPS) | 1 | 01-Sep-19* | 2019-09-01 | INFN-RAS | Secured | LNGS | R. Tartaglia | 0 | 605000 | 605000 | 0 | 0 | 0 |  |  | 0 |  | 550000 | 550000 |  |  | 0
DS-3132 | 3.01.03 | Cables and Installation for Seruci-1 | 1 | 01-Sep-19* | 2019-09-01 | INFN-RAS | Proposed | LNGS | R. Tartaglia | 0 | 66000 | 66000 | 0 | 0 | 0 |  |  | 0 |  | 60000 | 60000 |  |  | 0
DS-3133 | 3.01.03 | Cryogenic Trasnfer Lines for Seruci-1 | 1 | 01-Sep-19* | 2019-09-01 | INFN-RAS | Proposed | INFN-CA | M. Razeti | 0 | 199100 | 199100 | 0 | 0 | 0 |  |  | 0 |  | 181000 | 181000 |  |  | 0
DS-3137 | 3.01.03 | Water Cooling System for Seruci-1 (Vacuum system) | 213 | 01-Oct-19* | 2020-04-30 | INFN-RAS | Proposed | LNGS | R. Tartaglia | 0 | 40700 | 40700 | 0 | 0 | 0 |  |  | 0 |  | 37000 | 37000 |  |  | 0
DarkSide.3.01.04 Installation Commissioning & Running |  |  | 1492 | 2019-01-01 | 2023-01-31 |  |  |  |  | 550000 | 2480500 | 3030500 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 2255000 | 2755000 | 0 | 0 | 0
DS-3142 | 3.01.04 | Energy and Maintenance for Seruci-0 | 365 | 01-Jan-19* | 2019-12-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 220000 | 220000 | 0 | 0 | 0 |  |  | 0 |  | 200000 | 200000 |  |  | 0
DS-3141 | 3.01.04 | Installation Commissioning & Running Seruci-0 | 214 | 01-Jun-19* | 2019-12-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DS-3144 | 3.01.04 | argon storage facilities at Seruci | 1310 | 01-Jun-19* | 2022-12-31 | INFN-RAS | Proposed |  | W. Bonivento | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-3148 | 3.01.04 | Personnel on Shift | 1341 | 2019-06-01 | 2023-01-31 | INFN-RAS | Proposed | CA | W. Bonivento | 550000 | 0 | 550000 | 0 | 0 | 0 |  |  | 0 | 500000 |  | 500000 |  |  | 0
DS-3135 | 3.01.04 | Disassembling Seruci-0 + Reassembling in Seruci-1 | 91 | 01-Mar-20* | 2020-05-30 | INFN-RAS | Proposed | LNGS | F. Gabriele | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DS-3143 | 3.01.04 | Commissioning & Running Seruci-1 | 944 | 01-Jun-20* | 2022-12-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 335500 | 335500 | 0 | 0 | 0 |  |  | 0 |  | 305000 | 305000 |  |  | 0
DS-3145 | 3.01.04 | Energy and Maintenance for Seruci-1 purification mode | 944 | 01-Jun-20* | 2022-12-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 1320000 | 1320000 | 0 | 0 | 0 |  |  | 0 |  | 1200000 | 1200000 |  |  | 0
DS-3146 | 3.01.04 | Waste disposal | 944 | 01-Jun-20* | 2022-12-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DS-3147 | 3.01.04 | Shipping from Seruci to LNGS | 396 | 01-Jan-22* | 2023-01-31 | INFN-RAS | Proposed | CA | W. Bonivento | 0 | 220000 | 220000 | 0 | 0 | 0 |  |  | 0 |  | 200000 | 200000 |  |  | 0
DarkSide.3.02 DArT in ArDM |  |  | 1168 | 2018-04-30 | 2022-12-30 |  |  |  |  | 0 | 479700 | 479700 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 431000 | 431000 | 0 | 0 | 0
DS-321 | 3.02 | Simulation and sensitivity studies (Inkind) | 1 | 30-Apr-18* | 2018-04-30 |  |  | CIEMAT | P. Garcia | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-322 | 3.02 | Mechanical drawings with CAD (inkind) | 1 | 01-May-18* | 2018-05-01 |  |  | CIEMAT | L. Romero | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-327 | 3.02 | Acrylic machining | 62 | 28-Feb-19* | 2019-04-30 | CFI | Spent | Carleton | M. Kuzniak | 0 | 1400 | 1400 | 0 | 0 | 0 |  | 2000 | 2000 |  |  | 0 |  |  | 0
DS-323 | 3.02 | machining DART (inkind) | 1 | 30-Apr-19* | 2019-04-30 | Spain |  | CIEMAT | R. Santorelli | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-326 | 3.02 | Front-end DART | 31 | 30-Apr-19* | 2019-05-30 | INFN-RAS | Spent | LNGS | A. Razeto | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-331 | 3.02 | Cryogenics and gas system DART | 31 | 30-Apr-19* | 2019-05-30 | INFN-RAS | Secured | CA | M. Razeti | 0 | 132000 | 132000 | 0 | 0 | 0 |  |  | 0 |  | 120000 | 120000 |  |  | 0
DS-334 | 3.02 | purchases DART integration | 31 | 30-Apr-19* | 2019-05-30 | INFN-RAS | Secured | CA | M. Razeti | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-335 | 3.02 | purchases DART integration | 31 | 30-Apr-19* | 2019-05-30 | Spain | Secured | CIEMAT | L. Romero | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-325 | 3.02 | Slow Control DART | 62 | 30-Apr-19* | 2019-06-30 | INFN-RAS | Secured | UNICA | S. Sulis | 0 | 16500 | 16500 | 0 | 0 | 0 |  |  | 0 |  | 15000 | 15000 |  |  | 0
DS-333 | 3.02 | new single phase setup design and assembly ArDM | 62 | 30-Apr-19* | 2019-06-30 | ETHZ | Spent | ETHZ | A. Rubbia | 0 | 38500 | 38500 | 0 | 0 | 0 |  |  | 0 |  | 35000 | 35000 |  |  | 0
DS-338 | 3.02 | trigger integration | 92 | 30-Apr-19* | 2019-07-30 | Spain | Secured | UZ | M. Martinez | 0 | 5500 | 5500 | 0 | 0 | 0 |  |  | 0 |  | 5000 | 5000 |  |  | 0
DS-339 | 3.02 | DAQ integration | 92 | 30-Apr-19* | 2019-07-30 | INFN-RAS | Secured | UZ | M. Martinez | 0 | 37400 | 37400 | 0 | 0 | 0 |  |  | 0 |  | 34000 | 34000 |  |  | 0
DS-349 | 3.02 | Feasibilility study Gas Detector Proposal (inkind) | 154 | 30-Apr-19* | 2019-09-30 |  |  | UZ | S. Cebrian | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-340 | 3.02 | Lead purchase inkind | 245 | 30-Apr-19* | 2019-12-30 |  |  | LSC | LSC Director | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-324 | 3.02 | cleaning DART (inkind) | 31 | 01-May-19* | 2019-05-31 | Spain | Secured | CIEMAT | R. Santorelli | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-328 | 3.02 | Clean TPB-coatings | 62 | 01-May-19* | 2019-07-01 | CFI | Spent | Carleton | M. Kuzniak | 0 | 1400 | 1400 | 0 | 0 | 0 |  | 2000 | 2000 |  |  | 0 |  |  | 0
DS-332 | 3.02 | infrastructure update at LSC (inkind) | 31 | 30-Jun-19* | 2019-07-30 |  |  | ETHZ | A. Rubbia | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-336 | 3.02 | travel from INFN DART integration | 57 | 02-Jul-19* | 2019-08-27 | INFN-RAS | Secured | CA | M. Razeti | 0 | 11000 | 11000 | 0 | 0 | 0 |  |  | 0 |  | 10000 | 10000 |  |  | 0
DS-3331 | 3.02 | DART Integration and tests | 119 | 02-Jul-19* | 2019-12-23 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-346 | 3.02 | Inkind operation electricity costs and atmospheric argon without lead belt | 154 | 30-Jul-19* | 2019-12-30 |  |  | LSC | LSC Director | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-343 | 3.02 | travel from CIEMAT to LSC | 1250 | 30-Jul-19* | 2022-12-30 | Spain | Secured | CIEMAT | R. Santorelli | 0 | 5500 | 5500 | 0 | 0 | 0 |  |  | 0 |  | 5000 | 5000 |  |  | 0
DS-344 | 3.02 | travel from INFN TO LSC | 1250 | 30-Jul-19* | 2022-12-30 | INFN-RAS | Secured | CA | W. Bonivento | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-345 | 3.02 | argon shipping from Aria | 1250 | 30-Jul-19* | 2022-12-30 | INFN-RAS | Secured | INFN-CA | W. Bonivento | 0 | 8800 | 8800 | 0 | 0 | 0 |  |  | 0 |  | 8000 | 8000 |  |  | 0
DS-350 | 3.02 | Construction and operation Gas Detector Proposal | 1188 | 30-Sep-19* | 2022-12-30 |  |  | UZ | S. Cebrian | 0 | 110000 | 110000 | 0 | 0 | 0 |  |  | 0 |  | 100000 | 100000 |  |  | 0
DS-329 | 3.02 | Acrylic machining radio-pure | 31 | 30-Nov-19* | 2019-12-30 | CFI | Secured | Carleton | M. Kuzniak | 0 | 1400 | 1400 | 0 | 0 | 0 |  | 2000 | 2000 |  |  | 0 |  |  | 0
DS-337 | 3.02 | Transportation to LSC DART | 6 | 23-Dec-19* | 2019-12-29 | INFN-RAS | Secured | CA | M. Razeti | 0 | 13200 | 13200 | 0 | 0 | 0 |  |  | 0 |  | 12000 | 12000 |  |  | 0
DS-347 | 3.02 | argon shipping from DS50 | 32 | 30-Dec-19* | 2020-01-30 | INFN-RAS | Secured | CA | M. Razeti | 0 | 2200 | 2200 | 0 | 0 | 0 |  |  | 0 |  | 2000 | 2000 |  |  | 0
DS-348 | 3.02 | Inkind operation electricity costs and atmospheric argon with lead belt | 1097 | 30-Dec-19* | 2022-12-30 |  |  | LSC | LSC Director | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-330 | 3.02 | Clean TPB-coatings radio-pure | 31 | 31-Dec-19* | 2020-01-30 | CFI | Secured | Carleton | M. Kuzniak | 0 | 1400 | 1400 | 0 | 0 | 0 |  | 2000 | 2000 |  |  | 0 |  |  | 0
DS-341 | 3.02 | Leadstructure and belt installation | 31 | 31-Dec-19* | 2020-01-30 | Spain | Secured | CIEMAT | L. Romero | 0 | 5500 | 5500 | 0 | 0 | 0 |  |  | 0 |  | 5000 | 5000 |  |  | 0
DarkSide.4 Infrastructures |  |  | 1 | 2016-01-01 | 2016-01-01 |  |  |  |  | 0 | 601100 | 601100 | 0 | 0 | 0 | 0 | 458000 | 458000 | 0 | 255000 | 255000 | 0 | 0 | 0
DS-411000 | 4 | Safety Analysis | 1 | 01-Jan-16* | 2016-01-01 | INFN-CSN2 |  | LNGS | F. Gabriele | 0 | 55000 | 55000 | 0 | 0 | 0 |  |  | 0 |  | 50000 | 50000 |  |  | 0
DS-412000 | 4 | Facilities | 1 | 01-Jan-16* | 2016-01-01 |  |  | LNGS | F. Gabriele | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
DS-412100 | 4 | Building | 1 | 01-Jan-16* | 2016-01-01 | INFN-PON |  | LNGS | F. Gabriele | 0 | 225500 | 225500 | 0 | 0 | 0 |  |  | 0 |  | 205000 | 205000 |  |  | 0
DS-412500 | 4 | Storage @ LNGS | 1 | 01-Jan-16* | 2016-01-01 | CFI-CAP |  | Carleton | M. Boulay | 0 | 320600 | 320600 | 0 | 0 | 0 |  | 458000 | 458000 |  |  | 0 |  |  | 0
DarkSide.5 NOA |  |  | 1646 | 2018-06-30 | 2022-12-31 |  |  |  |  | 4470400 | 9368700 | 13839100 | 0 | 0 | 0 | 0 | 0 | 0 | 4064000 | 8517000 | 12581000 | 0 | 0 | 0
DS-510000 | 5 | Faculty personnel (PS) | 1463 | 30-Jun-18* | 2022-07-01 | INFN-MP | Secured | LNGS | Al. Ianni | 396000 | 0 | 396000 | 0 | 0 | 0 |  |  | 0 | 360000 |  | 360000 |  |  | 0
DS-505000 | 5 | Mechanical-3D | 1646 | 30-Jun-18* | 2022-12-31 | INFN-CIPE-1 |  | LNGS | Al. Ianni | 0 | 268400 | 268400 | 0 | 0 | 0 |  |  | 0 |  | 244000 | 244000 |  |  | 0
DS-505001 | 5 | Mechanical-3D | 1646 | 30-Jun-18* | 2022-12-31 | INFN-MP |  | LNGS | Al. Ianni | 157300 | 0 | 157300 | 0 | 0 | 0 |  |  | 0 | 143000 |  | 143000 |  |  | 0
DS-508000 | 5 | Travels | 1646 | 30-Jun-18* | 2022-12-31 | INFN-CIPE-1 |  | LNGS | Al. Ianni | 0 | 66000 | 66000 | 0 | 0 | 0 |  |  | 0 |  | 60000 | 60000 |  |  | 0
DS-506000 | 5 | NOA Infrastructures | 365 | 01-Jan-19* | 2019-12-31 | INFN-CIPE-1 |  | LNGS | Al. Ianni | 0 | 220000 | 220000 | 0 | 0 | 0 |  |  | 0 |  | 200000 | 200000 |  |  | 0
DS-507000 | 5 | Web sie & Outreach | 1461 | 01-Jan-19* | 2022-12-31 | INFN-CIPE-1 |  | LNGS | Al. Ianni | 0 | 44000 | 44000 | 0 | 0 | 0 |  |  | 0 |  | 40000 | 40000 |  |  | 0
DS-509000 | 5 | Administrative personnel | 1097 | 01-Jul-19* | 2022-07-01 | INFN-MP | Secured | LNGS | Al. Ianni | 140800 | 0 | 140800 | 0 | 0 | 0 |  |  | 0 | 128000 |  | 128000 |  |  | 0
DS-504000 | 5 | LA-ICPMS | 1 | 01-Oct-19* | 2019-10-01 | INFN-MP |  | LNGS | Al. Ianni | 157300 | 0 | 157300 | 0 | 0 | 0 |  |  | 0 | 143000 |  | 143000 |  |  | 0
DS-502000 | 5 | Packaging facility, housing, refurbishing, gas and electricity | 1096 | 01-Oct-19* | 2022-09-30 | INFN-CIPE-1 | Secured | LNGS | Al. Ianni | 0 | 2665300 | 2665300 | 0 | 0 | 0 |  |  | 0 |  | 2423000 | 2423000 |  |  | 0
DS-503000 | 5 | Silicon packaging equipments | 1096 | 01-Oct-19* | 2022-09-30 | INFN-CIPE-1 | Secured | Bologna | E. Scapparone | 0 | 3795000 | 3795000 | 0 | 0 | 0 |  |  | 0 |  | 3450000 | 3450000 |  |  | 0
DS-503001 | 5 | Silicon packaging equipments | 1096 | 01-Oct-19* | 2022-09-30 | INFN-CIPE-2 | Secured | Bologna | E. Scapparone | 0 | 220000 | 220000 | 0 | 0 | 0 |  |  | 0 |  | 200000 | 200000 |  |  | 0
DS-511000 | 5 | Faculty personnel, engineers, technicians | 1188 | 01-Oct-19* | 2022-12-31 | INFN-MP | Secured | LNGS | Al. Ianni | 3619000 | 0 | 3619000 | 0 | 0 | 0 |  |  | 0 | 3290000 |  | 3290000 |  |  | 0
DS-501000 | 5 | Clean Room | 1005 | 01-Apr-20* | 2022-12-31 | INFN-PON | Secured | LNGS | Al. Ianni | 0 | 2090000 | 2090000 | 0 | 0 | 0 |  |  | 0 |  | 1900000 | 1900000 |  |  | 0