## all data
N tiles PROTO | 370
N tiles PROTO spares | 10%
N tiles TPC | 8280
N tiles TPC spares | 4%
N tiles Veto | 3000
N tiles Veto spares | 5%
N ch TPC | 8280
N ch Veto | 3000
N SQB | 312
N TRB | 32
N MB spares | 10%
N MB Veto eqv | 150
N MB Veto eqv spares | 7.5%
Work Package | Responsible | Group | Number | Spare | Mod | Units | Unitary Cost | Core Cost [k€] | Core Cost [k$] | Core Cost [CAD] | Core Labor [k€] | Core Labor [k$] | Core Labor [CAD] | In Kind [k€] | In Kind [k$] | NSF Cap [k$] | NSF Labor [k$] | NSF In Kind [k$] | CFI CAP [CAD] | CFI Labor [CAD] | PNNL [k$] | BNL [k$] | INFN CSN2 [k€] | RAS MIUR [k€] | RA CIPE [k€] | INFN PON [k€] | INFN In Kind [k€] | INFN MP [k€] | STSFC [k€] | Spain [k€] | ETHZ [k€] | IHEP [k€] | IN2P3 In Kind [k€] | Poland [k€] | Russia [k€] | Common Funds [k€] | Check Sum
DarkSide-20k Project | C. Galbiati [G. Fiorillo] | Princeton/GSSI [Napoli] | [5 empty] | 54208.737 | 13719.023 | 13966.3848 | 1087 | 2308 | 1560 | 1975 | 1000 | 7696.418 | 1948 | 600 | 13966.3848 | 1560 | 810 | 5972.605 | 6475.7181 | 15498 | 11935.6788 | 17203.34 | 800 | 972 | 0 | 1528 | 10 | 938 | 100 | 510 | 600 | 700 | 0
1 DarkSide-20k | An. Ianni | Princeton | [5 empty] | 31711.637 | 5161.023 | 9644.6895 | 1087 | 1554 | 1000 | 1975 | 600 | 3138.418 | 1554 | 600 | 9644.6895 | 1000 | 50 | 1972.605 | 6425.7181 | 0 | 7741.6788 | 14598.24 | 800 | 972 | 0 | 1388 | 0 | 938 | 100 | 510 | 600 | 700 | 0
1.1 Photo-Electronics | E. Scapparone | Bologna | [5 empty] | 15680.9498 | 712.605 | 0 | 872 | 0 | 0 | 0 | 600 | 490 | 0 | 600 | 0 | 0 | 0 | 222.605 | 2410.1709 | 0 | 7591.6788 | 5679.1 | 0 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 SiPMs | E. Scapparone | LNGS | [5 empty] | 6280.15 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 491.05 | 5679.1 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1 Prototyping | A. Razeto | LNGS | [5 empty] | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.1.1 Prototype SiPM runs (2 R&D production in 2017 at 30k each) | A. Gola | TIFPA | 2 |  |  | run | 35 | 70 | [14 empty] | 70 | [13 empty] | 0
1.1.1.1.2 Consumables for prototype SiPM runs | A. Razeto | LNGS | [5 empty] | 40 | [14 empty] | 40 | [13 empty] | 0
1.1.1.2 Preproduction (+1 frontside mask +1 baskside mask) | E. Scapparone | Bologna | 370 | 10% |  | tile |  | 491.05 | [16 empty] | 491.05 | [11 empty] | 0
1.1.1.3 TPC production (+1 frontside mask + 1 backside mask) | E. Scapparone | Bologna | 8280 | 10% |  | tile |  | 4279.15 | [17 empty] | 4279.15 | [10 empty] | 0
1.1.1.4 Veto production | J. Monroe | RHUL | 3000 | 5% |  | tile |  | 1399.95 | [17 empty] | 1399.95 | [10 empty] | 0
1.1.1.5 Cryo-characterization operations | E. Scapparone | Bologna | 3 |  |  | tech-m | 4 |  |  |  | 12 | [16 empty] | 12 | [8 empty] | 0
1.1.2 Tile and substrates | G. Giovanetti | Princeton | [5 empty] | 632.2681 | 490 | 0 | 332 | 0 | 0 | 0 | 600 | 490 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 632.2681 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.1 Prototyping | G. Giovanetti | Princeton | [5 empty] | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 600 | 490 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.1.1 Engineering | G. Giovanetti | Princeton | [6 empty] | 200 | 0 |  |  |  |  | 200 | 200 |  | 200 | [18 empty] | 0
1.1.2.1.2 Characterization | G. Giovanetti | Princeton | [6 empty] | 145 | 0 |  |  |  |  | 200 | 145 |  | 200 | [18 empty] | 0
1.1.2.1.3 Testing | A. Pocar | UMass | [6 empty] | 145 | 0 |  |  |  |  | 200 | 145 |  | 200 | [18 empty] | 0
1.1.2.2 Preproduction | I. Kochanek | LNGS | [5 empty] | 31.6117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.6117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.2.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | I. Kochanek | LNGS | 370 | 10% |  | tile | 0.00175 | 0.71225 | [16 empty] | 0.71225 | [11 empty] | 0
1.1.2.2.2 Components (€0.54 per resistor, 48 resistors per tile) | I. Kochanek | LNGS | 370 | 10% |  | tile | 0.02592 | 10.5494 | [16 empty] | 10.5494 | [11 empty] | 0
1.1.2.2.3 Printed circuit boards (€50/tile) | I. Kochanek | LNGS | 370 | 10% |  | tile | 0.05 | 20.35 | [16 empty] | 20.35 | [11 empty] | 0
1.1.2.3 Production | I. Kochanek | LNGS | [5 empty] | 600.6564 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600.6564 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.3.1 TPC production | A. Razeto | LNGS | [5 empty] | 410.4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410.4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.3.1.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.00175 | 15.0696 | [16 empty] | 15.0696 | [11 empty] | 0
1.1.2.3.1.2 Components (€0.54 per resistor, 48 resistors per tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.02592 | 223.2023 | [16 empty] | 223.2023 | [11 empty] | 0
1.1.2.3.1.3 Printed circuit boards (€20/tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.02 | 172.224 | [16 empty] | 172.224 | [11 empty] | 0
1.1.2.3.2 Veto production | A. Razeto | LNGS | [5 empty] | 150.1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.1605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.3.2.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.00175 | 5.5125 | [16 empty] | 5.5125 | [11 empty] | 0
1.1.2.3.2.2 Components (€0.54 per resistor, 48 resistors per tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.02592 | 81.648 | [16 empty] | 81.648 | [11 empty] | 0
1.1.2.3.2.3 Printed circuit boards (€20/tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.02 | 63 | [16 empty] | 63 | [11 empty] | 0
1.1.2.3.3 Assembly | I. Kochanek | LNGS | [5 empty] | 40 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.3.3.1 Labor for printed circuit board production (6 techs for 5 months, 1 tech for 3 months setup) | I. Kochanek | LNGS | 33 |  |  | tech-m | 4 |  |  |  | 132 | [16 empty] | 132 | [8 empty] | 0
1.1.2.3.3.2 Labor for printed circuit board testing (1 tech for 2 months testing and 3 months setup) | I. Kochanek | LNGS | 5 |  |  | tech-m | 4 |  |  |  | 20 | [16 empty] | 20 | [8 empty] | 0
1.1.2.3.3.3 Consumables | I. Kochanek | LNGS | [5 empty] | 40 | [16 empty] | 40 | [11 empty] | 0
1.1.2.3.3.4 Labor for tile packaging (2 techs for 6 months and 3 months setup) | I. Kochanek | LNGS | 18 |  |  | tech-m | 4 |  |  |  | 72 | [16 empty] | 72 | [8 empty] | 0
1.1.2.3.3.5 Labor for packaged tile testing (3 techs for 6 months and 3 months setup) | I. Kochanek | LNGS | 27 |  |  | tech-m | 4 |  |  |  | 108 | [16 empty] | 108 | [8 empty] | 0
1.1.3 Front-end electronics | A. Razeto | LNGS | [5 empty] | 781.9144 | 0 | 0 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 681.9144 | 0 | 0 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.1 Prototyping | A. Razeto | LNGS | [5 empty] | 75 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.1.1 Design and engineering (labor for engineer of FEB at LNGS) | A. Razeto | LNGS | 48 |  |  | tech-m | 4 |  |  |  | 192 | [16 empty] | 192 | [8 empty] | 0
1.1.3.1.2 Prototypes construction (materials cost for prototype FEB construction) | A. Razeto | LNGS | [5 empty] | 75 | [14 empty] | 75 | [13 empty] | 0
1.1.3.2 Preproduction | A. Razeto | LNGS | [5 empty] | 33.2723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.2723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.2.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 370 | 10% |  | tile | 0.00175 | 0.71225 | [16 empty] | 0.71225 | [11 empty] | 0
1.1.3.2.2 Components (€30/tile) | A. Razeto | LNGS | 370 | 10% |  |  | 0.03 | 12.21 | [16 empty] | 12.21 | [11 empty] | 0
1.1.3.2.3 Run (€50/tile) | A. Razeto | LNGS | 370 | 10% |  |  | 0.05 | 20.35 | [16 empty] | 20.35 | [11 empty] | 0
1.1.3.3 Production | A. Razeto | LNGS | [5 empty] | 673.6421 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 648.6421 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.3.1 TPC production | A. Razeto | LNGS | [5 empty] | 445.6296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445.6296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.3.1.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.00175 | 15.0696 | [16 empty] | 15.0696 | [11 empty] | 0
1.1.3.3.1.2 Printed circuit boards (€20/tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.02 | 172.224 | [16 empty] | 172.224 | [11 empty] | 0
1.1.3.3.1.3 Components (4 TIA and 1 FTD per tile, €30/tile) | A. Razeto | LNGS | 8280 | 4% |  | tile | 0.03 | 258.336 | [16 empty] | 258.336 | [11 empty] | 0
1.1.3.3.2 Veto production | A. Razeto | LNGS | [5 empty] | 163.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.3.2.1 Substrates (€350/m2, 25 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.00175 | 5.5125 | [16 empty] | 5.5125 | [11 empty] | 0
1.1.3.3.2.2 Printed circuit boards (€20/tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.02 | 63 | [16 empty] | 63 | [11 empty] | 0
1.1.3.3.2.3 Components (4 TIA and 1 FTD per tile, €30/tile) | A. Razeto | LNGS | 3000 | 5% |  | tile | 0.03 | 94.5 | [16 empty] | 94.5 | [11 empty] | 0
1.1.3.3.3 Assembly and testing | A. Razeto | LNGS | [5 empty] | 65 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 40 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.3.3.3.1 Consumables used during the packaging | A. Razeto | LNGS | [5 empty] | 40 | [16 empty] | 40 | [11 empty] | 0
1.1.3.3.3.2 Labor for FEB circuit board production (6 techs for 7 months) | A. Razeto | LNGS | 42 |  |  | tech-m | 4 |  |  |  | 168 | [16 empty] | 168 | [8 empty] | 0
1.1.3.3.3.3 Labor for tile circuit board testing (1 tech for 3 months) | A. Razeto | LNGS | 3 |  |  | tech-m | 4 |  |  |  | 12 | [16 empty] | 12 | [8 empty] | 0
1.1.3.3.3.4 FEB assembly (2 techs for 4 months, 3 months setup) | A. Razeto | LNGS | 21 |  |  | tech-m | 4 |  |  |  | 84 | [16 empty] | 84 | [8 empty] | 0
1.1.3.3.3.5 FEB testing (3 techs for 2 months, 3 months setup) | A. Razeto | LNGS | 18 |  |  | tech-m | 4 |  |  |  | 72 | [16 empty] | 72 | [8 empty] | 0
1.1.3.3.3.6 FEB components screening | A. Razeto | LNGS | [5 empty] | 25 |  |  | 0 | [11 empty] | 25 | [13 empty] | 0
1.1.4 Detector module integration | E. Paoloni | Pisa | [5 empty] | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.1 Prototyping (construction of first 50 PDM) | E. Paoloni | Pisa | [5 empty] | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.1.1 Clean room consumables | E. Paoloni | Pisa | [5 empty] | 4 | [14 empty] | 4 | [13 empty] | 0
1.1.4.1.2 FEE support structure (copper OFHC, indium foil, copper screws) | E. Paoloni | Pisa | [5 empty] | 7 | [14 empty] | 7 | [13 empty] | 0
1.1.4.1.3 FEE support structures construction | E. Paoloni | Pisa | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.4.1.4 Plastic frames construction | E. Paoloni | Pisa | [5 empty] | 6 | [14 empty] | 6 | [13 empty] | 0
1.1.4.1.5 Assembly tools construction | E. Paoloni | Pisa | [5 empty] | 20 | [14 empty] | 20 | [13 empty] | 0
1.1.4.1.6 Assembly tools | E. Paoloni | Pisa | [5 empty] | 3 | [14 empty] | 3 | [13 empty] | 0
1.1.4.1.7 DM shipping boxes construction | E. Paoloni | Pisa | [5 empty] | 4 | [14 empty] | 4 | [13 empty] | 0
1.1.4.1.8 Test stand for room temperature characterization of the DM | E. Paoloni | Pisa | [5 empty] | 45 | [14 empty] | 45 | [13 empty] | 0
1.1.4.2 Preproduction | E. Paoloni | Pisa | [5 empty] | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.2.1 Clean room consumables and maintenance | E. Paoloni | Pisa | [5 empty] | 4 | [14 empty] | 4 | [13 empty] | 0
1.1.4.2.2 FEE support structure (copper OFHC, indium foil, copper screws) | E. Paoloni | Pisa | [5 empty] | 7 | [14 empty] | 7 | [13 empty] | 0
1.1.4.2.3 FEE support structures construction | E. Paoloni | Pisa | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.4.2.4 Plastic frames construction | E. Paoloni | Pisa | [5 empty] | 31 | [14 empty] | 31 | [13 empty] | 0
1.1.4.2.5 PDM shipping boxes construction | E. Paoloni | Pisa | [5 empty] | 4 | [14 empty] | 4 | [13 empty] | 0
1.1.4.2.6 PDM shipping boxes dimensional qualification | E. Paoloni | Pisa | [20 empty] | 0 | [13 empty] | 0
1.1.4.3 Production | E. Paoloni | Pisa | [5 empty] | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.4.3.1 Clean room consumables and maintenance | E. Paoloni | Pisa | [5 empty] | 4 | [14 empty] | 4 | [13 empty] | 0
1.1.4.3.2 FEE support structures (copper OFHC, indium foil) | E. Paoloni | Pisa | [5 empty] | 56 | [14 empty] | 56 | [13 empty] | 0
1.1.4.3.3 FEE support structures construction | E. Paoloni | Pisa | [5 empty] | 70 | [14 empty] | 70 | [13 empty] | 0
1.1.4.3.4 Plastic frames construction | E. Paoloni | Pisa | [5 empty] | 5 | [14 empty] | 5 | [13 empty] | 0
1.1.4.3.5 PDM shipping boxes construction | E. Paoloni | Pisa | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.4.3.6 Construction Database Software development (1 physics x 1 year) | E. Paoloni | Pisa | [20 empty] | 0 | [13 empty] | 0
1.1.4.3.7 Construction Database Hardware Infrastructures | E. Paoloni | Pisa | [5 empty] | 5 | [14 empty] | 5 | [13 empty] | 0
1.1.5 Motherboard Characterization | M. La Commara | Napoli | [5 empty] | 945.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.1 Setup | M. La Commara | Napoli | [5 empty] | 812.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812.8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.1.1 Procurement of Cryostat | Y. Suvorov | Napoli | [5 empty] | 84 | [14 empty] | 84 | [13 empty] | 0
1.1.5.1.2 Procurement of DMC mechanics (support for MB) | Y. Suvorov | Napoli | [5 empty] | 18 | [14 empty] | 18 | [13 empty] | 0
1.1.5.1.3 Assembly machine | Y. Suvorov | Napoli | [5 empty] | 150 | [14 empty] | 150 | [13 empty] | 0
1.1.5.1.4 Procurement of pumping system for DMC | Y. Suvorov | Napoli | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.5.1.5 Procurement of Slow Control | M. La Commara | Napoli | [5 empty] | 26.5 | [14 empty] | 26.5 | [13 empty] | 0
1.1.5.1.6 Heating System | Y. Suvorov | Napoli | [5 empty] | 7.5 | [14 empty] | 7.5 | [13 empty] | 0
1.1.5.1.7 Procurement of Laser source (1 power unit) | M. La Commara | Napoli | [5 empty] | 12 | [14 empty] | 12 | [13 empty] | 0
1.1.5.1.7 Light source distribution | M. La Commara | Napoli | 300 |  |  |  | 0.04 | 12 | [14 empty] | 12 | [13 empty] | 0
1.1.5.1.8 Procurement of fibers (light) | A. Razeto | LNGS | 4 |  |  | 4 | 17 | 68 | [14 empty] | 68 | [13 empty] | 0
1.1.5.1.8 Procurement of feedthroughs fibers (light) | A. Razeto | LNGS | [20 empty] | 0 | [13 empty] | 0
1.1.5.1.9 Procurement of feedthroughs Vbias, Vamp, Signal for MB | M. La Commara | Napoli |  |  |  | 0.05 | 48 | 2.4 | [14 empty] | 2.4 | [13 empty] | 0
1.1.5.1.10 Procurement of optical fibers (signal) + spare | A. Razeto | LNGS | 4 | 1 |  | 5 | 17 | 85 | [14 empty] | 85 | [13 empty] | 0
1.1.5.1.11 Procurement of DAQ board (CAEN-V1725B-4ns-14bit-16ch) | M. La Commara | Napoli |  |  |  | 19 | 9.2 | 174.8 | [14 empty] | 174.8 | [13 empty] | 0
1.1.5.1.11 Crate VME 8100 | M. La Commara | Napoli | [5 empty] | 7.259 | [14 empty] | 7.259 | [13 empty] | 0
1.1.5.1.12 Receivers | W. Bonivento | Cagliari | 300 |  |  | 300 | 0.092 | 27.6 | [14 empty] | 27.6 | [13 empty] | 0
1.1.5.1.12 Crate 9 unit for receivers | M. La Commara | Napoli | [5 empty] | 6.344 | [14 empty] | 6.344 | [13 empty] | 0
1.1.5.1.13 Procurement of power supply for 5v (CAEN A2517 8ch) | M. La Commara | Napoli | [5 empty] | 7.4298 | [14 empty] | 7.4298 | [13 empty] | 0
1.1.5.1.13 Procurement of Power supply for 5V (CAEN A2518 8ch) | M. La Commara | Napoli | [5 empty] | 4.9532 | [14 empty] | 4.9532 | [13 empty] | 0
1.1.5.1.13 Procurement of Power supply for Bias SiPM tiles (CAEN A1540 HDP 12 ch SHV) | M. La Commara | Napoli | [5 empty] | 3.9894 | [14 empty] | 3.9894 | [13 empty] | 0
1.1.5.1.13 Sy4527 basic Multichannel Power Supply System | M. La Commara | Napoli | [5 empty] | 7.198 | [14 empty] | 7.198 | [13 empty] | 0
1.1.5.1.13 A4533 Double Power Supply Unit | M. La Commara | Napoli | [5 empty] | 1.8544 | [14 empty] | 1.8544 | [13 empty] | 0
1.1.5.1.13 Filters | M. La Commara | Napoli | [5 empty] | 1.45 | [14 empty] | 1.45 | [13 empty] | 0
1.1.5.1.14 Noise Power Spectrum analysis | [7 empty] | 5.526 | [14 empty] | 5.526 | [13 empty] | 0
1.1.5.1.15 Computing + data management | S. Catalanotti | Napoli | [5 empty] | 79 | [14 empty] | 79 | [13 empty] | 0
1.1.5.1.16 Scaffolding for storage | M. La Commara | Napoli | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.5.2 Preproduction | Y. Suvorov | Napoli | [5 empty] | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.2.1 Transport | Y. Suvorov | Napoli | [5 empty] | 3 | [14 empty] | 3 | [13 empty] | 0
1.1.5.2.2 Cryogenic liquids | Y. Suvorov | Napoli | [5 empty] | 20 | [14 empty] | 20 | [13 empty] | 0
1.1.5.2.3 Clean room maintenance | Y. Suvorov | Napoli | [5 empty] | 10 | [14 empty] | 10 | [13 empty] | 0
1.1.5.3 Production | Y. Suvorov | Napoli | [5 empty] | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.5.3.1 DM characterization at cryogenic temperature (tech. support for tests) | Y. Suvorov | Napoli | [20 empty] | 0 | [13 empty] | 0
1.1.5.3.2 DM Characterization at cryogenic (PDM characterization) | Y. Suvorov | Napoli | [20 empty] | 0 | [13 empty] | 0
1.1.5.3.3 Transport | Y. Suvorov | Napoli | [5 empty] | 30 | [14 empty] | 30 | [13 empty] | 0
1.1.5.3.4 Cryogenic liquids | Y. Suvorov | Napoli | [5 empty] | 40 | [14 empty] | 40 | [13 empty] | 0
1.1.5.3.5 Clean Room maintenance + cryo liquids contract | Y. Suvorov | Napoli | [5 empty] | 30 | [14 empty] | 30 | [13 empty] | 0
1.1.6 Steering Module | S. Rescia | BNL | [5 empty] | 0 | 222.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.1 Prototyping (10 pieces) | S. Rescia | BNL | [6 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.1.1 Printed circuit boards (100 cm2, 6 layers) | S. Rescia | BNL | [6 empty] | 4 | [12 empty] | 4 | [8 empty] | 0 | [5 empty] | 0
1.1.6.1.2 Run | S. Rescia | BNL | [6 empty] | 4 | [12 empty] | 4 | [8 empty] | 0 | [5 empty] | 0
1.1.6.1.3 Argon for cryogenic test (1000 l at €1.3/l) | S. Rescia | BNL | [6 empty] | 2 | [12 empty] | 2 | [8 empty] | 0 | [5 empty] | 0
1.1.6.2 Preproduction (10 pieces) | S. Rescia | BNL | [6 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.2.1 Printed circuit boards (100 cm2, 6 layers) | S. Rescia | BNL | [6 empty] | 4 | [12 empty] | 4 | [8 empty] | 0 | [5 empty] | 0
1.1.6.2.2 Run | S. Rescia | BNL | [6 empty] | 6 | [12 empty] | 6 | [8 empty] | 0 | [5 empty] | 0
1.1.6.2.3 Argon for cryogenic test (1000 l at €1.3/l) | S. Rescia | BNL | [6 empty] | 1.3 | [12 empty] | 1.3 | [8 empty] | 0 | [5 empty] | 0
1.1.6.3 Production | S. Rescia | BNL | [6 empty] | 161.305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.6.3.1 Substrates (€350/m2, 312.5 cm2/layer, 2 layer/MB, €1.75/MB) | S. Rescia | BNL | 400 | 10% |  | MB | 0.021875 |  | 9.625 | [12 empty] | 9.625 | [8 empty] | 0 | [5 empty] | 0
1.1.6.3.2 Printed circuit boards (€22/MB) | S. Rescia | BNL | 400 | 10% |  | MB | 0.022 |  | 9.68 | [12 empty] | 9.68 | [8 empty] | 0 | [5 empty] | 0
1.1.6.3.3 Run (€300/MB) | S. Rescia | BNL | 400 | 10% |  | MB | 0.3 |  | 132 | [12 empty] | 132 | [8 empty] | 0 | [5 empty] | 0
1.1.6.3.4 Tests at cryogenic temperature (300 l/w × 20 w at €1.3/l) | S. Rescia | BNL | [6 empty] | 10 | [12 empty] | 10 | [8 empty] | 0 | [5 empty] | 0
1.1.7 Optolink | A. Razeto | Cagliari/LNGS | [5 empty] | 5094.8286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 272.9691 | 0 | 4821.8595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.1 Prototyping | A. Razeto | Cagliari/LNGS | [5 empty] | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.1.1 Design and engineering | A. Razeto | Cagliari/LNGS | [5 empty] | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.1.1.1 R&D on optical transmission module at Cagliari (forfait est. for 2 years of R&D at 15€/y) | W. Bonivento | Cagliari | [5 empty] | 30 | [14 empty] | 30 | [13 empty] | 0
1.1.7.1.1.2 Fibers prototype, 2 bundles (45€/bundles) | A. Razeto | LNGS | [5 empty] | 91 | [14 empty] | 91 | [13 empty] | 0
1.1.7.2 Preproduction (20 MB, 370 ch) | A. Razeto | LNGS | [5 empty] | 151.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.2.1 Substrates (€350/m2, 312.5 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 18 | 10% |  | MB | 0.021875 | 0.43312 | [14 empty] | 0.43312 | [13 empty] | 0
1.1.7.2.2 Fibers (100 fibers/bundle, €17k/bundle) | A. Razeto | LNGS | 370 | 10% |  | tile | 17 | 85 | [14 empty] | 85 | [13 empty] | 0
1.1.7.2.3 Components (€49/ch) | W. Bonivento | Cagliari | 370 | 10% |  | tile | 0.049 | 19.943 | [14 empty] | 19.943 | [13 empty] | 0
1.1.7.2.4 Printed circuit boards (€7/ch) | W. Bonivento | Cagliari | 370 | 10% |  | tile | 0.007 | 2.849 | [14 empty] | 2.849 | [13 empty] | 0
1.1.7.2.5 Receivers (€92/ch) | W. Bonivento | Cagliari | 370 | 10% |  | tile | 0.092 | 37.444 | [14 empty] | 37.444 | [13 empty] | 0
1.1.7.2.6 Crate VME 9U | M. Guerzoni/A. Margotti | Bologna | 1 |  |  | crate | 6.3 | 6.3 | [14 empty] | 6.3 | [13 empty] | 0
1.1.7.3 Production | A. Razeto | LNGS | [5 empty] | 4821.8595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4821.8595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.3.1 TPC Production | A. Razeto | LNGS | [5 empty] | 3427.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.3.1.1 Substrates (€350/m2, 312.5 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 344 | 10% |  | MB | 0.022 | 8.3248 | [16 empty] | 8.3248 | [11 empty] | 0
1.1.7.3.1.2 Fibers (100 fibers/bundle, €25k/bundle) | A. Razeto | LNGS | 8280 | 4% |  | ch | 25 | 2175 | [16 empty] | 2175 | [11 empty] | 0
1.1.7.3.1.3 Components (€49/ch) | A. Razeto | LNGS | 8280 | 4% |  | ch | 0.049 | 421.9488 | [16 empty] | 421.9488 | [11 empty] | 0
1.1.7.3.1.4 Printed circuit boards (€7/ch) | A. Razeto | LNGS | 8280 | 4% |  | ch | 0.007 | 60.2784 | [16 empty] | 60.2784 | [11 empty] | 0
1.1.7.3.1.5 Receivers (€92/ch) | W. Bonivento | Cagliari | 8280 | 4% |  | ch | 0.092 | 761.76 | [16 empty] | 761.76 | [11 empty] | 0
1.1.7.3.1 Veto Production | A. Razeto | LNGS | [5 empty] | 1255.9475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1255.9475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7.3.1.1 Substrates (€350/m2, 312.5 cm2/layer, 2 layer/tile, €1.75/tile) | A. Razeto | LNGS | 150 | 7.5% |  | MB | 0.022 | 3.5475 | [16 empty] | 3.5475 | [11 empty] | 0
1.1.7.3.1.2 Fibers (100 fibers/bundle, €25k/bundle) | A. Razeto | LNGS | 3000 | 5% |  | ch | 25 | 800 | [16 empty] | 800 | [11 empty] | 0
1.1.7.3.1.3 Components (€49/ch) | A. Razeto | LNGS | 3000 | 5% |  | ch | 0.049 | 154.35 | [16 empty] | 154.35 | [11 empty] | 0
1.1.7.3.1.4 Printed circuit boards (€7/ch) | A. Razeto | LNGS | 3000 | 5% |  | ch | 0.007 | 22.05 | [16 empty] | 22.05 | [11 empty] | 0
1.1.7.3.1.5 Receivers (€92/ch) | A. Razeto | LNGS | 3000 | 5% |  | ch | 0.092 | 276 | [16 empty] | 276 | [11 empty] | 0
1.1.7.3.3 Crates VME 9U | A. Razeto | LNGS | 21 | 1 |  | crate | 6.3 | 138.6 | [16 empty] | 138.6 | [11 empty] | 0
1.1.8 Cabling | M. Citterio | Milano/Bologna | [5 empty] | 227.4777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227.4777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.1 Prototyping | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.1.1 Motherboards strips to connect the 25 PDMs to the steering module and optolink board (2 pieces (1 MB +spare) x 500€/piece) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 2.5 | [14 empty] | 2.5 | [13 empty] | 0
1.1.8.1.2 Connectors (prototype) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 1.3 | [14 empty] | 1.3 | [13 empty] | 0
1.1.8.1.3 Cables to connect the steering module to the power supply feedthrough (100m x 6€/m) | M. Citterio | Milano | [5 empty] | 0.6 | [14 empty] | 0.6 | [13 empty] | 0
1.1.8.2 Preproduction | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 6.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.2.1 Motherboards strips Arlon procurement, 25 x 625cm2 (Arlon, 350€/m2) | M. Guerzoni/A. Margotti | Bologna | 25 |  |  |  | 0.065625 | 1.6406 | [14 empty] | 1.6406 | [13 empty] | 0
1.1.8.2.2 Procurement (25 pieces (1 for MB +10% spare) x 100€piece) |  |  | 25 |  |  |  | 0.1 | 2.5 | [14 empty] | 2.5 | [13 empty] | 0
1.1.8.2.3 Connectors (22 x ( 50 PDM-MB+ 2 MB-SM + 4 MB -Optolink) + 10 % spares) | M. Citterio | Milano | [5 empty] | 2.1 | [14 empty] | 2.1 | [13 empty] | 0
1.1.8.2.4 Cables to connect the steering module to the power subbly feedthroughs (22 x 6€/m x 5m) | M. Citterio | Milano | [5 empty] | 0.66 | [14 empty] | 0.66 | [13 empty] | 0
1.1.8.3 Production | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 216.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.8.3.1 Substrates (€350/m2 × 625 cm2, €22/MB) procurement, 356 x 625cm2 (Arlon, 350€/m2) | M. Guerzoni/A. Margotti | Bologna | 344 | 10% |  | MB | 0.032813 | 12.4163 | [14 empty] | 12.4163 | [13 empty] | 0
1.1.8.3.2 Motherboard strips to connect the 25 PDMs to the steering module and optolink board ((1 per motherboard ) x 100 € / piece) | M. Guerzoni/A. Margotti | Bologna | 344 | 10% |  | MB | 0.1 | 37.84 | [14 empty] | 37.84 | [13 empty] | 0
1.1.8.3.3 Connectors (N_MB x 87€ x ( 50 PDM-MB+ 2 MB-SM + 4 MB -Optolink) ) | M. Citterio | Milano | 344 | 10% |  | MB | 0.087 | 32.9208 | [14 empty] | 32.9208 | [13 empty] | 0
1.1.8.3.4 Cables to connect the steering module to the power supply feedthroughs (356 MB x 20 €/m x 15 m x 0.9 (avarage length)) | M. Citterio | Milano | 344 | 10% |  | MB | 0.0864 | 133 | [14 empty] | 133 | [13 empty] | 0
1.1.9 Motherboard | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 135.6203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.6203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.1 Prototyping (10 pieces) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 1.6058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.1.1 Copper OFHC for DarkSide-Proto (10 copper sheet of 27x27x1 cm3 at €22.5/kg) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 1.6058 | [14 empty] | 1.6058 | [13 empty] | 0
1.1.9.1.2 Motherboard milling | M. Guerzoni/A. Margotti | Bologna | [34 empty] | 0
1.1.9.2 Preproduction (25 pieces) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 4.0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.2.1 Copper OFHC for DarkSide-Proto (25 copper sheet of 27x27x1 cm3 at €22.5/kg) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 4.0145 | [14 empty] | 4.0145 | [13 empty] | 0
1.1.9.2.2 Motherboard milling | M. Guerzoni/A. Margotti | Bologna | [34 empty] | 0
1.1.9.3 Production | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.9.3.1 Copper OFHC for DarkSide (26x26x5mm=4kg)x400 round bars (3.5kg)x22.5€/kg) | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 67 | [14 empty] | 67 | [13 empty] | 0
1.1.9.3.2 Motherboards milling | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 60 | [14 empty] | 60 | [13 empty] | 0
1.1.9.3.3 Shipping | M. Guerzoni/A. Margotti | Bologna | [5 empty] | 3 | [14 empty] | 3 | [13 empty] | 0
1.1.10 SiPM power supplies | A. Razeto | LNGS | [5 empty] | 964.5869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.5869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.1 TPC SiPM power supplies | A. Razeto | LNGS | [5 empty] | 637.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.1.1 HV boards (CAEN A1540LX, 1 slot/board, 24 ch/board) | A. Razeto | LNGS | 15 | 2 | 24 | boards | 5.9414 | 101.0038 | [16 empty] | 101.0038 | [11 empty] | 0
1.1.10.1.2 HV crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 24 ch/board) | A. Razeto | LNGS | 1 | 1 | 16 | crates | 7.198 | 14.396 | [16 empty] | 14.396 | [11 empty] | 0
1.1.10.1.3 HV power unit (CAEN A4532) | A. Razeto | LNGS | 1 | 1 |  | crates | 1.037 | 2.074 | [16 empty] | 2.074 | [11 empty] | 0
1.1.10.1.4 HV filters (€122/4ch) | A. Razeto | LNGS | 344 | 10% |  | MB | 0.0305 | 11.5412 | [16 empty] | 11.5412 | [11 empty] | 0
1.1.10.1.5 LV +5V boards (CAEN A2518, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 43 | 5 | 8 | boards | 2.4766 | 118.8768 | [16 empty] | 118.8768 | [11 empty] | 0
1.1.10.1.6 LV +5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 3 | 1 | 16 | crates | 7.198 | 28.792 | [16 empty] | 28.792 | [11 empty] | 0
1.1.10.1.7 LV +5V power unit (CAEN A4533) | A. Razeto | LNGS | 3 | 1 |  | crates | 1.8544 | 7.4176 | [16 empty] | 7.4176 | [11 empty] | 0
1.1.10.1.8 LV +5V filters | A. Razeto | LNGS | 344 | 10% |  | MB | 0.0305 | 11.5412 | [16 empty] | 11.5412 | [11 empty] | 0
1.1.10.1.9 LV +2.5V boards (CAEN A2517, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 43 | 5 | 8 | boards | 2.4766 | 118.8768 | [16 empty] | 118.8768 | [11 empty] | 0
1.1.10.1.10 LV +2.5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 3 | 1 | 16 | crates | 7.198 | 28.792 | [16 empty] | 28.792 | [11 empty] | 0
1.1.10.1.11 LV +2.5V primary power unit (CAEN A4533) | A. Razeto | LNGS | 3 | 1 |  | crates | 1.8544 | 7.4176 | [16 empty] | 7.4176 | [11 empty] | 0
1.1.10.1.12 LV +2.5V secondary power unit (CAEN A4532) | A. Razeto | LNGS | 3 | 1 |  | crates | 1.037 | 4.148 | [16 empty] | 4.148 | [11 empty] | 0
1.1.10.1.13 LV +2.5V filters | A. Razeto | LNGS | 344 | 10% |  | MB | 0.0305 | 11.5412 | [16 empty] | 11.5412 | [11 empty] | 0
1.1.10.1.14 LV -2.5V boards (CAEN A2517, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 43 | 5 | 8 | boards | 2.4766 | 118.8768 | [16 empty] | 118.8768 | [11 empty] | 0
1.1.10.1.15 LV -2.5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 3 | 1 | 16 | crates | 7.198 | 28.792 | [16 empty] | 28.792 | [11 empty] | 0
1.1.10.1.16 LV -2.5V primary power unit (CAEN A4533) | A. Razeto | LNGS | 3 | 1 |  | crates | 1.8544 | 7.4176 | [16 empty] | 7.4176 | [11 empty] | 0
1.1.10.1.17 LV -2.5V secondary power unit (CAEN A4532) | A. Razeto | LNGS | 3 | 1 |  | crates | 1.037 | 4.148 | [16 empty] | 4.148 | [11 empty] | 0
1.1.10.1.18 LV -2.5V filters | A. Razeto | LNGS | 344 | 10% |  | MB | 0.0305 | 11.5412 | [16 empty] | 11.5412 | [11 empty] | 0
1.1.10.2 Veto SiPM power supplies | A. Razeto | LNGS | [5 empty] | 327.3931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.3931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.10.2.1 HV boards (CAEN A1540LX, 1 slot/board, 24 ch/board) | A. Razeto | LNGS | 7 | 1 | 24 | boards | 5.9414 | 47.5312 | [16 empty] | 47.5312 | [11 empty] | 0
1.1.10.2.2 HV crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 24 ch/board) | A. Razeto | LNGS | 1 | 1 | 16 | crates | 7.198 | 14.396 | [16 empty] | 14.396 | [11 empty] | 0
1.1.10.2.3 HV power unit (CAEN A4532) | A. Razeto | LNGS | 1 | 1 |  | crates | 1.037 | 2.074 | [16 empty] | 2.074 | [11 empty] | 0
1.1.10.2.4 HV filters (€122/4ch) | A. Razeto | LNGS | 150 | 7.5% |  | MB | 0.0305 | 4.9181 | [16 empty] | 4.9181 | [11 empty] | 0
1.1.10.2.5 LV +5V boards (CAEN A2518, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 19 | 2 | 8 | boards | 2.4766 | 52.0086 | [16 empty] | 52.0086 | [11 empty] | 0
1.1.10.2.6 LV +5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 2 | 1 | 16 | crates | 7.198 | 21.594 | [16 empty] | 21.594 | [11 empty] | 0
1.1.10.2.7 LV +5V power unit (CAEN A4533) | A. Razeto | LNGS | 2 | 1 |  | crates | 1.8544 | 5.5632 | [16 empty] | 5.5632 | [11 empty] | 0
1.1.10.2.8 LV +5V filters | A. Razeto | LNGS | 150 | 7.5% |  | MB | 0.0305 | 4.9181 | [16 empty] | 4.9181 | [11 empty] | 0
1.1.10.2.9 LV +2.5V boards (CAEN A2517, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 19 | 2 | 8 | boards | 2.4766 | 52.0086 | [16 empty] | 52.0086 | [11 empty] | 0
1.1.10.2.10 LV +2.5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 2 | 1 | 16 | crates | 7.198 | 21.594 | [16 empty] | 21.594 | [11 empty] | 0
1.1.10.2.11 LV +2.5V primary power unit (CAEN A4533) | A. Razeto | LNGS | 2 | 1 |  | crates | 1.8544 | 5.5632 | [16 empty] | 5.5632 | [11 empty] | 0
1.1.10.2.12 LV +2.5V secondary power unit (CAEN A4532) | A. Razeto | LNGS | 2 | 1 |  | crates | 1.037 | 3.111 | [16 empty] | 3.111 | [11 empty] | 0
1.1.10.2.13 LV +2.5V filters | A. Razeto | LNGS | 150 | 7.5% |  | MB | 0.0305 | 4.9181 | [16 empty] | 4.9181 | [11 empty] | 0
1.1.10.2.14 LV -2.5V boards (CAEN A2517, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 19 | 2 | 8 | boards | 2.4766 | 52.0086 | [16 empty] | 52.0086 | [11 empty] | 0
1.1.10.2.15 LV -2.5V crates (CAEN SY4527, 16 slot/crate, 1 slot/board, 8 ch/board) | A. Razeto | LNGS | 2 | 1 | 16 | crates | 7.198 | 21.594 | [16 empty] | 21.594 | [11 empty] | 0
1.1.10.2.16 LV -2.5V primary power unit (CAEN A4533) | A. Razeto | LNGS | 2 | 1 |  | crates | 1.8544 | 5.5632 | [16 empty] | 5.5632 | [11 empty] | 0
1.1.10.2.117 LV -2.5V secondary power unit (CAEN A4532) | A. Razeto | LNGS | 2 | 1 |  | crates | 1.037 | 3.111 | [16 empty] | 3.111 | [11 empty] | 0
1.1.10.2.18 LV -2.5V filters | A. Razeto | LNGS | 150 | 7.5% |  | MB | 0.0305 | 4.9181 | [16 empty] | 4.9181 | [11 empty] | 0
1.1.11 Integrated electronics | M. Rocha | Torino | [5 empty] | 1513.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.1 R&D | M. Rocha | Torino | [5 empty] | 42.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.2 Prototypes small scale | M. Rocha | Torino | [5 empty] | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.3 Prototype active substrate | M. Rocha | Torino | [5 empty] | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.11.4 Production of integrated electronics for Veto | M. Rocha | Torino | 3000 |  |  | tile | 0.4 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Inner detector | H. Wang | UCLA | [5 empty] | 1077.12 | 3238.418 | 5536 | 0 | 1142 | 0 | 1075 | 0 | 1988.418 | 1142 | 0 | 5536 | 0 | 0 | 1250 | 200 | 0 | 150 | 727.12 | 0 | 0 | 0 | 775 | 0 | 0 | 0 | 0 | 300 | 0 | 0
1.2.1 HHV feedthrough | E. Pantic | Davis | [5 empty] | 0 | 125.667 | 0 | 0 | 74 | 0 | 0 | 0 | 125.667 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.1 Prototyping (design and material) | E. Pantic | Davis | [6 empty] | 6.667 | 0 | [5 empty] | 6.667 | 0 | [19 empty] | 0
1.2.1.2 Engineering labor | E. Pantic | Davis | [9 empty] | 74 | 0 |  |  | 0 | 74 | [19 empty] | 0
1.2.1.3 Preproduction (materials, tools and machining) | E. Pantic | Davis | [6 empty] | 10 | 0 | [5 empty] | 10 | 0 | [19 empty] | 0
1.2.1.4 Production (materials, machining and testing) | E. Pantic | Davis | [6 empty] | 60 | 0 | [5 empty] | 60 | 0 | [19 empty] | 0
1.2.1.5 HV power supplies for cathode, first ring and grid | E. Pantic | Davis | [6 empty] | 30 | 0 | [5 empty] | 30 | 0 | [19 empty] | 0
1.2.1.6 Shipping and materials and supplies | E. Pantic | Davis | [6 empty] | 19 | 0 | [5 empty] | 19 | 0 | [19 empty] | 0
1.2.2 Field cage | E. Pantic | Davis | [5 empty] | 0 | 201 | 0 | 0 | 74 | 0 | 0 | 0 | 201 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2.1 Prototyping (design, material, tools) | E. Pantic | Davis | [6 empty] | 13 | 0 | [5 empty] | 13 | 0 | [19 empty] | 0
1.2.2.2 Engineering labor | E. Pantic | Davis | [9 empty] | 74 | 0 |  |  | 0 | 74 | [19 empty] | 0
1.2.2.3 Preproduction (materials and machining) | E. Pantic | Davis | [6 empty] | 13 | 0 | [5 empty] | 13 | 0 | [19 empty] | 0
1.2.2.4 Production (materials, machining and testing) | E. Pantic | Davis | [6 empty] | 138 | 0 | [5 empty] | 138 | 0 | [19 empty] | 0
1.2.2.5 HHV resistors procurement | E. Pantic | Davis | [6 empty] | 18 | 0 | [5 empty] | 18 | 0 | [19 empty] | 0
1.2.2.6 Shipping and materials and supplies | E. Pantic | Davis | [6 empty] | 19 | 0 | [5 empty] | 19 | 0 | [19 empty] | 0
1.2.3 Reflector cage | E. Pantic | Davis | [5 empty] | 0 | 36.383 | 83 | 0 | 74 | 0 | 630 | 0 | 36.383 | 74 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.3.1 Prototyping (design, material and machining) | E. Pantic | Davis | [6 empty] | 5 | 0 | [5 empty] | 5 | 0 | [19 empty] | 0
1.2.3.2 Engineering labor | R. Santorelli | CIEMAT | [9 empty] | 74 | 0 | 550 |  | 0 | 74 | [12 empty] | 550 | [6 empty] | 0
1.2.3.3 Preproduction (machining) | E. Pantic | Davis | [6 empty] | 12.383 | 0 |  |  |  | 30 |  | 12.383 | 0 | [12 empty] | 30 | [6 empty] | 0
1.2.3.4 Production (machining) | M. Boulay | Carleton | [6 empty] | 0 | 19 |  |  |  | 50 |  |  | 0 |  | 19 | [10 empty] | 50 | [6 empty] | 0
1.2.3.5 Acrylic and 3M foil procurement | M. Boulay | Carleton | [7 empty] | 64 | [6 empty] | 0 |  | 64 | [17 empty] | 0
1.2.3.6 Shipping and materials and supplies | E. Pantic | Davis | [6 empty] | 19 | 0 | [5 empty] | 19 | 0 | [19 empty] | 0
1.2.4 Anode & cathode planes | G. Giovanetti | Princeton | [5 empty] | 0 | 120 | 318 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 0 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.4.1 Prototyping (design, materials and machining) | G. Giovanetti | Princeton | [6 empty] | 60 | 0 |  | 0 | 0 |  |  | 60 | [20 empty] | 0
1.2.4.2 Preproduction (materials and machining) | G. Giovanetti | Princeton | [6 empty] | 60 | 0 | [5 empty] | 60 | [20 empty] | 0
1.2.4.3 Parts and materials | M. Boulay | Carleton | [6 empty] | 0 | 318 |  | 0 | 0 | [5 empty] | 318 | [17 empty] | 0
1.2.4.4 Labor | R. Santorelli | CIEMAT | [11 empty] | 120 | [15 empty] | 120 | [6 empty] | 0
1.2.5 Wire Plane | A. Renshaw | Houston | [5 empty] | 0 | 120 | 0 | 0 | 200 | 0 | 0 | 0 | 120 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5.1 Design and prototyping | A. Renshaw | Houston | [6 empty] | 20 | 0 | [5 empty] | 20 | 0 | [19 empty] | 0
1.2.5.2 Engineering labor | A. Renshaw | Houston | [9 empty] | 200 | 0 |  |  | 0 | 200 | [19 empty] | 0
1.2.5.3 Materials procurement | A. Renshaw | Houston | [5 empty] | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5.3.1 Stainless steel frame | A. Renshaw | Houston | [5 empty] | 0 | 30 | 0 | [5 empty] | 30 | [6 empty] | 0 | [13 empty] | 0
1.2.5.3.2 Stainless steel wire | A. Renshaw | Houston | [6 empty] | 10 | 0 | [5 empty] | 10 | [6 empty] | 0 | [13 empty] | 0
1.2.5.3.3 Stainless steel pillars | A. Renshaw | Houston | [6 empty] | 15 | 0 | [5 empty] | 15 | [6 empty] | 0 | [13 empty] | 0
1.2.5.4 Fabrication and assembly of parts | A. Renshaw | Houston | [6 empty] | 25 | 0 | [5 empty] | 25 | [20 empty] | 0
1.2.5.5 Shipping | A. Renshaw | Houston | [6 empty] | 20 | 0 | [5 empty] | 20 | [20 empty] | 0
1.2.6 ITO and TPB coating | M. Boulay | Carleton | [5 empty] | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6.1 Design and engineering | M. Boulay | Carleton | [7 empty] | 254 | [8 empty] | 254 | [17 empty] | 0
1.2.6.2 Parts and Materials | M. Boulay | Carleton | [7 empty] | 381 | [8 empty] | 381 | [17 empty] | 0
1.2.7 TPC mechanics fabrication | R. Santorelli | CIEMAT | [11 empty] | 25 | [15 empty] | 25 | [6 empty] | 0
1.2.8 TPC Vessel | S. De Cecco | Roma1 | [5 empty] | 877.12 | 1250 | 4500 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 1250 | 0 | 0 | 150 | 727.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
1.2.8.1 Test cryostat | S. De Cecco | Roma1 | [5 empty] | 150 | [16 empty] | 150 | [11 empty] | 0
1.2.8.2 TPC vessel | S. De Cecco | Roma1 | [5 empty] | 727.12 | [17 empty] | 727.12 | [10 empty] | 0
1.2.8.3 Cu-Ti alloys test, procurement & certification | A. Chepurnov | MSU | [11 empty] | 300 | [20 empty] | 300 |  | 0
1.2.8.4 Acrylic TPC vessel design and fabrication | A. Hallin | Alberta | [7 empty] | 4500 |  |  |  | 0 |  |  |  |  | 4500 | [15 empty] | 0 |  | 0
1.2.8.5 TPC development | M. Diwan | BNL | [6 empty] | 1250 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 1250 | [12 empty] | 0 |  | 0
1.2.9 Cryocooling system and gas handling | H. Wang | UCLA | [5 empty] | 0 | 1385.368 | 0 | 0 | 720 | 0 | 0 | 0 | 1385.368 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.1 Uar loop within TPC | P. Meyers | Princeton | [6 empty] | 15 | 0 | [5 empty] | 15 | [20 empty] | 0
1.2.9.2 Uar purification and cooling loop | H. Wang | UCLA | [5 empty] | 0 | 885.468 | 0 | 0 | 240 | 0 | 0 | 0 | 885.468 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.2.1 LN2 dewar | H. Wang | UCLA | [6 empty] | 15 | 0 | [5 empty] | 15 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.2 Ar condenser | H. Wang | UCLA | [6 empty] | 12.5 | 0 | [5 empty] | 12.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.3 GigaTorr SAES getters | H. Wang | UCLA | [6 empty] | 275 | 0 | [5 empty] | 275 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.4 Gas circulation pumps | H. Wang | UCLA | [6 empty] | 138.5 | 0 | [5 empty] | 138.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.5 Turbo pumps with controllers | H. Wang | UCLA | [6 empty] | 30 | 0 | [5 empty] | 30 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.6 Rough pumps | H. Wang | UCLA | [6 empty] | 10 | 0 | [5 empty] | 10 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.7 Radon trap activated carbon | H. Wang | UCLA | [6 empty] | 175 | 0 | [5 empty] | 175 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.8 Radon trap fabrication materials | H. Wang | UCLA | [6 empty] | 7 | 0 | [5 empty] | 7 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.9 Heat exchangers | H. Wang | UCLA | [6 empty] | 5.5 | 0 | [5 empty] | 5.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.10 Custom regulation valve | H. Wang | UCLA | [6 empty] | 2 | 0 | [5 empty] | 2 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.11 Cold box inner tubing and fittings | H. Wang | UCLA | [6 empty] | 7.5 | 0 | [5 empty] | 7.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.12 Cold box vacuum vessel | H. Wang | UCLA | [6 empty] | 30.888 | 0 | [5 empty] | 30.888 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.13 Cold box bayonet and transfer lines | H. Wang | UCLA | [6 empty] | 8.5 | 0 | [5 empty] | 8.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.14 Superinsulation | H. Wang | UCLA | [6 empty] | 2.5 | 0 | [5 empty] | 2.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.15 Safety rupture disks | H. Wang | UCLA | [6 empty] | 25 | 0 | [5 empty] | 25 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.16 Safety relief valves | H. Wang | UCLA | [6 empty] | 6 | 0 | [5 empty] | 6 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.17 Materials and shop time | H. Wang | UCLA | [6 empty] | 1 | 0 | [5 empty] | 1 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.18 Pressure transducers | H. Wang | UCLA | [6 empty] | 11.8 | 0 | [5 empty] | 11.8 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.19 Temperature sensor and monitor | H. Wang | UCLA | [6 empty] | 5 | 0 | [5 empty] | 5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.20 Temperature sensor and controller | H. Wang | UCLA | [6 empty] | 51.58 | 0 | [5 empty] | 51.58 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.21 Vacuum gauges | H. Wang | UCLA | [6 empty] | 1 | 0 | [5 empty] | 1 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.22 Vacuum valves | H. Wang | UCLA | [6 empty] | 5 | 0 | [5 empty] | 5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.23 Cooling tower frame | H. Wang | UCLA | [6 empty] | 10 | 0 | [5 empty] | 10 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.24 Engineering labor | P. Meyers | Princeton | [9 empty] | 240 | 0 |  |  | 0 | 240 | [5 empty] | 0 | [13 empty] | 0
1.2.9.2.25 Materials and supplies | H. Wang | UCLA | [6 empty] | 20.2 | 0 | [5 empty] | 20.2 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.26 Shipping | H. Wang | UCLA | [6 empty] | 29 | 0 | [5 empty] | 29 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3 Uar Recovery system cryogenics | P. Meyers | Princeton | [5 empty] | 0 | 249.2 | 0 | 0 | 240 | 0 | 0 | 0 | 249.2 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.3.1 LN2 dewar | P. Meyers | Princeton | [6 empty] | 15 | 0 | [5 empty] | 15 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.2 Ar condenser | P. Meyers | Princeton | [6 empty] | 22 | 0 | [5 empty] | 22 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.3 Turbo pumps with controllers | P. Meyers | Princeton | [6 empty] | 30 | 0 | [5 empty] | 30 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.4 Rough pumps | P. Meyers | Princeton | [6 empty] | 15 | 0 | [5 empty] | 15 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.5 Heat exchangers | P. Meyers | Princeton | [6 empty] | 5 | 0 | [5 empty] | 5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.6 Cold box inner tubing and fittings | P. Meyers | Princeton | [6 empty] | 7.5 | 0 | [5 empty] | 7.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.7 Cold box vacuum vessel | P. Meyers | Princeton | [6 empty] | 40 | 0 | [5 empty] | 40 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.8 Cold box bayonet and transfer lines | P. Meyers | Princeton | [6 empty] | 17 | 0 | [5 empty] | 17 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.9 Superinsulation | P. Meyers | Princeton | [6 empty] | 2.5 | 0 | [5 empty] | 2.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.10 Safety rupture disks | P. Meyers | Princeton | [6 empty] | 25 | 0 | [5 empty] | 25 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.11 Safety relief valves | P. Meyers | Princeton | [6 empty] | 6 | 0 | [5 empty] | 6 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.12 Custom regulating valve | P. Meyers | Princeton | [6 empty] | 4 | 0 | [5 empty] | 4 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.13 Temperature sensor and monitor | P. Meyers | Princeton | [6 empty] | 10.5 | 0 | [5 empty] | 10.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.14 Vacuum gauges | P. Meyers | Princeton | [6 empty] | 2 | 0 | [5 empty] | 2 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.15 Vacuum valves | P. Meyers | Princeton | [6 empty] | 5 | 0 | [5 empty] | 5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.3.16 Engineering labor | P. Meyers | Princeton | [7 empty] | 0 |  | 240 | 0 |  |  | 0 | 240 | [5 empty] | 0 | [13 empty] | 0
1.2.9.3.17 Materials and supplies | P. Meyers | Princeton | [6 empty] | 15 | 0 | [5 empty] | 15 | [6 empty] | 0 | [13 empty] | 0
1.2.9.2.18 Shipping | P. Meyers | Princeton | [6 empty] | 27.7 | 0 | [5 empty] | 27.7 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4 Uar loop warm parts and instrumentation loop | P. Meyers | Princeton | [5 empty] | 0 | 153.2 | 0 | 0 | 240 | 0 | 0 | 0 | 153.2 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.9.4.1 Room temperature valves | P. Meyers | Princeton | [6 empty] | 63 | 0 | [5 empty] | 63 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.2 Mass flow meters for Uar | P. Meyers | Princeton | [6 empty] | 6.5 | 0 | [5 empty] | 6.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.3 Mass flow meters for N2 | P. Meyers | Princeton | [6 empty] | 1.4 | 0 | [5 empty] | 1.4 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.4 Mass flow controller for calibration source | P. Meyers | Princeton | [6 empty] | 2 | 0 | [5 empty] | 2 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.5 Molecular drag pump systems | P. Meyers | Princeton | [6 empty] | 40 | 0 | [5 empty] | 40 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.6 Safety relief valves | P. Meyers | Princeton | [6 empty] | 6 | 0 | [5 empty] | 6 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.7 Tubing and fittings | P. Meyers | Princeton | [6 empty] | 5 | 0 | [5 empty] | 5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.8 Engineering labor | P. Meyers | Princeton | [7 empty] | 0 |  | 240 | 0 |  |  | 0 | 240 | [5 empty] | 0 | [13 empty] | 0
1.2.9.4.9 Materials and supplies | P. Meyers | Princeton | [6 empty] | 7.5 | 0 | [5 empty] | 7.5 | [6 empty] | 0 | [13 empty] | 0
1.2.9.4.10 Shipping | P. Meyers | Princeton | [6 empty] | 21.8 | 0 | [5 empty] | 21.8 | [6 empty] | 0 | [13 empty] | 0
1.2.9.5 Cryo-system Slow Control | P. Meyers | Princeton | [6 empty] | 82.5 | 0 | [5 empty] | 82.5 | [20 empty] | 0
1.2.10 TPC integration | Y. Suvorov | Napoli | [5 empty] | 200 | [14 empty] | 200 | [13 empty] | 0
1.3 Materials | R. Santorelli | CIEMAT | [5 empty] | 1113 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 500 | 0 | 0 | 0
1.3.1 Background budget | V. Pesudo | CIEMAT | [34 empty] | 0
1.3.1.1 Bulk | V. Pesudo | CIEMAT | [13 empty] | 0 | [20 empty] | 0
1.3.1.2 Emanation | V. Pesudo | CIEMAT | [34 empty] | 0
1.3.1.3 Surface | V. Pesudo | CIEMAT | [27 empty] | 0 | [6 empty] | 0
1.3.1.4 Cosmogenic & Intrinsic Activity | V. Pesudo | CIEMAT | [13 empty] | 0 | [20 empty] | 0
1.3.2 Inter-comparison and QC | G. Zuzel | Krakow | [34 empty] | 0
1.3.2.1 Surface / Rn emanation | [36 empty] | 0
1.3.2.2 HPGe | [36 empty] | 0
1.3.2.3 ICP-MS | [36 empty] | 0
1.3.3 Materials, handling and process development | R. Santorelli | CIEMAT | [34 empty] | 0
1.3.3.1 Mat. Handling procedures | [36 empty] | 0
1.3.3.2 Cleanliness Methods | [36 empty] | 0
1.3.3.3 Tracking and monitoring | [36 empty] | 0
1.3.4 Spreadsheets and database
1.3.4.1 Spreadsheet, assay request form, standard result form | [36 empty] | 0
1.3.4.2 Database and web interface | [36 empty] | 0
1.3.5 Cosmogenic & Intrinsic activity
1.3.5.1 Argon | [36 empty] | 0
1.3.5.2 TPC | [36 empty] | 0
1.3.5.3 PE | [36 empty] | 0
1.3.6 Materials radiopurity assay | G. Giovanetti | Princeton | [5 empty] | 1113 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 500 |  | 0 | 0
1.3.6.1 HPGe Gamma Counting | [9 empty] | 0 | [5 empty] | 0 | [20 empty] | 0
1.3.6.1.1 BHSU assays | [8 empty] | 90 | [6 empty] | 90 | [20 empty] | 0
1.3.6.1.2 LNGS assays | [36 empty] | 0
1.3.6.1.3 LSC assays | [7 empty] | 613 | [21 empty] | 613 | [6 empty] | 0
1.3.6.1.4 Temple assays | [8 empty] | 60 | [6 empty] | 60 | [20 empty] | 0
1.3.6.1.5 PNNL assays | [36 empty] | 0
1.3.6.2 Radiochem. And Mass Spec. | [36 empty] | 0
1.3.6.2.1 BHSU assays | [36 empty] | 0
1.3.6.2.2 CIEMAT assays | [36 empty] | 0
1.3.6.2.3 LNGS assays | [36 empty] | 0
1.3.6.2.4 PNNL assays | [8 empty] | 50 | [11 empty] | 50 | 0 | [14 empty] | 0
1.3.6.3 Radon emanation | [29 empty] | 0 | [6 empty] | 0
1.3.6.3.1 Crakow assays | [7 empty] | 500 | [25 empty] | 500 |  |  | 0
1.3.6.3.2 PNNL assays | [36 empty] | 0
1.3.6.4 Large area surface assay | [9 empty] | 0 | [5 empty] | 0 | [20 empty] | 0
1.3.6.4.1 LSC assays | [36 empty] | 0
1.3.6.4.2 Crakow assays | [36 empty] | 0
1.4 Calibrations | J. Maricic | Hawaii | [5 empty] | 195 | 460 | 0 | 115 | 412 | 0 | 0 | 0 | 460 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 300 | 0 | 0
1.4.1 Sources | J. Maricic | Hawaii | [5 empty] | 195 | 80 | 0 | 115 | 11 | 0 | 0 | 0 | 80 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 300 | 0 | 0
1.4.1.1 Gas Sources | P. Meyers | Princeton | [5 empty] | 5 | 10 | 0 | 5 | 1 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
1.4.1.1.1 83Kr transport | P. Meyers | Princeton | [6 empty] | 3 | 0 | [5 empty] | 3 | 0 | [19 empty] | 0
1.4.1.1.2 83Kr lab supplies | P. Meyers | Princeton | [6 empty] | 4 | 0 | [5 empty] | 4 | 0 | [16 empty] | 0 |  |  | 0
1.4.1.1.3 83Kr Shipping | P. Meyers | Princeton | [6 empty] | 3 | 0 | [5 empty] | 3 | 0 | [19 empty] | 0
1.4.1.1.4 83Kr - Source | P. Meyers | Princeton | [9 empty] | 1 | 0 |  |  |  | 1 | [16 empty] | 0 |  |  | 0
1.4.1.1.5 222Rn source fabrication | G. Zuzel | Krakow | [5 empty] | 5 | [8 empty] | 0 | [16 empty] | 5 |  |  | 0
1.4.1.1.6 222Rn labor | G. Zuzel | Krakow | [5 empty] | 0 |  |  | 5 | [5 empty] | 0 | [16 empty] | 5 |  |  | 0
1.4.1.2 γ-ray Sources | B. Vogelaar | Virginia Tech | [6 empty] | 30 | 0 |  | 5 | 0 |  |  | 30 | 5 | [19 empty] | 0
1.4.1.3 AmC, AmBe, AmLi | J. Martoff / J. Maricic | Temple / Hawaii | [6 empty] | 40 | 0 |  | 5 | 0 |  |  | 40 | 5 | [19 empty] | 0
1.4.1.4 252Cf | M. Gromow | BNRU / MSU | [5 empty] | 20 |  |  | 10 | [23 empty] | 30 |  | 0
1.4.1.5 UV led for veto calibration | M. Gromow | BNRU / MSU | [5 empty] | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0
1.4.1.5.1 UV fibers system | M. Gromow | BNRU / MSU | [5 empty] | 5 | [26 empty] | 5 |  | 0
1.4.1.5.2 Connector | M. Gromow | BNRU / MSU | [5 empty] | 5 | [26 empty] | 5 |  | 0
1.4.1.5.3 Design | M. Gromow | BNRU / MSU | [5 empty] | 5 | [26 empty] | 5 |  | 0
1.4.1.5.4 Construction | M. Gromow | BNRU / MSU | [5 empty] | 5 | [26 empty] | 5 |  | 0
1.4.1.6 Pyroelectric neutron generator | A. Chepurnov | BNRU / MSU | [5 empty] | 150 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0
1.4.1.6.1 Parts | A. Chepurnov | BNRU / MSU | [5 empty] | 150 | [26 empty] | 150 |  | 0
1.4.1.6.2 Fabrication and commissioning | A. Chepurnov | BNRU / MSU | [6 empty] | 0 | 0 | 100 | [23 empty] | 100 |  | 0
1.4.2 TPC guide mechanics | J. Maricic | Hawaii | [5 empty] | 0 | 40 | 0 | 0 | 5 | 0 | 0 | 0 | 40 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.3 Source insertion device (enclosed) | J. Maricic | Hawaii/Virginia | [5 empty] | 0 | 100 | 0 | 0 | 48 | 0 | 0 | 0 | 100 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.3.1 Sealed external housing | J. Maricic | Hawaii | [6 empty] | 30 | 0 |  | 5 | 0 |  |  | 30 | 5 | [19 empty] | 0
1.4.3.2 Automatic, precision stepper motor delivery system | J. Maricic | Hawaii | [6 empty] | 50 | 0 |  | 10 | 0 |  |  | 50 | 10 | [19 empty] | 0
1.4.3.3 Source exchangers (intelocking) | J. Maricic | Hawaii | [6 empty] | 20 | 0 |  | 5 | 0 |  |  | 20 | 5 | [19 empty] | 0
1.4.3.4 Engineering | J. Maricic | Hawaii/Virginia | [9 empty] | 28 | 0 |  |  |  | 28 | [19 empty] | 0
1.4.3.5 Installation and commissioning | J. Maricic | Hawaii/Virginia | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.4 External deployment system,Photoneutron source and camera system | J. Martoff | Temple | [5 empty] | 0 | 240 | 0 | 0 | 348 | 0 | 0 | 0 | 240 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.4.1 Photoneutron source production | J. Martoff / J. Maricic | Temple / Hawaii | [6 empty] | 120 | 0 |  | 30 | 0 |  |  | 120 | 30 | [19 empty] | 0
1.4.4.2 Engineering | J. Martoff / J. Maricic | Temple / Hawaii | [5 empty] | 0 | 0 | 0 |  | 308 | 0 | 0 | 0 | 0 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.4.3 Construction | J. Maricic | Hawaii | [6 empty] | 80 | 0 | [5 empty] | 80 | [20 empty] | 0
1.4.4.4 Camera system | B. Vogelaar | Virginia Tech | [5 empty] | 0 | 40 | 0 | 0 | 10 | 0 | 0 | 0 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.4.4.1 Camera and parts | B. Vogelaar | Virginia Tech | [6 empty] | 40 | 0 | [5 empty] | 40 | 0 | [19 empty] | 0
1.4.4.4.2 Engineering | B. Vogelaar | Virginia Tech | [9 empty] | 10 | 0 |  |  |  | 10 | [19 empty] | 0
1.5 Outer detector | G. Testera | Genova | [5 empty] | 1843 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938 | 0 | 0 | 0 | 0 | 0
1.5.1 LAr Veto development | G. Testera | Genova | [5 empty] | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.1 Radiopurity tests of mechanics samples | G. Testera | Genova | [5 empty] | 5 | [14 empty] | 5 | [13 empty] | 0
1.5.1.2 Radiopurity tests of electronics samples | G. Testera | Genova | [5 empty] | 5 | [14 empty] | 5 | [13 empty] | 0
1.5.1.3 Design and test of Veto Motherboard | P. Musico | Genova | [5 empty] | 30 | [14 empty] | 30 | [13 empty] | 0
1.5.1.4 Seismic studies | TBD | Genova | [5 empty] | 0 | [14 empty] | 0 | [13 empty] | 0
1.5.2 Prototype of LAr Veto module and test | G. Testera | Genova | [5 empty] | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.2.1 Smal scale Veto module | A. Caminata | Genova | [5 empty] | 25 | [14 empty] | 25 | [13 empty] | 0
1.5.2.2 TPB coating of surface | M. Boulay | Carleton | [5 empty] | 0 | [14 empty] | 0 | [13 empty] | 0
1.5.2.3 Veto design studies | A. Caminata | Genova | [5 empty] | 0 | [14 empty] | 0 | [13 empty] | 0
1.5.3 Veto procurement, construction and commissioning | TBD | Genova | [5 empty] | 1278 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938 | 0 | 0 | 0 | 0 | 0
1.5.3.1 Cabling and connectors | TBD | TBD | [5 empty] | 0 | 0 | [9 empty] | 0 | [17 empty] | 0
1.5.3.2 Tests of PDM for veto | S. Davini | Genova | [5 empty] | 0 | 0 | 0 | [8 empty] | 0 | [17 empty] | 0
1.5.3.3 TPB coating for Veto | M. Boulay | Carleton | [5 empty] | 0 | [20 empty] | 0 | [7 empty] | 0
1.5.3.4 Motherboards for Veto | P. Musico | Genova | [5 empty] | 90 | 0 | 0 | [8 empty] | 0 |  |  |  | 90 | [13 empty] | 0
1.5.3.5 Support structure engineering including sectorization, reflectors, PDM holding support | L. Di Noto | Genova | [5 empty] | 250 | 0 | [9 empty] | 0 |  |  |  | 250 | [13 empty] | 0
1.5.3.6 Acrylic for Veto | Changeen | IHEP | [5 empty] | 938 | 0 | 0 | [8 empty] | 0 | [12 empty] | 938 |  |  |  |  | 0
1.5.3.7 Gd loading of acrylic | Changeen | IHEP | [5 empty] | 0 | [20 empty] | 0 |  | 0 | [5 empty] | 0
1.5.3.8 Workshop machining of Veto acrylic | A. Hallin | Alberta / CIEMAT | [5 empty] | 0 | 0 | 500 | [8 empty] | 500 |  |  |  | 0 | [13 empty] | 0
1.5.5 Installation | A. Caminata | Genova | [5 empty] | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.5.1 Installation of Veto and commissioning | A. Caminata | Genova | [5 empty] | 150 | [10 empty] | 0 |  |  |  | 150 | [13 empty] | 0
1.5.5.2 Veto optical calibration system | A. Caminata | Genova | [5 empty] | 350 | [14 empty] | 350 | [13 empty] | 0
1.6 Electronics (DAQ, trigger and slow control) | M. Rescigno | Roma1 | [5 empty] | 500.5472 | 50 | 3608.6895 | 100 | 0 | 1000 | 0 | 0 | 50 | 0 | 0 | 3608.6895 | 1000 | 0 | 0 | 500.5472 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1 Readout | M. Rescigno | Roma1 | [5 empty] | 320.5472 | 0 | 3043.2695 | 100 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 3043.2695 | 1000 | 0 | 0 | 320.5472 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1.1 Readout boards | M. Rescigno | Roma1 | [5 empty] | 270.5472 | 0 | 2225.1863 | 100 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 2225.1863 | 1000 | 0 | 0 | 270.5472 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1.1.1 Readout boards for DS-Proto (370 ch, 64 ch/board, +IT VAT) | M. Rescigno | Roma1 | 6 | 1 | 64 | boards | 12.8832 | 90.1824 | [14 empty] | 90.1824 | [13 empty] | 0
1.6.1.1.2 Readout boards for TPC 1st contingent (896 ch, 64 ch/board, +IT VAT) | M. Rescigno | Roma1 | 14 | 0 | 64 | boards | 12.8832 | 180.3648 | [14 empty] | 180.3648 | [13 empty] | 0
1.6.1.1.3 Readout boards for TPC 2nd contingent (rest of needed boards) | F. Retiere | TRIUMF | 130 | 4% | 64 | boards | 12.8832 |  |  | 2225.1863 | [8 empty] | 2225.1863 | [17 empty] | 0
1.6.1.1.4 Readout software and control development (software) | F. Retiere | TRIUMF | [7 empty] | 0 |  | 0 | 500 | [6 empty] | 500 | [16 empty] | 0
1.6.1.1.5 Readout firmware development | F. Retiere | TRIUMF | [9 empty] | 0 | 500 | [6 empty] | 500 | [6 empty] | 0 | [9 empty] | 0
1.6.1.1.6 Readout software and firmware development (design) | M. Rescigno | Roma1 | [8 empty] | 100 | [16 empty] | 100 | [8 empty] | 0
1.6.1.2 Readout boards for veto | F. Retiere | TRIUMF | 47 | 5% | 64 | boards | 12.8832 |  | 0 | 818.0832 | [8 empty] | 818.0832 | [17 empty] | 0
1.6.1.3 Prototype boards | M. Rescigno | Roma1 | [5 empty] | 50 | [14 empty] | 50 | [13 empty] | 0
1.6.2 Trigger | A. Messina | Roma1 | [5 empty] | 180 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.2.1 Clock distribution and trigger logic | M. Rescigno | Roma1 | [6 empty] | 0 | 125 | [8 empty] | 125 | [17 empty] | 0
1.6.2.2 Event builder and software trigger | A. Messina | Roma1 | [5 empty] | 160 | [14 empty] | 160 | [13 empty] | 0
1.6.2.3 Cluster for smart trigger/data reduction | A. Razeto | LNGS | [5 empty] | 20 | [14 empty] | 20 | [13 empty] | 0
1.6.3 Slow controls | P. Cavalcante | VTech | [6 empty] | 50 | 0 | [5 empty] | 50 | [20 empty] | 0
1.6.4 Infrastructure and power supply | A. Candela | LNGS | [5 empty] | 0 | 0 | 440.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.4.1 Electronics Infrastructure, cabling, cooling | A. Candela | LNGS | [5 empty] | 0 | 0 | 440.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.4.1.1 High-end racks and crates with accessories (for TPC+Veto) | A. Candela | LNGS | 11 |  |  | crates |  |  |  | 312.42 | [8 empty] | 312.42 | [17 empty] | 0
1.6.4.1.2 Cooling equipment | A. Candela | LNGS | [6 empty] | 0 | 64 | [8 empty] | 64 | [17 empty] | 0
1.6.4.1.3 Cabling | A. Candela | LNGS | [6 empty] | 0 | 64 | [8 empty] | 64 | [17 empty] | 0
1.7 Offline | D. Franco | APC/Roma1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0
1.7.1 Computing | S. Giagu | Roma1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7.1.1 HW CPU and Storage | S. Giagu | Roma1 | [11 empty] | 800 | [12 empty] | 800 | [9 empty] | 0
1.7.2 Reconstruction software | N. Rossi | Roma1 | [34 empty] | 0
1.7.3 Science simulations | P. Agnes | APC | [34 empty] | 0
1.7.4 G4DS Monte Carlo | C. Giganti | APC | [11 empty] | 100 | [18 empty] | 100 |  |  |  | 0
1.8 ReD | L. Pandola | LNS | [5 empty] | 396 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.1 Simulation & Analysis | L. Pandola | LNS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.1.1 RED-TPC design and optimization | Y.Wang | UCLA | [34 empty] | 0
1.8.1.2 Neutron experiment simulation | M. Kuss | Pisa | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.1.2.1 Collimator design and optimization | [36 empty] | 0
1.8.1.2.2 nToF design and optimization | [36 empty] | 0
1.8.1.3 LAr response analysis and modelling | N. Rossi | Roma1 | [34 empty] | 0
1.8.2 ReD Photoelectronics | E. Scapparone | Bologna | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.2.1 SiPM prototyping + tests | A. Gola | TIFPA | [34 empty] | 0
1.8.2.2 Front-end electronics integration | A. Razeto | LNGS | [34 empty] | 0
1.8.2.3 Detector module design and production | M. La Commara | Napoli | [34 empty] | 0
1.8.2.4 Functional test and certification | M. La Commara | Napoli | [34 empty] | 0
1.8.3 RED-TPC | G. Fiorillo | Napoli | [5 empty] | 221 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.3.1 TPC & cryogenics | Y. Suvorov | Napoli | [5 empty] | 169 | [14 empty] | 169 | [13 empty] | 0
1.8.3.2 DAQ | G. Fiorillo | Napoli | [5 empty] | 23 | [14 empty] | 23 | [13 empty] | 0
1.8.3.3 Slow control | A. Caminata | Genova | [5 empty] | 14 | [14 empty] | 14 | [13 empty] | 0
1.8.3.4 Laser calibration system | M. Gulino | LNS | [5 empty] | 15 | [14 empty] | 15 | [13 empty] | 0
1.8.3.5 Offsite calibration | M. Diwan | BNL | [5 empty] | 0 | 500 | [12 empty] | 500 | 0 | [13 empty] | 0
1.8.4 Neutron beam and Si detectors | M. Gulino | LNS | [5 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.5 nToF Spectrometer | M. Rescigno | Roma1 | [5 empty] | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.5.1 Detector & DAQ | M. Rescigno | Roma1 | [5 empty] | 5 | [14 empty] | 5 | [13 empty] | 0
1.8.5.2 Mechanics | C. Cicalò | Cagliari | [5 empty] | 30 | [14 empty] | 30 | [13 empty] | 0
1.8.6 Commissioning & operation | G. Fiorillo | Napoli | [5 empty] | 80 | [14 empty] | 80 | [13 empty] | 0
1.9 DarkSide-Proto | G. Fiorillo/L. Mapelli | Napoli/Princeton | [5 empty] | 814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9.1 Integration | G. Fiorillo | Napoli | [5 empty] | 61 | [14 empty] | 61 | [13 empty] | 0
1.9.2 DAQ | M. Rescigno | Roma1 | [5 empty] | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9.2.1 DAQ and trigger | M. Rescigno | Roma1 | [5 empty] | 65 | [14 empty] | 65 | [13 empty] | 0
1.9.2.2 DAQ server and data management | M. Rescigno | Roma1 | [5 empty] | 15 | [14 empty] | 15 | [13 empty] | 0
1.9.2.2 Data storage | M. Rescigno | Roma1 | [5 empty] | 20 | [14 empty] | 20 | [13 empty] | 0
1.9.2.3 Slow control | M. Rescigno | Roma1 | [5 empty] | 20 | [14 empty] | 20 | [13 empty] | 0
1.9.3 Calibration Set-up | G. Fiorillo | Napoli | [5 empty] | 55 | [14 empty] | 55 | [13 empty] | 0
1.9.4 Commissioning | G. Fiorillo | Napoli | [5 empty] | 50 | [14 empty] | 50 | [13 empty] | 0
1.9.5 Operation | G. Fiorillo | Napoli | [5 empty] | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9.5.1 Consumables | G. Fiorillo | Napoli | [5 empty] | 50 | [14 empty] | 50 | [13 empty] | 0
1.9.5.2 Project associate at CERN | G. Fiorillo | Napoli | [5 empty] | 182 | [14 empty] | 182 | [13 empty] | 0
1.9.5.3 Travel | G. Fiorillo | Napoli | [5 empty] | 230 | [14 empty] | 230 | [13 empty] | 0
1.9.6 Cryostat | S. De Cecco | Roma1 | [5 empty] | 66 | [14 empty] | 66 | [13 empty] | 0
1.10 Outer cryostat | M. Nessi | LNGS | [5 empty] | 8892.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8192.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0
1.10.1 Warm structure | M. Nessi | LNGS | [5 empty] | 2089.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2089.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.10.1.1 Raw steel beams | M. Nessi | LNGS | [5 empty] | 193.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.10.1.2 Steel plates | M. Nessi | LNGS | [5 empty] | 56.12 | [17 empty] | 56.12 | [10 empty] | 0
1.10.1.3 SS plates | M. Nessi | LNGS | [5 empty] | 146.4 | [17 empty] | 146.4 | [10 empty] | 0
1.10.1.4 Custom pieces | M. Nessi | LNGS | [5 empty] | 137.86 | [17 empty] | 137.86 | [10 empty] | 0
1.10.1.5 Tools and consumables | M. Nessi | LNGS | [5 empty] | 417 | [17 empty] | 417 | [10 empty] | 0
1.10.1.6 Assembly & Installation | M. Nessi | LNGS | [5 empty] | 1138.26 | [17 empty] | 1138.26 | [10 empty] | 0
1.10.2 Cold Cryostat | M. Nessi | LNGS | [5 empty] | 3781.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.10.2.1 Design, list of material, assembly procedure, QA procedure | M. Nessi | LNGS | [5 empty] | 1024 | [17 empty] | 1024 | [10 empty] | 0
1.10.2.2 Insulation & membrane | M. Nessi | LNGS | [5 empty] | 1134.6 | [17 empty] | 1134.6 | [10 empty] | 0
1.10.2.3 Special material and consumables | M. Nessi | LNGS | [5 empty] | 473.36 | [17 empty] | 473.36 | [10 empty] | 0
1.10.2.4 Installation and final test | M. Nessi | LNGS | [5 empty] | 1150 | [17 empty] | 1150 | [10 empty] | 0
1.10.3 Cryogenics System | H. Wang | UCLA | [5 empty] | 2320.44 | [17 empty] | 2320.44 | [10 empty] | 0
1.10.4 Argon 5.0 | F. Gabriele | LNGS | [5 empty] | 700 | [27 empty] | 700 | 0
1.11 Technical coordination | An. Ianni | Princeton | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.11.1 Technical integration | T. Napolitano | LNF | [20 empty] | 0 | [13 empty] | 0
2 Urania | M. Simeone/A. Renshaw | Napoli/Houston | [5 empty] | 8049 | 8558 | 3864 | 0 | 754 | 560 | 0 | 400 | 4558 | 394 | 0 | 3864 | 560 | 760 | 4000 | 0 | 8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 Plant | M. Simeone | Napoli | [5 empty] | 8049 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 R&D activity in support of PSA design | M. Simeone | Napoli | [5 empty] | 100 | [15 empty] | 100 | [12 empty] | 0
2.1.2 Plant Design | M. Simeone | Napoli | [5 empty] | 500 | [15 empty] | 500 | [12 empty] | 0
2.1.3 Plant Construction | M. Simeone | Napoli | [5 empty] | 7449 | [15 empty] | 7449 | [12 empty] | 0
2.1.4 Plant performance check | M. Simeone | Napoli | [34 empty] | 0
2.1.5 Feed characterization | H. Back | PNNL | [12 empty] | 400 | [5 empty] | 400 | 0 | [14 empty] | 0
2.1.6 Plant shipment | M. Boulay | Carleton | [34 empty] | 0
2.2 Site Prep. & installation | A. Renshaw | Houston | [5 empty] | 0 | 3318 | 1003 | 0 | 466 | 377 | 0 | 0 | 3318 | 250 | 0 | 1003 | 377 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 Project management | A. Renshaw | Houston | [5 empty] | 0 | 0 | 0 | 0 | 216 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1.1 Plant operator (operations engineer) [FY19] | H. Back | PNNL | [9 empty] | 144 | 0 | [7 empty] | 144 | 0 | [14 empty] | 0
2.2.1.2 Plant operator (process engineer) [FY19] | M. Boulay | Carleton | [9 empty] | 0 | 183 | [6 empty] | 183 | [16 empty] | 0
2.2.1.3 Plant operator (operations engineer) [FY20] | H. Back | PNNL | [9 empty] | 72 | 0 | [7 empty] | 72 | 0 | [14 empty] | 0
2.2.1.4 Plant operator (process engineer) [FY20] | M. Boulay | Carleton | [9 empty] | 0 | 91 | [6 empty] | 91 | [16 empty] | 0
2.2.2 Preliminary site work | A. Renshaw | Houston | [6 empty] | 1000 | 0 | [5 empty] | 1000 | [20 empty] | 0
2.2.3 Plant and site integration | A. Pocar | UMass | [5 empty] | 0 | 1344 | 154 | 0 | 140 | 0 | 0 | 0 | 1344 | 140 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.3.1 Plant installation [FY19] | C. Galbiati/A. Ianni | Princeton | [6 empty] | 1344 | 0 |  | 30 | 0 |  |  | 1344 | 30 | [19 empty] | 0
2.2.3.2 Coupling between KM and URANIA [FY20] | M. Boulay | Carleton | [6 empty] | 0 | 154 | [8 empty] | 154 | [17 empty] | 0
2.2.3.3 Engineering labor for installation and commissioning | J. Napolitano | Temple | [9 empty] | 110 | 0 |  |  |  | 110 | [19 empty] | 0
2.2.4 Full system start-up and commissioning [FY20] | J. Napolitano | Temple | [5 empty] | 0 | 874 | 620 | 0 | 110 | 0 | 0 | 0 | 874 | 110 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.4.1 Installation and start-up project management | A. Renshaw | Houston | [6 empty] | 386 | 0 | [5 empty] | 386 | [20 empty] | 0
2.2.4.2 Plant consumables for start-up [FY20] | A. Renshaw | Houston | [6 empty] | 488 | 620 | [5 empty] | 488 |  |  | 620 | [17 empty] | 0
2.2.4.3 Engineering labor for installation and commissioning | J. Napolitano | Temple | [9 empty] | 110 | 0 |  |  |  | 110 | [19 empty] | 0
2.2.5 QA/QC instrumentation installation | M. Boulay | Carleton | [5 empty] | 0 | 0 | 229 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 229 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.5.1 Gas analysis instrumentation [FY18] | M. Boulay | Carleton | [6 empty] | 0 | 229 | [8 empty] | 229 | [17 empty] | 0
2.2.5.2 Installation of gas analysis instrumentation [FY20] | M. Boulay | Carleton | [9 empty] | 0 | 103 | [6 empty] | 103 | [16 empty] | 0
2.2.6 Feed optimization [FY18] | A. Renshaw | Houston | [6 empty] | 100 | 0 | [5 empty] | 100 | [20 empty] | 0
2.3 Extraction | H. Back | PNNL | [5 empty] | 0 | 5240 | 2861 | 0 | 288 | 183 | 0 | 0 | 1240 | 144 | 0 | 2861 | 183 | 144 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1 Project Management | H. Back | PNNL | [5 empty] | 0 | 0 | 0 | 0 | 288 | 183 | 0 | 0 | 0 | 144 | 0 | 0 | 183 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.1.1 Plant operator (operations engineer) [FY20, FY21] | H. Back | PNNL | [9 empty] | 144 | 0 | [7 empty] | 144 | 0 | [14 empty] | 0
2.3.1.2 Plant operator (process engineer) [FY20, FY21] | M. Boulay | Carleton | [9 empty] | 0 | 183 | [6 empty] | 183 | [16 empty] | 0
2.3.1.3 Plant operator (technical engineer) [FY20, FY21] | R. Haaland | Fort Lewis | [9 empty] | 144 | 0 |  |  |  | 144 | [19 empty] | 0
2.3.2 Plant Operations | H. Back | PNNL | [5 empty] | 0 | 5240 | 1337 | 0 | 0 | 0 | 0 | 0 | 1240 | 0 | 0 | 1337 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.2.1 Plant Maintenance [FY21, FY22] | A. Renshaw | Houston | [6 empty] | 265 | 0 | [5 empty] | 265 | [20 empty] | 0
2.3.2.2 Precision gas analysis [FY19, FY20, FY21, FY22] | M. Boulay | Carleton | [6 empty] | 0 | 99 | [8 empty] | 99 | [17 empty] | 0
2.3.2.3 Energy (Electricity and LN2) [FY20, FY21] | A. Ianni/M. Boulay | Princeton/Canada | [6 empty] | 975 | 1238 | [5 empty] | 975 |  |  | 1238 | [17 empty] | 0
2.3.2.4 Argon extraction operations [FY19, FY23] | M. Diwan | BNL | [6 empty] | 4000 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 4000 | [14 empty] | 0
2.3.3 Storage and Shipping | M. Boulay | Carleton | [5 empty] | 0 | 0 | 1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3.3.1 Storage and Shipping Vessels [FY18, FY19, FY20] | M. Boulay | Carleton | [6 empty] | 0 | 1270 | [8 empty] | 1270 | [17 empty] | 0
2.3.3.2 Ship Product [FY20, FY21] | M. Boulay | Carleton | [6 empty] | 0 | 254 | [8 empty] | 254 | [17 empty] | 0
2.3.4 Shutdown | A. Renshaw | Houston | [34 empty] | 0
3 Aria | L. Mapelli/R. Tartaglia/ A. Devoto | Princeton/LNGS/Cagliari | [5 empty] | 7599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 140 | 10 | 0 | 0 | 0 | 0 | 0 | 0
3.1 Seruci-I | F. Gabriele | LNGS | [5 empty] | 7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 Construction | F. Gabriele | LNGS | [5 empty] | 5765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.1 Column construction | M. Razeti | LNGS | [5 empty] | 5632 | [15 empty] | 5632 | [12 empty] | 0
3.1.1.2 Leak test at Polaris (travel) | M. Razeti | Cagliari | [5 empty] | 32 | [15 empty] | 32 | [12 empty] | 0
3.1.1.3 Leak test at CERN (travel) | Y. Suvorov | Napoli | [5 empty] | 101 | [15 empty] | 101 | [12 empty] | 0
3.1.2 Auxiliary Plants and test in Seruci-0 | F. Gabriele | LNGS | [5 empty] | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2.1 Nitrogen Recovery | P Cavalcante | Virginia Tech | [34 empty] | 0
3.1.2.2 Vacuum System | C. Kendziora/M. Razeti/Y. Suvorov | Fermilab/Cagliari/Napoli | [34 empty] | 0
3.1.2.3 Nitrogen Circuit System | P. Cavalcante | Virginia Tech | [5 empty] | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.2.3.1 Backup K102 compressor | F. Gabriele | LNGS | [34 empty] | 0
3.1.2.3.2 Nitrogen storage | M. Razeti/R. Tartaglia | Cagliari/LNGS | [5 empty] | 37 | [15 empty] | 37 | [12 empty] | 0
3.1.2.4 Product storage system | F. Gabriele | LNGS | [34 empty] | 0
3.1.3 Installation | F. Gabriele | LNGS | [5 empty] | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.3.1 Residual gas analyzer | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 122 | [15 empty] | 122 | [12 empty] | 0
3.1.3.2 Cryogenic transfer lines | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 211 | [15 empty] | 211 | [12 empty] | 0
3.1.3.3 Travel | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 128 | [15 empty] | 128 | [12 empty] | 0
3.1.3.4 Piller | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 549 | [15 empty] | 549 | [12 empty] | 0
3.1.3.5 Cables and Installation | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 61 | [15 empty] | 61 | [12 empty] | 0
3.1.4 Commissioning | F. Gabriele/M. Razeti/R. Tartaglia | LNGS/Cagliari/LNGS | [5 empty] | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.4.1 Commissioning & running of Seruci I | TBD | Cagliari | [5 empty] | 305 | [15 empty] | 305 | [12 empty] | 0
3.1.4.2 Energy and maintenance | TBD | Cagliari | [21 empty] | 0 | [12 empty] | 0
3.2 DArT | W. Bonivento | Cagliari | [5 empty] | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 140 | 10 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 DarT @ ArDM | W. Bonivento/P. Garcia | Cagliari/CIEMAT | [5 empty] | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 140 | 10 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1.1 Prototype design and construction | W. Bonivento | Cagliari | [5 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1.1.1 Materials (OFHC Copper, acrylic, reflectors) | M. Razeti | Cagliari | [5 empty] | 10 | [15 empty] | 10 | [12 empty] | 0
3.2.1.1.2 Readout electronics | A. Razeto | LNGS | [5 empty] | 5 | [15 empty] | 5 | [12 empty] | 0
3.2.1.1.3 Machining | R. Santorelli | CIEMAT | [5 empty] | 15 | [21 empty] | 15 | [6 empty] | 0
3.2.1.1.4 Material assay | R. Santorelli | CIEMAT | [5 empty] | 15 | [21 empty] | 15 | [6 empty] | 0
3.2.1.1.5 Tests and shipment | R. Santorelli | CIEMAT | [5 empty] | 15 | [21 empty] | 15 | [6 empty] | 0
3.2.1.2 1L test detector assembly | W. Bonivento/A. Razeto | Cagliari/LNGS | [5 empty] | 5 | [15 empty] | 5 | [12 empty] | 0
3.2.1.3 Tests at CERN in a clone ArDM cryostat (6 weeks, 2 people) | C. Regenfus | ETHZ | [5 empty] | 20 | [15 empty] | 10 | [5 empty] | 10 | [6 empty] | 0
3.2.1.4 Installations at LSC | C. Regenfus | ETHZ | [5 empty] | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1.4.1 Gas storage/cryogenics (HOKE cyl./LN2 dewar/safety/N2 extraction) | C. Regenfus | ETHZ | [5 empty] | 25 | [21 empty] | 25 | [6 empty] | 0
3.2.1.4.2 Mechanical infrastructure | [7 empty] | 15 | [15 empty] | 5 | [5 empty] | 10 | [6 empty] | 0
3.2.1.4.3 SC system & electronics | C. Regenfus | ETHZ | [5 empty] | 10 | [22 empty] | 10 | [5 empty] | 0
3.2.1.4.4 Installation/commissioning at LSC (4 weeks, 4 people) | [7 empty] | 40 | [15 empty] | 5 | [5 empty] | 35 | [6 empty] | 0
3.2.1.5 Run @ LSC and data taking for 1L test (4 weeks, 2 people) | [7 empty] | 20 | [15 empty] | 5 | [5 empty] | 15 | [6 empty] | 0
3.2.2 DArT in Seruci | [7 empty] | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.1 Detector system | M. Razeti | Cagliari | [5 empty] | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.1.1 Cryogenic system | M. Razeti | Cagliari | [5 empty] | 35 | [15 empty] | 35 | [12 empty] | 0
3.2.2.1.2 Inner detector | M. Razeti | Cagliari | [5 empty] | 15 | [15 empty] | 15 | [12 empty] | 0
3.2.2.2.3 Pumping system | [7 empty] | 23 | [15 empty] | 23 | [12 empty] | 0
3.2.2.2 Veto and shielding systems | [7 empty] | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.2.1 Cosmic veto | [7 empty] | 10 | [15 empty] | 10 | [12 empty] | 0
3.2.2.2.2 Lead bricks | [7 empty] | 40 | [15 empty] | 40 | [12 empty] | 0
3.2.2.3 Readout electronics | [7 empty] | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.3.1 High voltage | W. Bonivento | Cagliari | [5 empty] | 12 | [15 empty] | 12 | [12 empty] | 0
3.2.2.3.2 Photon detectors | W. Bonivento | Cagliari | [5 empty] | 0 | [15 empty] | 0 | [12 empty] | 0
3.2.3.3.3 DAQ | [7 empty] | 10 | [15 empty] | 10 | [12 empty] | 0
3.2.2.4 Logistics | [7 empty] | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.4.1 Transportation to Seruci | [7 empty] | 4 | [15 empty] | 4 | [12 empty] | 0
3.2.2.4.2 Moving laboratory in container | M. Tuveri | Cagliari | [5 empty] | 5 | [15 empty] | 5 | [12 empty] | 0
3.2.2.4.3 Argon for tests | [7 empty] | 2 | [15 empty] | 2 | [12 empty] | 0
3.2.2.6 Data taking | [7 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.2.6.1 Tests at INFN CA | [7 empty] | 0 | [15 empty] | 0 | [12 empty] | 0
3.2.2.6.2 Run at Seruci | [7 empty] | 10 | [15 empty] | 10 | [12 empty] | 0
3.2.2.7 Underground lab | [7 empty] | 60 | [15 empty] | 60 | [12 empty] | 0
4 Infrastructures | An. Ianni | Princeton | [5 empty] | 255.1 | 0 | 457.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.6953 | 0 | 0 | 0 | 50 | 0 | 0 | 205.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 Infrastructures | F. Gabriele | LNGS | [5 empty] | 255.1 | 0 | 457.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.6953 | 0 | 0 | 0 | 50 | 0 | 0 | 205.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 Safety analysis | F. Gabriele | LNGS | [5 empty] | 50 | [14 empty] | 50 | [13 empty] | 0
4.1.2 Facilities | F. Gabriele | LNGS | [5 empty] | 205.1 | 0 | 457.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 205.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.2.1 Building | F. Gabriele | LNGS | [5 empty] | 205.1 | [17 empty] | 205.1 | [10 empty] | 0
4.1.2.5 Argon recovery cryostats | M. Boulay | Carleton | [6 empty] | 0 | 457.6953 | [8 empty] | 457.6953 | [17 empty] | 0
5 NOA Activities | E. Scapparone | Bologna | [5 empty] | 6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4194 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Clean Room | Al. Ianni | LNGS | [5 empty] | 2400 | [17 empty] | 2400 | [10 empty] | 0
5.2 Silicon packaging equipments | E. Scapparone | Bologna | [5 empty] | 3650 | [16 empty] | 3650 | [11 empty] | 0
5.3 LA-ICPMS | Al. Ianni | LNGS | [5 empty] | 0 | [16 empty] | 0 | [11 empty] | 0
5.4 Mechanical-3D | Al. Ianni | LNGS | [5 empty] | 244 | [16 empty] | 244 | [11 empty] | 0
5.5 NOA infrastructures | Al. Ianni | LNGS | [5 empty] | 200 | [16 empty] | 200 | [11 empty] | 0
5.6 Web site & outreach | Al. Ianni | LNGS | [5 empty] | 40 | [16 empty] | 40 | [11 empty] | 0
5.7 Travels | Al. Ianni | LNGS | [5 empty] | 60 | [16 empty] | 60 | [11 empty] | 0
4 DarkSide-50 | P. Meyers | Princeton | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 Technical & run coordination | N. Canci | LNGS | [20 empty] | 0 | [13 empty] | 0
4.2 Data monitoring | M. Wada | Princeton | [5 empty] | 0 | [28 empty] | 0
4.3 Physics coordination | J. Martoff | Temple | [5 empty] | 0 | [28 empty] | 0
4.3.1 Analysis | E. Pantic/S. Davini | UC Davis/Genova | [34 empty] | 0

## summary
Work Package | Responsible | Group | Core Cost [k€] | Core Cost [k$] | Core Cost [CAD] | Core Labor [k€] | Core Labor [k$] | Core Labor [CAD] | In Kind [k€] | In Kind [k$] | NSF Cap [k$] | NSF Labor [k$] | NSF In Kind [k$] | CFI CAP [CAD] | CFI Labor [CAD] | PNNL [k$] | INFN CSN2 [k€] | RAS MIUR [k€] | RA CIPE [k€] | INFN PON [k€] | INFN In Kind [k€] | INFN MP [k€] | STSFC [k€] | Spain [k€] | ETHZ [k€] | IHEP [k€] | IN2P3 In Kind [k€] | Poland [k€] | Russia [k€] | Common Funds [k€]
1 DarkSide-20k | An. Ianni | Princeton | 31862 | 3188.418 | 9645 | 1087 | 1554 | 1000 | 1975 | 600 | 3138.418 | 1554 | 600 | 9645 | 1000 | 50 | 6426 | 0 | 7742 | 14598 | 800 | 972 | 1000 | 1388 | 150.5223 | 0 | 100 | 510 | 600 | 700
2 Urania | M. Simeone/A. Renshaw | Napoli/Houston | 8049 | 4558 | 3864 | 0 | 754 | 560 | 0 | 400 | 4558 | 394 | 0 | 3864 | 560 | 760 | 0 | 8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 Aria | L. Mapelli/R. Tartaglia/ A. Devoto | Princeton/LNGS/Cagliari | 7599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7449 | 0 | 0 | 0 | 0 | 0 | 140 | 10 | 0 | 0 | 0 | 0 | 0
4 Infrastructures | An. Ianni | Princeton | 255.1 | 0 | 457.6953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457.6953 | 0 | 0 | 50 | 0 | 0 | 205.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 NOA Activities | E. Scapparone | Bologna | 6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4194 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totale | [27 empty] | 510
DarkSide-20k Project | C. Galbiati [G. Fiorillo] | Princeton/GSSI [Napoli] | 54359.1 | 7746.418 | 13966.6953 | 1087 | 2308 | 1560 | 1975 | 1000 | 7696.418 | 1948 | 600 | 13966.6953 | 1560 | 810 | 6476 | 15498 | 11936 | 17203.1 | 800 | 972 | 1000 | 1528 | 160.5223 | 0 | 100 | 510
| All values in k€ | INFN | NSF | CFI | PNNL | other | Common Funds
| 1 DarkSide-20k | 30538 | 4116.1561 | 7096.6667 | 43.8596 | 3748.5223 | 700 | 46243.2048
| 2 Urania | 8049 | 4343.8596 | 2949.3333 | 666.6667 | 0 | 0 | 16008.8596
| 3 Aria | 7449 | 0 | 0 | 0 | 150 | 0 | 7599
| 4 Infrastructures | 255.1 | 0 | 305.1302 | 0 | 0 | 0 | 560.2302
| 5 NOA Activities | 6594 | 0 | 0 | 0 | 0 | 0 | 6594
|  | 52885.1 | 8460.0158 | 10351.1302 | 710.5263 | 3898.5223 | 700 | 77005.2946